Items to clarify:

MONDAYS work

1. mechanical: chemo hood is in room and ready to be connected monday, the exhaust duct will be rerouted monday also and insulated.
2. The second hood wont fit thru the door and bob wiltbank is coming in wednesday to remove the wall so it can be brought into the room.

Electrical: The 2x2 lights are in and will be installed monday still waiting on the 2x4 lights which will be in the first of next week.

The electrician is running the power for the APS-1 unit on monday

Tusedays work
1. the control guy is coming to hook everything up

Thursdays work
The balance guy is coming to do his work

General discussion

All windows are sealed except one
sheet rock and paint is complete
floor covering removed and the floor needs to be cleaned
Smoke walls are complete
door locks are being changed to match the existing (I personally did not know we had to have a specific type)
Fire marshall will do another curtsy inspection

the project will be complete before the end of the year. Still no word from DHH for approval.