Owner

Engineer

Consultant

Contractor

PROJECT:						FIELD REPORT NUMBER: 12

Slidell Memorial Hospital					ENGINEER’S PROJECT NUMBER:  2185

Walgreens

Slidell, Louisiana

CONTRACT:  Renovation

DATE:  06/23/2014			             TIME: 10:02 AM	WEATHER: Clear	TEMP RANGE: 83°

EST % OF COMPLETION:  49%			CONFORMANCE WITH SCHEDULE (+/-):  On Schedule

WORK IN PROGRESS:  				PRESENT AT SITE:

Phase 2			    	                           Contractor, Electrician & Painter

OBSERVATIONS:

The knee wall and nurses station are to be constructed tomorrow. The electrician is running all his power and lighting requirements. The painter is preparing walls for primer. Wednesday the ceiling tiles will be installed. Friday the A/C mechanic will install the registers. Saturday the flooring contractor is scheduled to install the flooring.

ITEMS TO VERIFY:

INFORMATION OR ACTION REQUIRED:

ATTACHMENTS: