Owner

Engineer

Consultant

Contractor

PROJECT:						FIELD REPORT NUMBER: 13

Slidell Memorial Hospital					ENGINEER’S PROJECT NUMBER:  2185

Walgreens

Slidell, Louisiana

CONTRACT:  Renovation

DATE:  06/30/2014			             TIME: 10:30 AM	WEATHER: Clear	TEMP RANGE: 88°

EST % OF COMPLETION:  85%			CONFORMANCE WITH SCHEDULE (+/-):  On Schedule

WORK IN PROGRESS:  				PRESENT AT SITE:

Phase 2			    	                           Contractor, Electrician, Painter & Floor man

OBSERVATIONS:

The knee wall is constructed and being finished. The nurse’s station knee wall is constructed and waiting for cabinets and electrical tie-ins and staining. The ceiling tiles are 85% installed and are waiting for electrician, HVAC & sprinkler to be completed. The flooring contractor is onsite installing the flooring. This area is scheduled to be turned over on the 7th of July.

ITEMS TO VERIFY:

INFORMATION OR ACTION REQUIRED:

ATTACHMENTS: