Owner

Engineer

Consultant

Contractor

PROJECT:						FIELD REPORT NUMBER: 14

Slidell Memorial Hospital					ENGINEER’S PROJECT NUMBER:  2185

Walgreens

Slidell, Louisiana

CONTRACT:  Renovation

DATE:  07/07/2014			             TIME: 7:30 AM	WEATHER: Clear	TEMP RANGE: 77°

EST % OF COMPLETION:  95%			CONFORMANCE WITH SCHEDULE (+/-):  On Schedule

WORK IN PROGRESS:  				PRESENT AT SITE:

Phase 2			    	                           Contractor/Helpers

OBSERVATIONS:

The nurse’s station is constructed and waiting for cabinets and counter tops to be installed Tuesday. The hall doors are installed and waiting for the installation of the glass sidelites. The bathroom fixtures are to be installed today by the plumber. The carpet in the waiting area will be installed tomorrow. There are a number of punch list items that will be noted after the above items are installed. Today SMH is moving all their equipment into the cardio area. Demolition work will begin today in the Walgreens side.

ITEMS TO VERIFY:

INFORMATION OR ACTION REQUIRED:

ATTACHMENTS: