Owner

Engineer

Consultant

Contractor

PROJECT:						FIELD REPORT NUMBER: 17

Slidell Memorial Hospital					ENGINEER’S PROJECT NUMBER:  2185

Walgreens

Slidell, Louisiana

CONTRACT:  Renovation

DATE:  07/28/2014			             TIME: 2:00 PM	WEATHER: Cloudy   TEMP RANGE: 89°

EST % OF COMPLETION:  80%			CONFORMANCE WITH SCHEDULE (+/-):  On Schedule

WORK IN PROGRESS:  				PRESENT AT SITE:

Walgreens		    	                           Contractor/Helpers/Trades/Walgreens Subs

OBSERVATIONS:

Walgreens installers are installing cabinets, electricians are connecting all the wiring on the customer cabinets, and the painter is painting all walls. The ceiling lights, air diffusers, sprinkler heads are all in and the ceiling tiles will be installed tomorrow. Glass for all doors will be in Friday a long with flooring. The Cardio side punch list items will be completed by week’s end.

ITEMS TO VERIFY:

INFORMATION OR ACTION REQUIRED:

ATTACHMENTS: