% Complete	EVENT	START DATE	END DATE	RESPONSIBLE
	Bldg 10 SSC Govt Offices Project	7/22/11	10/21/11
	Develop layout dwgs	7/22/11	7/27/11	G. Moragne
	Finalize SOW	7/22/11	7/27/11	J. Berman
	Approval of SOW / dwgs	7/27/11	7/28/11	R. Pilcher/J.O Smith
	Obtain Architect Quotes	7/28/11	8/3/11	B. Uhle/K. Boudreaux
	IT Plan / Determine Cost	7/28/11	8/3/11	L. Tran
	Maintenance Plan / Cost	7/28/11	8/3/11	B. Uhle
	Outfit & Furnishings Cost	7/28/11	8/3/11	B. Uhle
	Generate / Submit CAR	8/3/11	8/5/11	J. Berman / B. Uhle
	CAR Approval	8/8/11	8/12/11	R. Pilcher
	Generate PRs / POs	8/15/11	8/19/11	K. Boudreaux
	On-Site Construction	9/6/11	9/30/11	Contractor
	IT Upgrades during Construction	9/19/11	10/77/11	L. Tran
	Outfit & Furnishings (Setup, Furniture, IT)	10/3/11	10/21/11	B. Uhle
	Mark Parking Spaces	10/20/11	10/21/11	B. Uhle
	Project Complete	10/21/11	10/21/11