## AIA form
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 2 OF 2 PAGES
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 1
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2014-09-25
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2014-09-25
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Mobilization | 1000 |  | 1000 |  | 1000 | 100% | 0 | 100
2 | Rough in office area | 6500 |  | 6500 | 1500 | 8000 | 123.1% | -1500 | 800
3 | rough in simulator area / A/C | 6300 |  | 820 | 1500 | 2320 | 36.83% | 3980 | 232
4 | wire feeders | 6300 |  |  |  | 0 | 0.00% | 6300 | 0
5 | lighting/ trim out | 11500 |  |  |  | 0 | 0.00% | 11500 | 0
6 | testing | 1000 |  |  |  | 0 | 0.00% | 1000 | 0
7 | [5 empty] | 0 |  | 0 | 0
8 | [5 empty] | 0 |  | 0 | 0
9 | [5 empty] | 0 |  | 0 | 0
10 | [5 empty] | 0 |  | 0 | 0
11 | [5 empty] | 0 |  | 0 | 0
12 | [5 empty] | 0 |  | 0 | 0
13 | [5 empty] | 0 |  | 0 | 0
14 | [5 empty] | 0 |  | 0 | 0
15 | [5 empty] | 0 |  | 0 | 0
16 | [5 empty] | 0 |  | 0 | 0
17 | [5 empty] | 0 |  | 0 | 0
18 | [5 empty] | 0 |  | 0 | 0
19 | [5 empty] | 0 |  | 0 | 0
20 | [5 empty] | 0 |  | 0 | 0
21 | [5 empty] | 0 |  | 0 | 0
22
|  | 32600 | 0 | 8320 | 3000 | 11320 |  | 21280 | 1132