## AIA form
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 2 OF 2 PAGES
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 4
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2013-11-22
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2013-11-22
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Demolition PS 231 Melody Lane | 1200 | 1200 | 0 |  | 1200 | 100% | 0 | 120
2 | Power Pole,Conduit Rough-in, Frame Fabrication | 13500 | 13500 | 0 |  | 13500 | 100% | 0 | 1350
3 | Controler Installation | 5580 | 5580 | 0 |  | 5580 | 100% | 0 | 558
4 | Pump Motor and Float Connections | 3678.35 | 3678.35 | 0 |  | 3678.35 | 100% | 0 | 367.835
5 | Finals | 2100 | 2100 | 0 |  | 2100 | 100% | 0 | 210
6 | [5 empty] | 0 |  | 0 | 0
7 | [5 empty] | 0 |  | 0 | 0
8 | Demolition PS32 Independence | 1200 | 600 | 600 |  | 1200 | 100% | 0 | 120
9 | Conduit Rough-in and Frame Fabrication | 13500 | 6700 | 6800 |  | 13500 | 100% | 0 | 1350
10 | Controler Installation | 5580 |  | 5580 |  | 5580 | 100% | 0 | 558
11 | Pump Motor and Float Connections | 3678.35 |  | 3678.35 |  | 3678.35 | 100% | 0 | 367.835
12 | Finals | 2100 |  | 2100 |  | 2100 | 100% | 0 | 210
13 | [5 empty] | 0 |  | 0 | 0
14 | [5 empty] | 0 |  | 0 | 0
15 | Demolition PS203 Youpon | 1200 |  |  |  | 0 | 0.00% | 1200 | 0
16 | Conduit Rough-in and Frame Fabrication | 13500 |  |  |  | 0 | 0.00% | 13500 | 0
17 | Controler Installation | 5580 |  |  |  | 0 | 0.00% | 5580 | 0
18 | Pump Motor and Float Connections | 3678.35 |  |  |  | 0 | 0.00% | 3678.35 | 0
19 | Finals | 2100 |  |  |  | 0 | 0.00% | 2100 | 0
20 | [5 empty] | 0 |  | 0 | 0
21 | [5 empty] | 0 |  | 0 | 0
22
|  | 78175.05 | 33358.35 | 18758.35 | 0 | 52116.7 |  | 26058.35 | 5211.67