## AIA form
APPLICATION AND CERTIFICATE FOR PAYMENT | [5 empty] | Computerized Replication of AIA Document G702 |  |  |  | Page __1_ of __2_ Pages
| To OWNER: | Gottfried Contracting, LLC |  | PROJECT: | PEC No. 11093.06 |  |  | APPLICATION NO: | 1 | Distribution to:
|  | 6 Meyers Rd. | [5 empty] | PERIOD TO: | 2015-10-31 | Owner
|  | Covington, LA 70435 | [5 empty] | PROJECT NOS.: | 407-004 | Architect
[9 empty] | 16000 | Contractor | x
| From CONTRACTOR: | Gulf Coast Electric Co., LLC |  | VIA ARCHITECT: |  |  |  | CONTRACT DATE: | 2015-03-27
554 Old Spanish Trail
Slidell, LA 70458
| Contract for: | Mandeville Lift Stations 22, 23, & 33 Improvements
CONTRACTOR'S APPLICATION FOR PAYMENT
Application is made for payment, as shown below, in connection with the Contract
Continuation Sheet attached.
1. | Original Contract Sum . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 19200 |  | CONTRACTOR:
2. | Net Change by Change Order . . . . . . . . . . . . . . . . . . . . . | [5 empty] | By: ________________________________________ Date:__________________
3. | Contract Sum to Date (Line 1 + 2) . . . . . . . . . . . . . . . . . . . . |  |  |  | 19200 |  | State of:
County of:
4. | Total Completed and Stored to Date . . . . . . . . . . . . . . . |  |  |  | 3100 |  | Subscribed and sworn to before
| (Column G on G703) | [5 empty] | me this day of
5. | Retainage:
|  | a 10% of Completed Work |  | 310
|  | (Columns D + E on G703) |  |  |  |  | Notary Public:
|  | b 0 % OF Stored Materials |  |  |  |  | My Commission expires:
(Columns F on G703)
|  | Total Retainage (Line 5a + 5b or |  |  |  |  | ARCHITECT'S APPLICATION FOR PAYMENT
|  | Total in Column I G703) . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | 310
Plus line item demobilization deduct
6. | Total Earned Less Retainage . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 2790
( Line 4 less Line 5 Total)
7. | Less Previous Certificates for Payment . . . . . . . . . . . . |  |  |  | 0
| (Line 6 from Prior Certificate) | [5 empty] | AMOUNT CERTIFIED . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | $_________________
8. | Current Payment Due . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 2790
9. | Balance to Finish, Including Retainage |  |  | 16410
| (Line 3 less Line 6) | [5 empty] | ARCHITECT:
By: ________________________________________ Date:__________________
| CHANGE ORDER SUMMARY |  |  | ADDITIONS | DEDUCTIONS
Total changes approved in
| previous months by Owner |  |  |  | 0
Total approved this month
Totals
| NET CHANGES by Change order |  |  | 0

## Sheet2
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 2 OF 2 PAGES
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 1
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2015-10-26
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2015-10-31
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Lift station 22
2 | mobilization | 600 |  | 600 |  | 600 | 100% | 0 | 60
3 | Demolition | 600 |  | 600 |  | 600 | 100% | 0 | 60
4 | under ground pipe | 1500 |  | 1500 |  | 1500 | 100% | 0 | 150
5 | Equipment install | 2000 |  | 400 |  | 400 | 20% | 1600 | 40
6 | Start up and testing | 1700 |  |  |  | 0 | 0% | 1700 | 0
7
8 | Lift station 23
9 | mobilization | 600 |  |  |  | 0 | 0.00% | 600 | 0
10 | Demolition | 600 |  |  |  | 0 | 0.00% | 600 | 0
11 | under ground pipe | 1500 |  |  |  | 0 | 0.00% | 1500 | 0
12 | Equipment install | 2000 |  |  |  | 0 |  | 2000 | 0
13 | Start up and testing | 1700 |  |  |  | 0 | 0.00% | 1700 | 0
14
15 | Lift station 33
16 | mobilization | 600 |  |  |  | 0 | 0.00% | 600 | 0
17 | Demolition | 600 |  |  |  | 0 | 0.00% | 600 | 0
18 | under ground pipe | 1500 |  |  |  | 0 | 0.00% | 1500 | 0
19 | Equipment install | 2000 |  |  |  | 0 | 0.00% | 2000 | 0
20 | Start up and testing | 1700 |  |  |  | 0 | 0.00% | 1700 | 0
21 | [5 empty] | 0 |  | 0 | 0
22 | contract completion
|  | 19200 | 0 | 3100 | 0 | 3100 |  | 16100 | 310