## Sheet1
[14 empty] | ESTIMATED |  |  |  | Work Schedule
|  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9
|  | Apri |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  | November |  | December | January
F | 1 |  |  | S | 1 |  |  | W | 1 | Treme |  | F | 1 |  |  | M | 1 |  |  | T | 1 |  |  |  | S |  |  | T |  | T
S | 2 |  |  | M | 2 | Rough-in |  | T | 2 | K6/K6 RI |  | S | 2 |  |  | T | 2 |  |  | F | 2 |  |  |  | S |  |  | W |  | F
S | 3 |  |  | T | 3 | Kaufman |  | F | 3 | Bldg 213 |  | S | 3 |  |  | W | 3 |  |  | S | 3 |  |  |  | M |  |  | T |  | S
M | 4 |  |  | W | 4 |  |  | S | 4 | Bldg 215 |  | M | 4 | Treme |  | T | 4 |  |  | S | 4 |  |  |  | T |  |  | F |  | S
T | 5 |  |  | T | 5 |  |  | S | 5 |  |  | T | 5 | C2/K6 RI |  | F | 5 | Treme |  | M | 5 |  |  |  | W |  |  | S |  | M
W | 6 |  |  | F | 6 |  |  | M | 6 |  |  | W | 6 | RI 218-109 |  | S | 6 |  |  | T | 6 |  |  |  | T |  |  | S |  | T
T | 7 |  |  | S | 7 |  |  | T | 7 | Marcos |  | T | 7 |  |  | S | 7 |  |  | W | 7 |  |  |  | F |  |  | M |  | W
F | 8 |  |  | S | 8 |  |  | W | 8 | W Bank | Treme | F | 8 |  |  | M | 8 |  |  | T | 8 |  |  |  | S |  |  | T |  | T
S | 9 |  |  | M | 9 | Welbilt |  | T | 9 |  | K6/K6 RI | S | 9 |  |  | T | 9 | K6/K6 TO |  | F | 9 |  |  |  | S |  |  | W |  | F
S | 10 |  |  | T | 10 | Madison |  | F | 10 |  | Bldg 207 | S | 10 |  |  | W | 10 | Bldg 207 |  | S | 10 |  |  |  | M |  |  | T |  | S
M | 11 |  |  | W | 11 |  |  | S | 11 |  | Bldg 220 | M | 11 | Marcos |  | T | 11 | Bldg 220 |  | S | 11 |  |  |  | T |  |  | F |  | S
T | 12 |  |  | T | 12 |  |  | S | 12 |  |  | T | 12 | Meterie |  | F | 12 |  |  | M | 12 |  |  |  | W |  |  | S |  | M
W | 13 | trim out Tuscany |  | F | 13 |  |  | M | 13 |  |  | W | 13 |  |  | S | 13 |  |  | T | 13 |  |  |  | T |  |  | S |  | T
T | 14 |  |  | S | 14 |  |  | T | 14 |  |  | T | 14 |  |  | S | 14 |  |  | W | 14 |  |  |  | F |  |  | M |  | W
F | 15 |  |  | S | 15 |  |  | W | 15 |  |  | F | 15 |  |  | M | 15 |  |  | T | 15 |  |  |  | S |  |  | T |  | T
S | 16 |  |  | M | 16 | Welbilt |  | T | 16 |  |  | S | 16 |  |  | T | 16 |  |  | F | 16 |  |  |  | S |  |  | W |  | F
S | 17 |  |  | T | 17 | Madison |  | F | 17 |  |  | S | 17 |  |  | W | 17 |  |  | S | 17 |  |  |  | M |  |  | T |  | S
M | 18 | Set temp poles N.O |  | W | 18 |  |  | S | 18 |  |  | M | 18 |  |  | T | 18 |  |  | S | 18 |  |  |  | T |  |  | F |  | S
T | 19 |  |  | T | 19 |  |  | S | 19 |  |  | T | 19 |  | Treme | F | 19 |  |  | M | 19 |  |  |  | W |  |  | S |  | M
W | 20 | Call inspec Tuscany |  | F | 20 |  |  | M | 20 | Marcos |  | W | 20 |  | K6/K6 TO | S | 20 |  |  | T | 20 |  |  |  | T |  |  | S |  | T
T | 21 | Bldg 213 | 215 UG | S | 21 |  |  | T | 21 | Madiville |  | T | 21 |  | Bldg 213 | S | 21 |  |  | W | 21 |  |  |  | F |  |  | M |  | W
F | 22 | Bldg 207 | 220 UG | S | 22 |  |  | W | 22 |  |  | F | 22 |  | Bldg 215 | M | 22 | Treme |  | T | 22 |  |  |  | S |  |  | T |  | T
S | 23 |  |  | M | 23 | Treme |  | T | 23 |  |  | S | 23 |  |  | T | 23 | C2/K6 TO |  | F | 23 |  |  |  | S |  |  | W |  | F
S | 24 |  |  | T | 24 | K6/K6 RI |  | F | 24 |  | Treme | S | 24 |  |  | W | 24 | Bldg 218 |  | S | 24 |  |  |  | M |  |  | T |  | S
M | 25 | Derick Dr | UG 218/219 | W | 25 | Bldg 213 |  | S | 25 |  |  | M | 25 |  |  | T | 25 | Bldg 109 |  | S | 25 |  |  |  | T |  |  | F |  | S
T | 26 | 7:00 |  | T | 26 | Bldg 215 |  | S | 26 |  |  | T | 26 |  |  | F | 26 |  |  | M | 26 |  |  |  | W |  |  | S |  | M
W | 27 |  |  | F | 27 |  |  | M | 27 | Marcos | C2/K6 | W | 27 |  |  | S | 27 |  |  | T | 27 |  |  |  | T |  |  | S |  | T
T | 28 |  |  | S | 28 |  |  | T | 28 | Madiville | RI 218-109 | T | 28 |  |  | S | 28 |  |  | W | 28 |  |  |  | F |  |  | M |  | W
F | 29 |  |  | S | 29 |  |  | W | 29 |  |  | F | 29 |  |  | M | 29 |  |  | T | 29 |  |  |  | S |  |  | T |  | T
S | 30 |  |  | M | 30 |  |  | T | 30 |  |  | S | 30 |  |  | T | 30 |  |  | F | 30 |  |  |  | S |  |  | W |  | F
|  |  |  | T | 31 | [6 empty] | S | 31 |  |  | W | 31 |  |  |  | 31 |  |  |  | M |  |  |  |  | S
Welbilt
N Covington
Abita
MS
Cypres Lake
[14 empty] | ESTIMATED |  |  |  | Work Schedule
|  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  |  | 10 |  | 11
|  | Apri |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  | November |  | December | January
F | 1 |  |  | S | 1 |  |  | W | 1 |  | Welbilt | F | 1 |  |  | M | 1 | Treme |  | T | 1 | TREME RI | TREME TO |  | S | 1 |  | T |  | T
S | 2 |  |  | M | 2 | Welbilt | Welbilt | T | 2 | D2/C1 RI | Madisonv | S | 2 |  |  | T | 2 | T/O 117 | FDP RI | F | 2 | 217/219 | 216/214 |  | S | 2 |  | W |  | F
S | 3 |  |  | T | 3 | Welbilt | Madisonv | F | 3 | 93/95 |  | S | 3 |  |  | W | 3 | 221 |  | S | 3 |  |  |  | M | 3 |  | T |  | S
M | 4 |  |  | W | 4 | Kaufman |  | S | 4 |  |  | M | 4 |  | Car wash | T | 4 |  |  | S | 4 |  |  |  | T | 4 |  | F |  | S
T | 5 |  |  | T | 5 | Rough-in |  | S | 5 |  |  | T | 5 |  |  | F | 5 |  |  | M | 5 |  |  |  | W | 5 |  | S |  | M
W | 6 |  |  | F | 6 |  |  | M | 6 |  |  | W | 6 |  |  | S | 6 |  |  | T | 6 |  |  |  | T | 6 |  | S |  | T
T | 7 |  |  | S | 7 |  |  | T | 7 |  |  | T | 7 |  |  | S | 7 |  |  | W | 7 |  |  |  | F | 7 | TREME TO 217/219 | M |  | W
F | 8 |  |  | S | 8 |  |  | W | 8 |  |  | F | 8 |  | Car wash | M | 8 |  |  | T | 8 |  | TREME TO |  | S | 8 |  | T |  | T
S | 9 |  |  | M | 9 | Kaufman | UG J6/E1 | T | 9 |  |  | S | 9 |  |  | T | 9 |  |  | F | 9 |  | 117/221 |  | S | 9 |  | W |  | F
S | 10 |  |  | T | 10 | Rough-in | 216/214 | F | 10 |  |  | S | 10 |  |  | W | 10 | Treme |  | S | 10 |  |  |  | M | 10 |  | T |  | S
M | 11 |  |  | W | 11 | 703 Toma | Outback St | S | 11 |  |  | M | 11 |  | Car wash | T | 11 | T/O 108 |  | S | 11 |  |  |  | T | 11 |  | F |  | S
T | 12 |  |  | T | 12 |  | Outback St | S | 12 |  |  | T | 12 | TREME |  | F | 12 | 219 |  | M | 12 |  |  | FDP Tout | W | 12 |  | S |  | M
W | 13 | trim out Tuscany |  | F | 13 |  | Three Devas | M | 13 |  | Car wash | W | 13 | RI 119 |  | S | 13 |  |  | T | 13 |  |  |  | T | 13 |  | S |  | T
T | 14 |  |  | S | 14 |  |  | T | 14 | Marcos |  | T | 14 | 121 |  | S | 14 |  |  | W | 14 |  |  |  | F | 14 |  | M |  | W
F | 15 |  |  | S | 15 |  |  | W | 15 | W Bank |  | F | 15 | 123 | Car wash | M | 15 |  |  | T | 15 |  |  |  | S | 15 |  | T |  | T
S | 16 |  |  | M | 16 |  | Outback St | T | 16 |  |  | S | 16 |  |  | T | 16 |  |  | F | 16 |  |  |  | S | 16 |  | W |  | F
S | 17 |  |  | T | 17 | Derick Dr |  | F | 17 |  | FDP UG Con | S | 17 |  |  | W | 17 |  |  | S | 17 |  |  |  | M | 17 |  | T |  | S
M | 18 | Set temp poles N.O |  | W | 18 | 7:00 | Rough-in | S | 18 |  |  | M | 18 |  |  | T | 18 |  |  | S | 18 |  |  |  | T | 18 |  | F |  | S
T | 19 |  |  | T | 19 | Kaufman | Kaufman | S | 19 |  |  | T | 19 |  | A1/E1 TO | F | 19 | TREME RI | TREME TO | M | 19 | TREME TO |  | FDP Tout | W | 19 |  | S |  | M
W | 20 | Call inspec Tuscany |  | F | 20 | Center St. | Center St. | M | 20 | Marcos | FDP UG Con | W | 20 |  | 66/64 | S | 20 |  |  | T | 20 | 108/219 |  |  | T | 20 |  | S |  | T
T | 21 |  |  | S | 21 |  |  | T | 21 | W Bank |  | T | 21 | TREME |  | S | 21 |  |  | W | 21 |  |  |  | F | 21 |  | M |  | W
F | 22 |  |  | S | 22 |  |  | W | 22 |  |  | F | 22 | RI 216/214 |  | M | 22 | 120/122 | 119/121 | T | 22 |  |  |  | S | 22 |  | T |  | T
S | 23 |  |  | M | 23 | FDP T Pole | Welbilt | T | 23 |  |  | S | 23 |  |  | T | 23 |  | 123 | F | 23 |  |  |  | S | 23 |  | W |  | F
S | 24 |  |  | T | 24 | A1/E1 RI | Madisonvil | F | 24 |  |  | S | 24 |  |  | W | 24 |  |  | S | 24 |  |  |  | M | 24 |  | T |  | S
M | 25 | Derick Dr | Welbilt | W | 25 | 66/64 |  | S | 25 |  |  | M | 25 |  |  | T | 25 |  |  | S | 25 |  |  |  | T | 25 |  | F |  | S
T | 26 | 7:00 | Suite 3 | T | 26 |  |  | S | 26 |  |  | T | 26 | Marcos | D2/C1 TO | F | 26 |  |  | M | 26 |  |  |  | W | 26 |  | S |  | M
W | 27 | SC |  | F | 27 |  |  | M | 27 | Marcos | Car wash | W | 27 | Mand | 93/95 | S | 27 |  |  | T | 27 |  |  |  | T | 27 |  | S |  | T
T | 28 | Welbilt | Welbilt | S | 28 |  |  | T | 28 | W Bank |  | T | 28 |  |  | S | 28 |  |  | W | 28 | TREME TO |  |  | F | 28 |  | M |  | W
F | 29 | Welbilt | Welbilt | S | 29 |  |  | W | 29 |  |  | F | 29 |  |  | M | 29 |  |  | T | 29 | 120/122 |  |  | S | 29 |  | T |  | T
S | 30 |  |  | M | 30 | Holliday |  | T | 30 |  |  | S | 30 |  |  | T | 30 | TREME RI | TREME TO | F | 30 |  |  |  | S | 30 |  | W |  | F
|  |  |  | T | 31 | Derick Dr. | [5 empty] | S | 31 |  |  | W | 31 | 217/219 | 216/214 | [5 empty] | M | 31 |  |  |  | S
[6 empty] | Welbilt | 5-houses |  |  | Marcos | west bank
[6 empty] | Olimpic | Demo Gap |  |  | Kaufman | 3 houses
[6 empty] | Olimpic | Fire Station |  |  | Novia | house
[6 empty] | Olimpic | Restraunt |  |  | Kaufman | Car wash
Note on M7: owner: Independence Day
Note on V8: owner: Labor Day
Note on AA34: owner: Holloween
Note on M48: owner: Independence Day
Note on V49: owner: Labor Day
Note on H55: owner: Outback Steak House Slidell, Mindy
Note on AA75: owner: Holloween