## Sheet1
Bid Dates | Scope Design | Scope of Work
2013-06-26 | Original Scope Design | Replace gravity fed service laterals and repair the main & install CIPP in the mainline
2014-05-21 | Original Scope Design | Replace gravity fed service laterals and repair the main & install CIPP in the mainline
RFP 02 dated 7/26/2013 to video the service laterals
2014-08-28 | Change Design New Scope | Install Lift Stations for each of the laterals supporting the buildings and repair the main & install CIPP in the mainline
Not issued for Bid | No Change in Scope 5/14/2015 | Complete set generated but never published for bid
1/21/2016 Bid Canceled | Change Design New Scope | Replace gravity fed service laterals except at Bldg 21 the Mechanical Room where a lift station would be installed; repair the main but do not install CIPP in the mainline. Bid canceled due to not having a Levee Permit
2017-03-07 | Change Design New Scope | Replace gravity fed service laterals, do not install the Lift Station at Bldg 21, do not repair the main nor install CIPP in the mainline