## Sheet1
1 |  | Install 6 Adjustment Rings on ManHoles |  |  |  | Missing MH-25
2 |  | Construct a Concrete Pad around MH-12 |  |  |  | Change Order?
3A |  | MainLine Repair Tap - Gym CO |  |  |  | Change Order?
3B |  | MainLine Repair Tap |  |  |  | Complete
3C |  | MainLine Repair Tap |  |  |  | Complete
3D |  | MainLine Replace Tap |  |  |  | Complete
| Bldg(s) | Contract Length of Pipe |  |  | Completed Length of Pipe
4A | Admin Gym | 185 | FT OF PIPE |  | 185 | FT OF PIPE
4B | Admin | 38 | FT OF PIPE |  | 38 | FT OF PIPE
4C | Admin End | 101.6 | FT OF PIPE |  | 101.6 | FT OF PIPE
4D | Gym | 143 | FT OF PIPE |  | 143 | FT OF PIPE
4E | Mental Health | 10 | FT OF PIPE |  | 10 | FT OF PIPE
4F | Bldg K | 175 | FT OF PIPE |  | 75 | FT OF PIPE
4G | Bldg K | 180 | FT OF PIPE |  |  | FT OF PIPE
4H | Bldg K | 10 | FT OF PIPE |  | 10 | FT OF PIPE
4J | Bldg K | 180 | FT OF PIPE |  |  | FT OF PIPE
4K | Res #1, #2, #3 | 100 | FT OF PIPE |  | 100 | FT OF PIPE
4L | Res #1, #2, #3 | 94 | FT OF PIPE |  | 94 | FT OF PIPE
4M | Res #1, #2, #3 | 10 | FT OF PIPE |  | 10 | FT OF PIPE
4N | Bldg 9 New School House |  |  | Hydro Jet &C/O
4O | Bldg 10 Movie |  |  | Hydro Jet &C/O
4P | Bldg 11 Old School House |  |  | Hydro Jet &C/O
4Q | Bldg 12 New School House | 80 | FT OF PIPE |  | 80 | FT OF PIPE
4R | Dining Hall | 245 | FT OF PIPE |  | 245 | FT OF PIPE
4S | Bldg J | 100 | FT OF PIPE |  | 100 | FT OF PIPE
4T | Bldg J | 100 | FT OF PIPE |  | 100 | FT OF PIPE
4U | Bldg J | 90 | FT OF PIPE |  | 90 | FT OF PIPE
4V | Infirmary Toilet to Bldg J | 70 | FT OF PIPE |  | 70 | FT OF PIPE
4W | Infirmary Main | 120 | FT OF PIPE |  | 120 | FT OF PIPE
4X | Res. 17 Parking | 60 | FT OF PIPE |  | 60 | FT OF PIPE
4Y | Res. 19 Parking | 35 | FT OF PIPE |  | 35 | FT OF PIPE
4Z | Director Res |  |  | Hydro Jet &C/O
4AA | Clean-Out Near Front Gate | 45 | FT OF PIPE |  | 45 | FT OF PIPE
4BB | Mechanical Toilet | 30 | FT OF PIPE |  | 30 | FT OF PIPE
4CC | Laundry |  |  | Hydro Jet
4DD | Pavilion | 95 | FT OF PIPE |  | 95 | FT OF PIPE
Change Order #1 | Add Connection at Admin | 40 | FT OF PIPE |  | 40 | FT OF PIPE
Change Order #2 | Days for Mississippi River
Change Order #3 | 4A, 4C & 4D changed length above, 4BB added C/O to LeanTo, #2 Revised size of concrete pad, 4DD reduced length of pipe
Change Order #4 | Add Bldg J Drinking Fountain | 42 | FT OF PIPE |  | 42 | FT OF PIPE
Change Order #5 | Time Spent on Digging
Change Order #6 | Time Spent on Digging
% Complete
Total |  | 2378.6 | FT OF PIPE |  | 1918.6 | FT OF PIPE | 80.66%