Estimated timeline without dates:

We do estimate bid documents for 8/26/2019 (Julian Date 238)

Time between bid documents and actual advertisement			7 days

Bid advertisement 								30 days

(Pre-Bid Conference to be on Bid Advertisement)

Engineer to provide feedback on contractors bid 				7 days

Sign low bid contractor for project						14 days

Limited Notice to Proceed, This will be adjusted by GC

Lead time on ordering AHU( 1 Week Review & 10 Weeks)			80 days

Construction Notice to Proceed

Contractor starts work after AHU ships					90 days