## Sheet1
Request for Information
Rotolo Consultants, Inc.
894 Robert Blvd. Slidell, LA 70458 Phone: 985-643-2427 FAX 985-643-2691
Project Name: | Springs @ Fremaux
Project Location: | Slidell, Louisiana
Date: | 2014-08-04
Project Number:
ACC Project Number:
RFI #: | 1
Inquiring Company: | Rotolo Consultants, Inc.
894 Robert Boulevard
Slidell, Louisiana 70458
Inquiry By: | John Tipton
QUESTION:
Exhibit C -Division 05000 #2 Calls out that the downs spouts shall be 3"x5" - what type of down spout adapter is to be used to connect the down spouts to the subsurface drainage? The scope spread sheet says down spout tie in (materials by others), can you provide a detail showing the connection? What size pipe will the down spouts be tying into? Will the subsurface drainage be stubbed up at the point of future down spout connection?
Answer Required By:
Cost Impact:
Schedule Impact:
Responding Company: | Doster Construction
Answered By: | Heather R. Gallagher
ANSWER:
See attached Sheet D-4. The Downspouts are 3" x 4" as indicated in the Architectural Drawings. The piping will
not be stubbed up for connection. Rotolo will be required to get the downspout boot connection as well as the
piping to the 'T' at the 6" PVC Storm Pipe.
Contact Name:
Contact Phone:
Date Answered: