## blank aia front
APPLICATION AND CERTIFICATE FOR PAYMENT | [5 empty] | Computerized Replication of AIA Document G702 |  |  |  | Page __1_ of __2_ Pages
|  | To OWNER: | Gottfried Contracting, LLC | PROJECT: | NASJRB - Belle Chasse |  |  | APPLICATION NO: | 1 | Distribution to:
|  |  | 6 Meyers Rd. |  | Renovations to Building 385 |  |  | PERIOD TO: | 2014-09-25 | Owner
|  |  | Covington, LA 70435 |  | W912NR-09-D-0001/0013 |  |  | PROJECT NOS.: | SC 391-001 | Architect
[10 empty] | Contractor | x
|  | From CONTRACTOR: | Gulf Coast Electric Co., LLC | VIA ARCHITECT: |  |  |  | CONTRACT DATE: | 2014-08-04
554 Old Spanish Trail
Slidell, LA 70458
| Contract for: |  | NASJRB - Belle Chasse
CONTRACTOR'S APPLICATION FOR PAYMENT
Application is made for payment, as shown below, in connection with the Contract
Continuation Sheet attached.
1. | Original Contract Sum . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 32600 |  | CONTRACTOR:
2. | Net Change by Change Order . . . . . . . . . . . . . . . . . . . . . |  |  |  | 0 |  | By: ________________________________________ Date:__________________
3. | Contract Sum to Date (Line 1 + 2) . . . . . . . . . . . . . . . . . . . . |  |  |  | 32600 |  | State of:
County of:
4. | Total Completed and Stored to Date . . . . . . . . . . . . . . . |  |  |  | 6100 |  | Subscribed and sworn to before
| (Column G on G703) | [5 empty] | me this day of
5. | Retainage:
|  | a _% of Completed Work |  | 610
|  | (Columns D + E on G703) |  |  |  |  | Notary Public:
|  | b 0 % OF Stored Materials |  |  |  |  | My Commission expires:
(Columns F on G703)
|  | Total Retainage (Line 5a + 5b or |  |  |  |  | ARCHITECT'S APPLICATION FOR PAYMENT
|  | Total in Column I G703) . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | 610
Plus line item demobilization deduct
6. | Total Earned Less Retainage . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 5490
( Line 4 less Line 5 Total)
7. | Less Previous Certificates for Payment . . . . . . . . . . . . |  |  |  | 0
| (Line 6 from Prior Certificate) | [5 empty] | AMOUNT CERTIFIED . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | $_________________
8. | Current Payment Due . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 5490
9. | Balance to Finish, Including Retainage |  |  | 27110
| (Line 3 less Line 6) | [5 empty] | ARCHITECT:
By: ________________________________________ Date:__________________
| CHANGE ORDER SUMMARY |  |  | ADDITIONS | DEDUCTIONS
| Total changes approved in |  |  | 0
| previous months by Owner |  |  |  | 0
| Total approved this month |  |  | 0
|  |  | Totals | 0
| NET CHANGES by Change order |  |  | 0