## AIA form
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 2 OF 2 PAGES
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 2
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2014-11-25
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2014-11-30
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Mobilization | 500 | 500 | 0 |  | 500 | 100% | 0 | 50
2 | 120V Receptacles in office | 2500 | 2000 | 500 |  | 2500 | 100% | 0 | 250
3 | Receptacles in rear engine shop | 4100 | 3300 | 800 |  | 4100 | 100% | 0 | 410
4 | 120V Receptacles in front Engine Shop | 4800 |  | 4800 |  | 4800 | 100% | 0 | 480
5 | lower lighting in two offices | 800 | 300 | 500 |  | 800 | 100% | 0 | 80
6 | 480V panelboard and disconnect | 16000 |  | 16000 |  | 16000 | 100% | 0 | 1600
7 | Testing | 3900 |  | 3900 |  | 3900 | 100% | 0 | 390
8 | [5 empty] | 0 |  | 0 | 0
9 | [5 empty] | 0 |  | 0 | 0
10 | [5 empty] | 0 |  | 0 | 0
11 | [5 empty] | 0 |  | 0 | 0
12 | [5 empty] | 0 |  | 0 | 0
13 | [5 empty] | 0 |  | 0 | 0
14 | [5 empty] | 0 |  | 0 | 0
15 | [5 empty] | 0 |  | 0 | 0
16 | [5 empty] | 0 |  | 0 | 0
17 | [5 empty] | 0 |  | 0 | 0
18 | [5 empty] | 0 |  | 0 | 0
19 | [5 empty] | 0 |  | 0 | 0
20 | [5 empty] | 0 |  | 0 | 0
21 | [5 empty] | 0 |  | 0 | 0
22
|  | 32600 | 6100 | 26500 | 0 | 32600 |  | 0 | 3260