## Sheet1
CHANGE ORDER PROPOSAL REQUEST
DATE: | 2017-07-31 | PROPOSAL REQUEST NO. |  | 1
PROJECT: | Bridge City Center For Youth | FROM ENGINEER: | Dammon Engineering
Sewer System Renovation
08-403-11-01, Part 01 & 08-403-04B-01, Part 20 & 01-107-06B-11, Part U7
OWNER: | State Of Louisiana | CONTRACTOR: | ARC Mechanical Contractors, Inc
Facility Planning & Control
Please submit an itemized proposal for changes in the Contract Sum and Contract Time for proposed modifications to the Contract Documents described herein within ten (10) days. The Contractor must submit this proposal or notify the Architect, in writing, of the date on which proposal submission is anticipated.
THIS IS NOT A CHANGE ORDER, A CONSTRUCTION CHANGE DIRECTIVE OR A DIRECTION TO PROCEED WITH THE WORK DESCRIBED IN THE PROPOSED MODIFICATIONS.
DESCRIPTION OF WORK:
1. A. Terminate the line along the Admin Bldg at the existing duct bank interferes with the continuation of service lateral. Install clean-out. Sheet C2 Note # 4A Sheet C102. Is amended to read "INSTALL NEW 6" LATERAL TO MH-19, MAKE NEW 6" CONNECTION IN MANHOLE, MAKE APPROPRIATE CONNECTIONS FOR SIDE LATERALS. APPROXIMATE LENGTH (230FT) 172FT. CONCRETE CUTTING & PATCHING REQUIRED. " (CREDIT FOR 58 FT OF 6" PIPE NOT INSTALLED. ALSO CREDIT FOR ITEM 4C = 55FT OF 4" AND 4D = 185FT OF 6" )
1. B. Repair existing service lateral between Gym and sewer mainline. Sheet C2 Note # 4C is amended to read " INSTALL NEW 4" LATERAL WITH NEW CLEAN-OUT(S) CONNECT TO NEW SERVICE LATERAL AT APPROXIMATELY 65 FT AS MEASURED FROM THE END OF THE EXISTING SERVICE LATERAL. APPROXIMATE LENGTH (55FT) 117.4 FT OF 4" PIPE." Sheet C2 Note #4D is amended to read " INSTALL NEW 6" LATERAL WITH NEW CLEAN-OUTS CONNECT TO EXISTING SERVICE LATERAL AT APPROXIMATELY 75 FT AS MEASURED FROM THE END OF THE EXISTING SERVICE LATERAL AT CORNER OF GYMN. APPROXIMATE LENGTH OF PIPE (185FT) 154.6 FT OF 6" PIPE. UNEARTH CLEAN-OUT ON EXISTING SERVICE LATERAL AND INSTALL AN ACCESS COVER, CLEAN-OUT IS LOCATED AT APPROXIMATELY 63.6 FT MEASURED FROM THE MAINLINE TOWARD THE GYM. REPAIR A BREAK IN THE EXISTING LATERAL LOCATED APPROXIMATELY 157.75FT AS MEASURED FROM THE END OF THE SERVICE LATERAL NEXT TO THE GYM AND INSTALL CLEAN-OUT.
2. Sheet C2 Note # 4BB is amended to include the installation of clean-out where sewer line above the parking area of the Directors Residence Bldg 20 turns down, next to Bldg 19, and enters the ground. Video the line from this point to the clean-out next to Bldg 21, this line goes under the drive to the parking area of Bldg 20.
3. Sheet C2 Note C-2 item #2 is amended " CONTRACTOR SHALL CONSTRUCT A 10'x10'x8" CONCRETE PAD AROUND MH-12, REDUCE ELEVATION OF MANHOLE COVER TO BE NO MORE THAN 3 INCHES ABOVE LOCAL GRADE. REPLACE MANHOLE COVER AND FRAME WITH ONES THAT MEET AASHTO M306 TRAFFIC RATINGS. DETAILS 3A AND 3B HAVE BEEN REVISED SEE SHEET C-4. Provide credit for bollards not installed.
4. Abandon existing manhole discovered next to Residence Building 06.
5. Provide credit for remainder of lateral that was not installed at the Pavillion. Sheet C2 Note 4DD. Estimated 180 ft, installed 95 ft.
ATTACHMENTS:
SHEET C3 & C4
REQUESTED BY ENGINEER:
Signature