Meeting minutes at BCCY 2-8-2013

Meeting attendants: 	Lance Daniels, Director BCCY

Sterling White, Asst Maintenance Director BCCY

Hart, Richard, Operations Supervisor

David Dammon, Dammon Engineering

Kevin Kinchen, Dammon Engineering

- Contractor’s work time inside the BCCY security campus:

Start Time:	7:00		Stop Time:	3:30		Monday through Friday

We discussed that during the relining process of the main sewer piping it will require certain buildings to be without sewer service during that day and the possibility of extending the work day for these certain events.  Example, the contractor must block sewage coming from certain buildings because they connect to the Sewer Main between manholes.  The contractor must complete the work causing the outage and reopen the sewage service before leaving for the day; no building(s) can be left disconnected from the Sewer Main overnight.  These types of outages and possible overtime will be scheduled a minimum of 72 hours in advance by the contractor.  There was discussion about how BCCY has limited abilities in turning off the water to these buildings; the only way to remove water to the affected buildings would be to turn off the water for the entire campus.  It was also discussed that once the contractor starts the process of lining a section of pipe, it must complete the process before allowing sewer from those affected buildings.  These types of outages will need to be handled by operations.

- The contractor shall establish a mobile fenced-in security enclosure around each work site allowing them to move the enclosure from location to location.  This enclosure shall be 6 feet in height.  A discussion about the security fence included a suggestion that privacy material should be installed to limit the interaction between workers and the youth under the care of BCCY.  This privacy material would create blind spots.

- The contractor and all subcontractors will be allowed to leave equipment that is trailer’d within the mobile fenced-in security enclosures overnight; however the equipment must not be self-propelled nor drivable.  All other tools, equipment and selective demolition materials must be removed from inside the BCCY security enclosure to the one of the staging areas at the end of each workday.

- The contractor Superintendent and sub contractor Supervisor(s) can carry cell phones within the construction zones?

- BCCY has written documents for security and typical standards of conduct for personnel on site?  These documents will be provided to the contractors  at the pre-bid conference.

- BCCY does want to get copies of submittals for products; electronic copies will be provided during construction and a paper copy at the completion of the project.

- All contractor and sub-contractors employees entering the BCCY site will be subject to and must pass a background check prior to gaining access to the secure grounds.  Personnel information must be submitted 5 working days in advance for processing.