554 Old Spanish Trail

Slidell, LA 70458

Phone: 985-649-5832

dammonengineering.com

info@dammonengineering.com

City Of Slidell

NEW SIDEWALKS AND DRAINAGE:

PUBLIC ST. (between 8TH & 10th St.)

SLIDELL LA 70458

SLIDELL JOB NO. 5000-31

Bid No. 17-B009

Pre-construction meeting minutes

11-04-16

Minutes:

- Meeting opened at 10 am with signing in of attendees - see attached sign in sheet.

- The following information was disseminated during the pre-construction meeting:

- Reviewed scope of work with Natal.

- Drawings were reviewed to verify scope of work with Natal.

- Natal stated that there are 90 days designated for this project but should only take 30 days to complete.

- The job sign will be submitted for review and will be placed on 10th st.

- The lay down area will be on vacant land on 8th street after notifying the owner.

- City of Slidell Engineering Department will give out notice to proceed to Natal for November 28th.

- 6:30 am to 4 pm are working hours of Natal employees and no weekends are included.

- All submittals will be received by Dammon Engineering for review and then turned into the City of Slidell Engineering Department for final processing.

- Natal shall complete the section 3 labor compliance and submit to Dammon Engineering.

The meeting was adjourned at 10:30 am.