## Sheet1
NATCO
133 Commercial Square
Slidell, La 70461
Phone: 985-690-4189
Fax: 985-690-4969
REQUEST FOR INFORMATION
To: Robert W. |  |  | PROJECT: | St Tammany Parish |  |  | DATE: | 2009-06-19
Administration Complex
|  |  |  | Slidell, LA |  |  | RFI # : | 73
Subject Description |  | Spec. Sec. Ref. |  | Paragraph Ref. |  | Drawing Ref. |  | Detail
Framing Mezzanine wall to NW wall in conference room | [7 empty] | Needed
Cost Impact (if known) |  | Amount |  | Schedule Impact (if known) |  | Days | Drawing Impact |  | Completed
Information Requested:
On the NW side of the mezzanine I'm under the impression the wall must continue to the NW side of the
conference room. If this is so, I also believe the pipes on the NW wall will be a conflict. The wall will have to jog
around the pipes. Also, the area will need an extra vent.
Am I to submit a PCO for this?
Please advise
Johnathan M Horton |  |  |  | Signature: | Johnathan M Horton
(Print Name)
|  |  |  | Title: | Deputy Project Manager
Suggestions:
Reply:
Stand pipe location and resulting pipe runs are a result of the sprinkler contractor's layout. Any conflicts
should not result in extra costs for St. Tammany Parish Government.
Reply by:_________________________________________________ |  |  |  | Signature:
(Print Name)
Date:____________________________________________ |  |  |  | Title: