## Sheet1
Sketch Number | Modifies Sheet | Issued For |  | Issue Date | Disipline
|  |  | Description |  | A | C | S | M | E | P | Comments
SKA01 | A2 | Addendum 04 | Floor Plan | 2013-12-11 | A | [5 empty] | Owner requested changes
SKA02 | A2 | Addendum 04 | Door Schedule | 2013-12-11 | A | [5 empty] | Owner requested changes
SKAE01 | E3 | Addendum 04 | Electrical Detail Plans | 2013-12-11 |  |  |  |  | E |  | Lighting correction
SKA02 | E2 | Addendum 04 | Lighting Schedule | 2013-12-11 |  |  |  |  | E |  | Owner requested changes
SKA03 | A2 | Addendum 05 | Architectural Floor Plan | 2013-12-12 | A | [5 empty] | Owner requested changes
SKS01 | S2 | Addendum 05 | Header Detail | 2013-12-12 |  |  | S |  |  |  | Owner requested changes
SKS02 | S2 | Addendum 05 | New Door Header Detail | 2013-12-12 |  |  | S |  |  |  | Owner requested changes
SKA04 | A7 | Addendum 05 | Partition Types | 2013-12-12 | A | [5 empty] | Partition Type Corrections