554 Old Spanish Trail

Slidell, LA 70458

Phone: 985-649-5832

www.dammonengineering.com

info@dammonengineering.com

CAMP VILLERE

NEW HOME CONSTRUCTION

State Project: LA14-A-037

Engineer’s Project: 2210

Bi-Weekly Construction Meeting Minutes

March 14, 2017

9:00 a.m.

Attendees:

James Downing, LANG - Operations

Gerald J. Leonick, Camp Villere

Jason Cox, Grillot Construction

David Dammon, Dammon Engineering, Inc

Minutes:

- Meeting opened with a review of Change Orders that are in the process of being issued.

- Change Order #1 to adjust the number of days. Waiting for the owner to process.

- Change Order #2 to add an additional test method for pilings. Submitting the Change Order that has been signed by the contractor.

- A copy of the Facility Planning and Control adverse weather days was distributed.  See attached.  The contractor will submit the number of rain days with each pay app.

- A review of the schedule was performed looking for critical path tasks.  The contractor is expected to mobilize for piling starting 3/15/2017 and drive piles 3/16/2017.   The piles will setup for 3 days and one pile will be tested the week of 3/20/2017.  Framing will start after the pile test.

- The interior and exterior color samples, submittal CV-099123-18, as well as the asphalt shingle samples, submittal CV-073113-16, were delivered.  Mr. Downing took one set of samples to make the color selections.

- A site visit was performed prior to the installation of the pilings.

- Next scheduled meeting is 3/28/2017 at 9 am (0900).