554 Old Spanish Trail

Slidell, LA 70458

Phone: 985-649-5832

www.dammonengineering.com

info@dammonengineering.com

CAMP VILLERE

NEW HOME CONSTRUCTION

State Project: LA14-A-037

Engineer’s Project: 2210

Bi-Weekly Construction Meeting Minutes

July 11, 2017

9:00 a.m.

Attendees:

James Downing, LANG - Operations

Gerald J. Leonick, Camp Villere

Autry Chandler, LANG - Facility Engineer

Dustin Hitt, Grillot Construction

David Dammon, Dammon Engineering, Inc

Minutes:

- The electrician submitted a list of light fixtures that were no longer available with alternative fixtures.  The list that was provided was approved except fixture L-2 that was 9.5 inches in diameter.  At the site another alternative for L-2 that was 13 inches in diameter was presented and approved.  See attached pdf of light fixtures.

- Another Change Order for additional time will be processed for the number of rain days.

- A site inspection was performed.

- The next scheduled meeting was 7/25/2017.  Please adjust your scheduled reminders.