554 Old Spanish Trail

Slidell, LA 70458

Phone: 985-649-5832

www.dammonengineering.com

info@dammonengineering.com

CAMP VILLERE

NEW HOME CONSTRUCTION

State Project: LA14-A-037

Engineer’s Project: 2210

Bi-Weekly Construction Meeting Minutes

August 8, 2017

9:00 a.m.

Attendees:

James Downing, LANG - Operations

Autry Chandler, LANG - Facility Engineer

Charles Crawford, Grillot Construction.

Dustin Hitt, Grillot Construction

David Dammon, Dammon Engineering, Inc

Minutes:

- The house will be ready for substantial completion walk through by next Tuesday August 15th.

- The electric meter issue is being pursued through the city of Slidell and the contractor expects to have it resolved shortly.

- The water line has been installed in the ground to the location where the water main is located.  The connection is expected to be completed by next week.

- The lift station has been delivered and expected to be installed by next week.

- A couple of corner pieces for the kitchen cabinets need to be replaced.

- The countertop for the kitchen was affected by the flooding in New Orleans and is expected in shortly.

- The hood system for the stove has not been purchased by the government; therefore a penetration into the ceiling has not been accomplished.

- Since the government has not provided the dishwasher, it was requested that the space be covered.

- A site inspection was performed.

- The next scheduled meeting is 8/15/2017.  Please adjust your scheduled reminders.