## Sheet1
Number |  |  |  |  | Title | Vendor or Subcontractor | Received |  | Returned |  |  | Response |  |  |  | Allow 15 business days for review of each submittal
Specification Number | Submittal Item No. | Resubmittal No. | Contractor Submittal # | Informational Submittal |  |  | Date Received | Copies or Electronic (E) | Date Sent | Copies Returned | Date Due Back | Reviewed | Reviewed as Noted | Revise & Resubmit | Rejected
Comments
013100 | 001 |  | 01 |  | Submittal Register | Grillot Construction | 2017-03-01 | E | 2017-03-02 |  |  | X
012900 | 001 |  | 02 |  | Schedule of Values | Grillot Construction | 2017-03-01 | E | 2017-03-02 |  |  | X
012900 | 002 |  | 03 |  | Construction Schedule | Grillot Construction | 2017-03-01 | E | 2017-03-02 |  |  | X
013100 | 001 |  | 04 |  | List of Sub-Contractors | Grillot Construction | 2017-03-01 | E | 2017-03-02 |  |  |  | X |  |  | When updating list include area of work each area sub will be working on
316219 | 001 |  | 05 |  | Timber Pile Product Data | Baker Pile Driving | 2017-03-01 | E | 2017-03-02 |  |  | X
316219 | 002 |  | 06 |  | Timber Pile Shop Drawing | Baker Pile Driving | 2017-03-01 | E | 2017-03-02 |  |  | X
316219 | 003 |  | 07 |  | Timber Pile Treatment Data | Baker Pile Driving | 2017-03-01 | E | 2017-03-02 |  |  | X
316219 | 004 |  | 08 |  | Timber Pile Driving Equipment | Baker Pile Driving | 2017-03-01 | E | 2017-03-02 |  |  | X
085313 | 001 |  | 09 |  | Vinyl Windows | Gulf Southern Construction | 2017-03-01 | E
081100 | 001 |  | 10 |  | Hollow Core Interior Doors | Gulf Southern Construction | 2017-03-04 | E | 2017-03-06 |  |  | X
312000 | 001 |  | 11 | X | Pre-Excavation Photography | Grillot Construction | 2017-03-04 | E
072500 | 001 |  | 12 |  | Weather Barrier System | Gulf Southern Construction | 2017-03-04 | E | 2017-03-06 |  |  | X
081000 | 001 |  | 13 |  | Steel Doors | Gulf Southern Construction | 2017-03-04 | E | 2017-03-06 |  |  |  |  | X |  | 1.Warranty 10 Yrs; 2. Door thickness .02 inches
073113 | 001 |  | 14 |  | Shingle Product Information | Architectural Roofing | 2017-03-04 | E | 2017-03-06 |  |  |  | X |  |  | Provide Samples
074661 | 001 |  | 15 |  | Fiber Cement Siding and Trim | Architectural Roofing | 2017-03-04 | E | 2017-03-06 |  |  |  | X |  |  | Provide Samples; Follow nail pattern Detail 1 on S3
085313 | 001 | 001 | 09.1 |  | Vinyl Windows | Gulf Southern Construction | 2017-03-09 | E | 2017-03-29 |  |  |  | X
073113 | 001 |  | 16 |  | Shingle & Underlayment Product Information | Architectural Roofing | 2017-03-13 |  | 2017-03-13 | [6 empty] | Missing information
073113 | 001 | 001 | 16.1 |  | Shingle Sample | Architectural Roofing | 2017-03-14 | 2 | 2017-03-16 |  |  |  | X |  |  | Selection : Pristine Weathered Shadow
099113 | 001 |  | 17 |  | Top Coat Exterior Paint Sample | Gulf Southern Construction | 2017-03-14 | 2 | 2017-03-16 |  |  |  | X |  |  | Selection: Shiitake SW# 9173 (Card #248)
099123 | 001 |  | 18 |  | Top Coat Interior Paint Sample | Gulf Southern Construction | 2017-03-14 | 2 | 2017-03-29 |  |  |  | X |  |  | Selection: Fragile Beauty (SW 7553) Interior Trim Paint - Pure White (SW 7005) Interior Ceiling Paint Only - 50%/50% blend of Pure White (SW 7005) and Fragile Beauty (SW 7553)
073113 | 001 |  | 19 |  | Roof Underlayment Product Info | Architectural Roofing | 2017-03-14 | E | 2017-03-29 |  |  | X
061000 | 001 |  | 20 |  | Wood Preservatives | Gulf Southern Construction | 2017-03-16 | E | 2017-03-16 |  |  | X
061000 | 002 |  | 21 |  | Framing Lumber | Gulf Southern Construction | 2017-03-16 | E | 2017-03-16 |  |  | X
099123 | 001 | 001 | 22 |  | Painting Preparation | Gulf Southern Construction | 2017-03-20 | E | 2017-03-29 |  |  | X
072100 | 001 |  | 23 |  | Fiberglass Insulation | Gulf Southern Construction | 2017-03-21 | E | 2017-04-03 |  |  |  |  | X |  | Waiting for docs to be marked with selection
260519 | 001 |  | 24 |  | Electrical Wire | Skeins and Sons Electric | 2017-04-03 | E | 2017-04-03 |  |  | X
262416 | 001 |  | 25 |  | Load Centers | Skeins and Sons Electric | 2017-04-03 | E | 2017-04-03 |  |  |  |  | X |  | Clearly Mark Selection of Load Center
262726 | 001 |  | 26 |  | Electrical Outlet Devices | Skeins and Sons Electric | 2017-04-03 | E | 2017-04-03 |  |  | X |  |  |  | Color choice is Ivory
260533 | 001 |  | 27 |  | Electrical Outlet Boxes | Skeins and Sons Electric | 2017-04-03 | E | 2017-04-03 |  |  |  | X |  |  | Provide data stating Reiker outlet is NEMA FB-1
260533 | 002 |  | 28 |  | Electrical Conduit | Skeins and Sons Electric | 2017-04-03 | E | 2017-04-03 |  |  | X
072100 | 001 | 001 | 23.1 |  | Fiberglass Insulation | Gulf Southern Construction | 2017-04-04 | E | 2017-04-05 |  |  | X
081000 | 001 | 001 | 13.1 |  | Steel Doors | Gulf Southern Construction | 2017-04-04 | E | 2017-04-05 |  |  | X
123530 | 001 |  | 29 |  | Cabinets | Gulf Southern Construction | 2017-04-07 | E | 2017-04-20 |  |  | X |  |  |  | Color choice Thatch; Revise Handle RH25
262416 | 001 | 001 | 25.1 |  | Breakers and Load Centers | Skeins and Sons Electric | 2017-04-10 | E | 2017-04-24 |  |  | X
260533 | 001 | 001 | 27.1 |  | Ceiling Outlet Boxes | Skeins and Sons Electric | 2017-04-20 | E | 2017-04-19 |  |  | X |  |  |  | Carlon Ceiling Box
262416 | 001 | 002 | 25.2 |  | Load Centers | Skeins and Sons Electric | 2017-04-19 | E | 2017-04-24 |  |  | X
093001 | 001 |  | 30.1 |  | Finishes, Solid Vinyl Floor Tile Product Data | Ferguson Enterprises, Inc | 2017-04-24 | E | 2017-04-24 |  |  | X
093001 | 002 |  | 30.2 |  | Finishes, Solid Vinyl Floor Tile Samples | Ferguson Enterprises, Inc | 2017-04-24 | E | 2017-05-09 |  |  |  | X |  |  | Vinyl Plank selection is the BNP 7655
093001 | 003 |  | 30.3 |  | Finishes, Solid Vinyl Floor Tile Maintenance Instructions | Ferguson Enterprises, Inc | 2017-04-24 | E | 2017-04-24 |  |  | X
093001 | 004 |  | 30.4 |  | Finishes, Solid Vinyl Floor Tile, Warranty | Ferguson Enterprises, Inc | 2017-04-24 | E | 2017-04-24 |  |  |  | X |  |  | Provide inspection report prior to installation
221116 | 001 |  | 31.1 |  | Water Hammer Arrestor | Ferguson Enterprises, Inc | 2017-05-01 | E | 2017-05-04 |  |  | X
221116 | 002 |  | 31.2 |  | Copper Tubing & Fittings | Ferguson Enterprises, Inc | 2017-05-01 | E | 2017-05-04 |  |  | X
221313 | 001 |  | 32 |  | Sanitary Sewer PVC Pipe and Fittings | Ferguson Enterprises, Inc | 2017-05-01 | E | 2017-05-04 |  |  | X
221343 | 001 |  | 33 |  | Grinder Pump and Accessories | Ferguson Enterprises, Inc | 2017-05-01 | E | 2017-05-04 |  |  |  | X |  |  | Provide information on Sump Pit
224100 | 001 |  | 34 |  | Plumbing Fixtures | Ferguson Enterprises, Inc | 2017-05-01 | E | 2017-05-04 |  |  |  | X |  |  | Provide substituted Kitchen Faucet in Stainless
233300 | 001 |  | 35 |  | Smoke Detectors | Grillot Construction | 2017-05-01 | E | 2017-05-09 |  |  | X
233300 | 002 |  | 36 |  | Fan/Heater | Grillot Construction | 2017-05-01 | E | 2017-05-09 |  |  | X
E