## G703
NATCO, INC. |  |  |  | SCHEDULE OF VALUES |  |  |  | PAGE OF PAGES |  | /WGPD
[7 empty] | APPLICATION NO: |  |  | /wir.{d 25}~{r 6}/cf~~{L 6}~
NATCO's signed certification is attached. | [6 empty] | APPLICATION DATE: |  |  | /wgpe
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: |  |  | /ru.{d 26}
[7 empty] | ARCHITECT'S PROJECT NO: |  |  | {L 5}
{L 9}
A | B | C | D | E | F | G |  | H | I | /ru.{d 26}~
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Mobilization | 814637.09 |  | 48878.23 |  | 48878.23 | 6% | 765758.86
2 | General & Administrative 0verhead | 297298.52 |  | 144866.81 |  | 144866.81 | 49% | 152431.71
3 | Bonds/ | 106875 |  | 106875 |  | 106875 | 100% | 0
4 | Permits | 21375 |  | 21375 |  | 21375 | 100% | 0
5 | Special Insurance/ Builders Risk | W/ Bonds | [5 empty] | W/ Bonds
6 | Misc. Site Work | 54500 | [5 empty] | 54500
7 | Paving Removal/ Sub Grade Preparartion | W/ Gen Demo | [5 empty] | W/ Gen Demo
8 | New Concrete Paving/ Curbs | 210000 | [5 empty] | 210000
9 | General Demolition/ | 262500 |  | 91875 |  | 91875 | 35% | 170625 | 4593.75
10 | Exterior Wall Demolition/Asbestos | 77209 | [5 empty] | 77209
11 | Piling @ Stairwells | 214500 | [5 empty] | 214500
12 | Concrete Work | 97000 | [5 empty] | 97000
13 | Stained / Scored Concrete | 24500 | [5 empty] | 24500
14 | Masonry | 48000 | [5 empty] | 48000
15 | Steel Stair System | 157500 | [5 empty] | 157500
16 | Porte Corchere | 40000 | [5 empty] | 40000
17 | Misc. Iron | 50000 | [5 empty] | 50000
18 | Metal Decking/Concrete @ Landing | W/ Steel Stairs | [5 empty] | W/ Steel Stairs
19 | Chiller Platform | W/ Steel Stairs | [5 empty] | W/ Steel Stairs
20 | Metal Siding and Roof @ Stairs | W/ Metal Roofing | [5 empty] | W/ Metal Roofing
21 | Wood Doors | 25983 | [5 empty] | 25983
22 | Vanity Tops | W/ Plumbing | [5 empty] | W/ Plumbing
23 | Metal Roofing / Retrofit | 84500 | [5 empty] | 84500
24 | Hollow Metal | 12615 | [5 empty] | 12615
25 | Roll-up Door | 7500 | [5 empty] | 7500
26 | Covered Walkway | N/A | [5 empty] | N/A
27 | Exterior Window Wall System | 1234462 | [5 empty] | 1234462
28 | Millwork | 24000 | [5 empty] | 24000
29 | Plaster Work | 29500 | [5 empty] | 29500
30 | Drywall System | 147000 | [5 empty] | 147000
31 | Ceramic Tile | 71594.3 | [5 empty] | 71594
32 | Resilient Tile/Base | 38063.36 | [5 empty] | 38063.36
33 | Carpeting | 201664.2 | [5 empty] | 201664.2
34 | Acoustical Work | 135000 | [5 empty] | 135000
35 | Painting | 160000 | [5 empty] | 160000
36 | Toilet Compartments | 19767 | [5 empty] | 19767
37 | Toilet Accessories | 16873 | [5 empty] | 16873
38 | Firefighting Devices | 36834 | [5 empty] | 36834
39 | Finish Hardware | 34314 | [5 empty] | 34314
40 | Lawn Sprinklers | W/ Landscaping | [5 empty] | W/ Landscaping
41 | Elevators | 140817 | [5 empty] | 140817
42 | Landscaping | 45265 | [5 empty] | 45265
43 | Fencing | 15000 | [5 empty] | 15000
44 | Sprinkler Work | 196940 | [5 empty] | 196940
45 | Presidents Office | 50000 | [5 empty] | 50000
46 | Sod | W/ Landscaping | [5 empty] | W/Landscaping
47 | Plumbing Work | 171800 | [5 empty] | 171800
48 | HVAC | 980000 | [5 empty] | 980000
49 | Electrical Work | 769613.53 | [5 empty] | 769613.53
[6 empty] | 0 | 0 | 0
| GRAND TOTALS | 7125000 | 0 | 413870.04 |  | 413870.04 |  | 6711129.96 | 4593.75