## G703
NATCO, INC. |  |  |  | SCHEDULE OF VALUES |  |  |  | PAGE OF PAGES
[7 empty] | APPLICATION NO: | 9
NATCO, Inc's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2008-07-31
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2008-07-31
ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | MOBILIZATION | 71250 | 71250 |  |  | 71250 | 100% | 0 | 3562.5
TRAILER RENTAL
SAFETY EQUIPTMENT
FENCING
2 | GENERAL & ADMIN. OVERHEAD | 550000 | 242000 | 30250 |  | 272250 | 50% | 277750 | 13612.5
PROJECT MANAGEMENT SALARIES
FUEL
CELL PHONES
OFFICE SUPPLIES
HOUSING
TRAVEL EXPENSE
SUPPLIES
BID PREPARATION
MANAGEMENT STAFF SLIDELL
CORPORATE VEHICLES
VEHICLE INSURANCE
COPIER LEASE
POSTAGE/ FED-EX
QUALITY CONTROL
FURNITURE
MAINTENANCE
OFFICE PHONE
INTERNET
COMPUTERS
COMPUTER SOFTWARE
MEDICAL INSURANCE
WORKERS COMP
PLANS
BOOK KEEPER
OVERHEAD AND PROFIT
3 | BONDS | 106875 | 106875 |  |  | 106875 | 100% | 0 | 5343.75
SPECIAL INSURANCE/BUILDERS RISK
4 | PERMITS | 21375 | 21375 |  |  | 21375 | 100% | 0 | 1068.75
5 | MISC. SITE WORK | 26500 | 21730 |  |  | 21730 | 82% | 4770 | 1086.5
6 | NEW CONCRETE PAVING/ CURBS | 219000 | 23000 |  |  | 23000 | 11% | 196000 | 1150
7 | GENRERAL DEMO | 321500 | 272200 | 2500 |  | 274700 | 85% | 46800 | 13735
CEILINGS
WALLS
FRAMEWORK
WALLPAPER
PANELING
BASE CASE TRIM
CARPETING
PAVING REMOVAL/ SUB GRADE PREP
EXTERIOR WALL DEMOLITION
8 | ASBESTOS ABATEMENT | 86209 | 86209 |  |  | 86209 | 100% | 0 | 4310.45
9 | PILING @ STAIRWELLS | 39000 | 15990 |  |  | 19500 | 50% | 19500 | 975
10 | CONCRETE WORK | 106000 | 37100 |  |  | 37100 | 35% | 68900 | 1855
11 | STAINED/ SCORED CONCRETE | 33500 | 24125 |  |  | 24125 | 72% | 9375 | 1206.25
12 | MASONRY | 57000 | 23282.5 |  |  | 34565 | 61% | 22435 | 1728.25
13 | STEEL STAIR SYSTEM | 393000 | 37449 |  |  | 279400.05 | 71% | 113599.95 | 13970
METAL DECKING/ CONCRETE @ LANDING
CHILLER PLATFORM
14 | PORTE CORCHERE | 49000 | [5 empty] | 49000
15 | MISC. IRON | 59000 | 12930 |  |  | 35530 | 60% | 23470 | 1776.5
INTERIOR MISC. STEEL
EXTERIOR COLUMNS
BOLLARDS
LOUVERS @ BLOWOUT WALL
STEEL STAIRS TO PENTHOUSE
16 | WOOD DOORS | 34983 | [5 empty] | 34983
17 | METAL ROOFING/ RETROFIT | 248460 | 2484.6 | 50000 |  | 89753.6 | 36% | 158706.4 | 4487.68
METAL SIDING AND ROOF @ STAIRS
18 | HOLLOW METAL DOORS | 21615 | [5 empty] | 21615
19 | ROLL-UP DOOR | 16500 | 16005 |  |  | 16005 | 97% | 495 | 800.25
20 | COVERED WALKWAY | 46000 | [5 empty] | 46000
21 | EXTERIOR WINDOW WALL SYSTEM | 1243462 | [5 empty] | 1243462
22 | MILLWORK/ TROPHY CABINETRY | 33000 | [5 empty] | 33000
23 | PLASTER WORK | 28500 | 1675 |  |  | 17675 | 62% | 10825 | 883.75
24 | DRYWALL SYSTEM | 96000 | 62000 |  |  | 63600 | 66% | 32400 | 3180
FRAMEWORK 1ST FLOOR
FRAMEWORK 2ND FLOOR
FRAMEWORK 3RD FLOOR
FRAMEWORK 4TH FLOOR
FRAMEWORK 5TH FLOOR
FRAMEWORK 6TH FLOOR
25 | CERAMIC TILE | 80594.3 | [5 empty] | 80594.3
26 | RESILIENT TILE/ BASE | 42603.36 | [5 empty] | 42603.36
27 | CARPETING | 210664.2 | [5 empty] | 210664.2
28 | ACCOUSTICAL WORK | 76500 | [5 empty] | 76500
29 | PAINTING | 114000 | [5 empty] | 114000
30 | TOILET COMPARTMENTS | 28767 | [5 empty] | 28767
31 | TOILET ACCESSORIES | 25873 | [5 empty] | 25873
32 | FIREFIGHTING DEVICES | 45834 |  |  |  | 2291.7 | 5% | 43542.3 | 114.59
(13) FIRE EXTINGUISHERS
FIRE EXTI. TAGGED/ INSPECTED
SMOKE DETECTORS
33 | FINISH HARDWARE | 43314 | [5 empty] | 43314
34 | ELEVATORS | 149817 | [5 empty] | 149817
35 | LANDSCAPING | 54265 | [5 empty] | 54265
LAWN SPRINKLERS
SOD
36 | FENCING | 24000 | [5 empty] | 24000
37 | SPRINKLER WORK | 205940 |  |  | 86679 | 101094.8 | 49% | 104845.2 | 5054.74
38 | PRESIDENTS OFFICE | 59000 | [5 empty] | 59000
39 | PLUMBING WORK | 238485.61 | 80340.96 | 40000 |  | 123469.96 | 52% | 115015.65 | 6173.49
FLOOR 1/ ROUGH END
FLOOR 2/ ROUGH END
FLOOR 3/ ROUGH END
FLOOR 4/ ROUGH END
FLOOR 5/ ROUGH END
FLOOR 6/ ROUGH END
FIXTURES
WATER METER
URINAL
COMMODES
WATER FOUNTAINS
VANITY TOPS
40 | HVAC | 1014000 | [5 empty] | 1014000
VAV BOXES
CONTROLLERS
DUCT WORK
CHILLERS
POPING
RETURNS
REFRIDGERATION
TEST & BALANCE
41 | ELECTRICAL WORK | 803613.53 | 301370.19 |  |  | 353589.95 | 44% | 450023.58 | 17679.5
FLOOR 1/ ROUGH END
FLOOR 2/ ROUGH END
FLOOR 3/ ROUGH END
FLOOR 4/ ROUGH END
FLOOR 5/ ROUGH END
FLOOR 6/ ROUGH END
LIGHTING INTE / EXTE
FUSE/ CURCUIT BOXES
CONDUIT
WIRING
SWITCHES
RECEPTICALS
SPECIAL LIGHTING
OFFICE TRAILER
GEAR
VOICE DATA
SECURITY CARD SYSTEM
42 | WEST SIDE FENCE | 8322.66 | 1500 |  |  | 1500 | 18% | 6822.66 | 75
| GRAND TOTALS | 7133322.66 | 1460891.25 | 122750 | 86679 | 2076589.06 | 29% | 5056733.6 | 103829.45