## Sheet1
1 | ELECTRICIAN DISCONNECT HEATERS/MAKE SAFE
2 | DEMO HEATERS
3 | REMOVE WATER FOUNTAIN FOR STEEL
4 | RUN DUCTWORK IN LOCKER ROOMS
5 | INSTALL EXTERIOR LADDERS
6 | ELECTRICIAN RUN COND.WIRE, AND DISCONNECTS
7 | CORE DRILL HOLES IN ROOF
8 | INSTALL COLUMNS THROUGH ROOF
9 | ROOFER WATER TIGHT COLUMNS
10 | ROOFER INSTALL PARATREAD
11 | DEMO MINI SPLIT IN CONCESSION/MAKE SAFE
12 | INSTALL BOTH MINI SPLITS
13 | ELECTRICIAN WIRE IN MINI SPLITS
14 | CUT HOLES FOR LOUVERS
15 | INSTALL LOUVERS
16 | DEMO AHU'S IN LOCKER ROOMS
17 | INSTALL AHU'S IN LOCKER ROOMS
18 | ELECTRICIAN WIRE IN AHU'S
19 | INSTALL PLATFORM
20 | INSTALL RTU'S
21 | ELECTRICIAN WIRE IN RTU'S
22 | CUT HOLES FOR DUCT FROM RTU'S
23 | INSTALL DUCT THROUGH WALLS
24 | INSTALL DUCT IN GYM (SPIRAL)
25 | WEATHER SEAL DUCT (OUTSIDE)
26 | ELECTRICIAN FINISH ALL DISCONNECTS TURN ON POWER
27 | INSTALL ALL GRILLS
28 | DEMO UNITS IN GYM
29 | PATCH HOLES FROM UNITS IN GYM
30 | PAINT ALL PATCHES
31 | REINSTALL WATER FOUNTAIN
32 | BUILD FENCE (CHANGE ORDER)
33 | PAINT STEEL AND UNIT (CHANGE ORDER)
34 | START UP UNITS
35 | TEST AND BALANCE
36 | FINAL CLEAN
37 | PUNCH LIST
38 | TURN OVER