## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Boyet Jr High HVAC Replacement
TODAY'S DATE: 5/28/2024
Scrolling increment: |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
JAMES HEINSZ JR
Project start date: | 2024-05-29 |  |  |  |  | May | [6 empty] | June | [34 empty] | July | [22 empty] | AUGUST
Scrolling increment: | 0 | time axis 2024-05-29 to 2024-10-31
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-29 to 2024-10-31
Project development
SEND OUT SUBCONTRACTS | Goal | JAMES | 100% | 2024-05-29 | 3 | 2024-05-29: 2; 2024-05-30: 2; 2024-05-31: 2
SEND SUBMITTALS TO ENGINEER | Goal | JAMES | 100% | 2024-04-02 | 5
SUBMITTAL REVIEW | Goal | DAMMON | 100% | 2024-04-05 | 15
ORDER EQUIPMENT | Goal | JAMES | 100% | 2024-04-05 | 1
PRECON MEETING | Med Risk | JAMES | 0% | 2024-05-31 | 1
SHOP DRAWINGS | Goal | JAMES | 100% | 2024-06-24 | 3 | 2024-06-24: 2; 2024-06-25: 2; 2024-06-26: 2
LAST DAY OF SCHOOL | Milestone | SCHOOL | 100% | 2024-05-23 | 1
MEASURE STRUCT STEEL | On Track | JOLY'S | 0% | 2024-06-03 | 2
START ELECT WORK | On Track | REGENCY | 0% | 2024-06-03 | 45
DEMO HEATERS | On Track | A&A | 0% | 2024-06-06 | 2
REMOVE WATER FOUNTAIN | On Track | A&A | 0% | 2024-06-06 | 2
INSTALL LADDERS | On Track | A&A | 0% | 2024-06-17 | 4
DEMO SPLIT SYSTEMS | On Track | A/C SPEC. | 0% | 2024-06-17 | 1
INSTALL SPLIT SYSTEMS | On Track | A/C SPEC. | 0% | 2024-06-18 | 4
INSTALL AHU IN LOCKER RMS | On Track | A/C SPEC. | 0% | 2024-06-18 | 2
INSTALL DUCT IN LOCKER RMS | On Track | A/C SPEC. | 0% | 2024-06-18 | 5
INSTALL STRUCTURAL STEEL | On Track | JOLY'S | 0% | 2024-06-27 | 5
PATCH ROOF PENETRATIONS | On Track | FISCHERS | 0% | 2024-06-27 | 2
REINSTALL WATER FOUNTAIN | On Track | A&A | 0% | 2024-06-27 | 1
INSTALL ROOF PARATREAD PADS | On Track | FISCHERS | 0% | 2024-07-01 | 2
CUT OPENING FOR DUCT IN GYM | On Track | A&A | 0% | 2024-07-08 | 4
INSTALL RTU'S | On Track | NOIW | 0% | 2024-07-15 | 2
INSTALL GYM DUCT | On Track | A/C SPEC. | 0% | 2024-07-15 | 6
INSTALL OUTSIDE DUCT | On Track | A/C SPEC. | 0% | 2024-07-18 | 4
WEATHERPROOF DUCT | On Track | A/C SPEC. | 0% | 2024-07-22 | 4
PATCH AND PAINT | On Track | PERFECT PAINT | 0% | 2024-07-22 | 2
UNIT START UP | On Track | A/C SPEC. | 0% | 2024-07-26 | 3
PAINT STEEL & UNIT | On Track | PERFECT PAINT | 0% | 2024-07-26 | 5
INSTALL FENCING | On Track | A&A | 0% | 2024-07-26 | 4
TEST AND BALANCE | On Track | MECHANICAL SER. | 0% | 2024-07-29 | 4
FINAL CLEAN | On Track | A&A | 0% | 2024-07-29 | 2
PUNCH LIST | On Track | A&A | 0% | 2024-07-29 | 3
TURN OVER | On Track | A&A | 0% | 2024-08-02 | 1
To add more data, Insert new rows ABOVE this one

## Sheet1
PROJECT: Boyet Jr High HVAC Replacement
A&A MECHANICAL LLC |  |  |  |  | Legend:
JAMES HEINSZ JR
Project start date: | 2024-05-29
Scrolling increment: | 0
Milestone description | Category | Assigned to | Progress | Start | Days
Project development
SEND OUT SUBCONTRACTS | Goal | JAMES | 80% | 2024-05-29 | 3
SEND SUBMITTALS TO ENGINEER | Goal | JAMES | 90% | 2024-04-02 | 5
SUBMITTAL REVIEW | High Risk | DAMMON | 50% | 2024-04-05 | 15
ORDER EQUIPMENT | Goal | JAMES | 80% | 2024-06-18 | 1
PRECON MEETING | Med Risk | JAMES | 0% | 2024-05-22 | 3
SHOP DRAWINGS | Low Risk | JAMES | 0% | 2024-06-22 | 3
LAST DAY OF SCHOOL | Milestone | SCHOOL | 50% | 2024-05-23 | 1
DEMO FENCE | On Track | A&A | 0% | 2024-06-17 | 4
MAINTENANCE PADS | Low Risk | A&A | 0% | 2024-07-18 | 2
START ELECT WORK | On Track | REGENCY | 0% | 2024-06-03 | 45
INSTALL FENCING | Low Risk | JOLY'S | 0% | 2024-07-29 | 10
INSTALL LADDERS | Low Risk | A&A | 0% | 2024-06-17 | 3
INSTALL SPLIT SYSTEMS | On Track | A/C SPEC. | 0% | 2024-06-20 | 4
INSTALL DUCT IN LOCKERRMS | Med Risk | A/C SPEC. | 0% | 2024-06-23 | 14
INSTALL DUCT IN GYM | On Track | A/C SPEC. | 0% | 2024-07-08 | 10
INSTALL RTU'S | Goal | NOIW | 0% | 2024-07-18 | 3
CUT OPENING FOR DUCT IN GYM | Med Risk | A&A | 0% | 2024-07-18 | 2
INSTALL OUTSIDE DUCT | High Risk | A/C SPEC. | 0% | 2024-07-22 | 4
WEATHERPROOF DUCT | Med Risk | A/C SPEC. | 0% | 2024-07-26 | 2
UNIT START UP | Med Risk | A/C SPEC. | 0% | 2024-07-26
FINAL CLEAN | Goal | A&A | 0% | 2024-07-28 | 2
PUNCH LIST | Goal | A&A | 0% | 2024-07-28 | 1
TURN OVER | Milestone | A&A | 0% | 2024-08-07 | 1
Formulas:
Start = [Start, row above]+3

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2024-05-29 |  |  |  |  | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-06-03 to 2024-07-28
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: T
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-05-29 |  |  |  |  | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-06-03 to 2024-07-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-03 to 2024-07-28
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: 2024-06-03
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: 2024-06-18
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: 2024-06-13
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | 2024-07-05: 2; 2024-07-06: 2; 2024-07-07: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one