May 31, 2024

Pre-Construction Meeting Agenda

STPSB Project No. PO428

Boyet Junior High School, Replacement of Gymnasium HVAC Units

- Summary of work.

This project consists of the removal and replacement of the existing HVAC equipment: air handler units, condensing units, and demolition of some heaters within the approximately 13,000 sq ft gymnasium.

- Staging area.

  - Finalize limits of staging area and coordinate with STSB.

- Site access:

  - Owner will occupy site and existing buildings during construction period.  Perform work so as not to interfere with Owner’s day-to-day operations.

  - Maintain access to existing roads,  …etc.

  - Provide not less than 72 hours notice to Owner of activities that will affect Owner’s operations.

  - Work shall generally be performed outside the building during normal business hours.

  - Smoking is not allowed on STSPB property.

  - Workmen to wear same color shirts on jobsite.

  - Deliveries and daily access.

- Utilities

  - Use of Owner’s property, power, water, telephone & other facilities

    - Provide temporary water closet.

    - Notify Owner of any outages

- Job Site Noise & Dust Control

  - Respect users (students, employees, neighbors), no loud music or foul language

- Scheduling / Coordination

  - Construction Duration

    - Phase II Construction time is 60 days.

    - Complete all construction prior to beginning of 2024-2025 school year.

    - Notice to proceed.

- Meetings & Inspections

  - Permits

  - Site Inspections

  - Progress / Coordination Meetings

- Quality Control

  - Contractor’s responsibility

  - Owners expects good quality

  - Unacceptable work

- Submittals

  - # of copies & who gets

  - Response time

- Request for Payment

  - Number of copies to be submitted.

  - Accompanied by updated schedule if changes.

  - Lien releases

  - Stored materials

    - Must be suitably stored and per manufacturer’s recommendation when applicable

    - Off-site - copy of invoice & applicable insurance.

    - On-site - copy of invoice

  - Review at monthly progress meeting

- Modifications and/or Changes

  - Must have prior approval from Architect/Engineer before proceeding with changes

  - Steps

    - RFI

    - Contractor or architect cost proposal

    - Construction Change Directive

    - Change Order

  - Mtg. to discuss CO’s & proposals as necessary

- Claims & Delays

  - Process explained in contract documents

  - Liquidated damages - $500 per day

- Construction Methods and Safety Procedures (Comply with OSHA)

## Means & Methods are the contractor’s sole prerogative

  - Safety is responsibility of the contractor.

  - Safety & construction signs are contractor’s responsibility

- Substantial Completion

  - Contractual obligations fulfilled

  - Formally notify Architect or Engineer for substantial inspection

    - Include list of incomplete items

  - O&M manuals – Submit as package, not bits & pieces

- Final Acceptance / Closeout

  - Contractual obligations fulfilled including Consent of Surety and Contractor’s Affidavit

  - Date Architect/Engineer signs final pay request unless otherwise approved in writing

  - Formally notify Architect/Engineer for final inspection

  - Punch-list needs to be signed & returned to Architect/Engineer

- Review metal color choices and options.