ST Tammany Junior – Termite Damage

Construction Meeting #1

4-8-25

Agenda

Meeting Minutes

Attendance-

- Steele McDaniel- SRD

- Sammy Manino- Owner

- David Dammon- Arch

- Black Nagims- Steel erector

- Reps from Northlake Glass

- Permits/Inspections

  - Electrical rough-in

  - Mechanical rough-in

  - Plumbing rough-in

  - Roof Framing

  - Electrical final

  - Mechanical final

  - Plumbing final

  - Building final

  - SFM letter

  - Cert of Occupancy

- Monthly pay app

- Pay app #1 submitted- Architect handed Sammy the signed pay app at meeting

- Submittal under review

- 15-700 Heating, Venting, and Air Conditioning – Architect is waiting on review from mech eng

- Submittal to be submitted

- 09-810 Stucco

- 08-500 Windows

- 13-900 Fire Suppression

- Change order

  - CO#1 Remove Store and reinstall all wood doors and hardware- remove marker boards and Chalk boards. Architect to send response

    - Denied Architect.

      - Owner to remove doors from site and install doors and hardware once project is over

  - CO#2 Demo and replace VCT-

    - to be reviewed by Architect- Architect to send response

  - CO#3 Replace wall scones Lighting - Architect to send response

    - to be reviewed by Architect

  - CO#4 SRD to submit price for the roof changes

  - CO#5 Add a stucco band around the exterior where the mate line of new and old stucco will be as it is expected to crack.

    - This needs to be submitted for Architects review.  SRD to submit price

- Work issues/adjustments

  - Roof leak at existing roof

    - Owner to address with existing roof warranty. Owners’ roofer was on site reviewing the leak

    - Should SRD provide price to replace drop ceiling it that area? Owner declined at this time

  - Epoxy floor is in bad condition. Just want to point this out again. This was acknowledged

- Schedule

  - Job delayed do to steel not arriving when it was scheduled

  - 3 week look ahead

| Task Name | Duration | Start | Finish | Predecessors |
| --- | --- | --- | --- | --- |
| Install Temp protection from rain | 4 days | Mon 4/14/25 | Thu 4/17/25 | 22 |
| Reroute down spouts | 1 day | Mon 4/14/25 | Mon 4/14/25 | 22 |
| Anchor and set new HHS 4x4x1/4 Columns | 3 days | Tue 4/15/25 | Thu 4/17/25 | 24 |
| Set new W12X16 beams | 3 days | Fri 4/18/25 | Tue 4/22/25 | 25 |
| Install top Plates on Steel Beams | 2 days | Wed 4/23/25 | Thu 4/24/25 | 26 |
| Install 2x6 treated joists | 3 days | Fri 4/25/25 | Tue 4/29/25 | 27 |
| Frame for new knee wall | 3 days | Wed 4/30/25 | Fri 5/2/25 | 28 |
| Frame for new stud wall | 2 days | Mon 5/5/25 | Tue 5/6/25 | 29 |
| Install 5/8 Sheathing & 1x6 Facia | 1 day | Wed 4/30/25 | Wed 4/30/25 | 28 |
| Install New Siplast Roof | 5 days | Thu 5/1/25 | Wed 5/7/25 | 31 |

3 week look ahead was fine with the owner and architect.

Architect mentions some issues with the schedule as a hole that SRD needs to correct.

SRD to send RFI on steel gap tolerance

SRD to submit wedge anchor product data

RFI list was provided by Architect

CO list was provided by Architect