## Sheet1
NATCO
133 Commercial Square
Slidell, La 70461
Phone: 985-690-4189
Fax: 985-690-4969
REQUEST FOR INFORMATION
To: Robert W. |  |  | PROJECT: | St Tammany Parish |  |  | DATE: | 2008-06-04
Administration Complex
|  |  |  | Slidell, LA |  |  | RFI # : | 20
Subject Description |  | Spec. Sec. Ref. |  | Paragraph Ref. |  | Drawing Ref. |  | Detail
Electrical recepticles | [5 empty] | E-1P
Cost Impact (if known) |  | Amount |  | Schedule Impact (if known) |  | Days | Drawing Impact |  | Completed
0 |  | 0 |  | none
Information Requested:
Are the electrical recepticles to be installed in wall or mounted on wall.
Robert Johnson |  |  |  | Signature: | Robert Johnson
(Print Name)
|  |  |  | Title: | Superintendent
Suggestions:
Reply:
Reply by:_________________________________________________ |  |  |  | Signature:
(Print Name)
Date:____________________________________________ |  |  |  | Title: