Copyright 2010 AIA
MasterSpec Professional
02/10

Copyright 2010 by The American Institute of Architects (AIA)

Exclusively published and distributed by Architectural Computer Services, Inc. (ARCOM) for the AIA

SECTION 013200 - CONSTRUCTION PROGRESS DOCUMENTATION
TIPS:
To view non-printing Editor's Notes that provide guidance for editing, click on Masterworks/Single‑File Formatting/Toggle/Editor's Notes.
To read detailed research, technical information about products and materials, and coordination checklists, click on Masterworks/Supporting Information.

Revise this Section by deleting and inserting text to meet Project-specific requirements.

This Section uses the term "Architect." Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

PART 1 -  GENERAL

1.1 SUMMARY

A. Section includes administrative and procedural requirements for documenting the progress of construction during performance of the Work, including the following:

1. Contractor's construction schedule.

2. Construction schedule updating reports.

3. Daily construction reports.

4. Site condition reports.

B. Related Requirements:

Retain subparagraph below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

1. Section 011200 "Multiple Contract Summary" for preparing a combined Contractor's construction schedule.

1.2 DEFINITIONS

Retain terms that remain after this Section has been edited for a project.

A. Activity: A discrete part of a project that can be identified for planning, scheduling, monitoring, and controlling the construction project. Activities included in a construction schedule consume time and resources.

1. Critical Activity: An activity on the critical path that must start and finish on the planned early start and finish times.

2. Predecessor Activity: An activity that precedes another activity in the network.

3. Successor Activity: An activity that follows another activity in the network.

B. CPM: Critical path method, which is a method of planning and scheduling a construction project where activities are arranged based on activity relationships. Network calculations determine when activities can be performed and the critical path of Project.

C. Critical Path: The longest connected chain of interdependent activities through the network schedule that establishes the minimum overall Project duration and contains no float.

Retain definition in "Float" Paragraph below for most projects using CPM-type schedule. Designating ownership of float can save arguments later. See Evaluations.

D. Float: The measure of leeway in starting and completing an activity.

1. Float time [belongs to Owner] [is not for the exclusive use or benefit of either Owner or Contractor, but is a jointly owned, expiring Project resource available to both parties as needed to meet schedule milestones and Contract completion date].

1.3 INFORMATIONAL SUBMITTALS

A. Format for Submittals: Submit required submittals in the following format:

1. Working electronic copy of schedule file, where indicated.

Retain one of two subparagraphs below

2. PDF electronic file.

3. [Two] <Insert number> paper copies.

B. Startup Network Diagram: Of size required to display entire network for entire construction period. Show logic ties for activities.

C. Contractor's Construction Schedule: Initial schedule, of size required to display entire schedule for entire construction period.

Retain subparagraph below if Architect, Owner, or Construction Manager will use scheduling software to revise Contractor's data or to integrate scheduling data from multiple contracts or separate contracts.

1. Submit a working electronic copy of schedule, using software indicated, and labeled to comply with requirements for submittals. Include type of schedule (initial or updated) and date on label.

D. CPM Reports: Concurrent with CPM schedule, submit each of the following reports. Format for each activity in reports shall contain activity number, activity description, original duration, remaining duration, early start date, early finish date, late start date, late finish date, and total float in calendar days.

1. Activity Report: List of all activities sorted by activity number and then early start date, or actual start date if known.

2. Logic Report: List of preceding and succeeding activities for all activities, sorted in ascending order by activity number and then early start date, or actual start date if known.

3. Total Float Report: List of all activities sorted in ascending order of total float.

4. Earnings Report: Compilation of Contractor's total earnings from [commencement of the Work] [the Notice to Proceed] until most recent Application for Payment.

E. Construction Schedule Updating Reports: Submit with Applications for Payment.

F. Daily Construction Reports: Submit at [weekly] [monthly] intervals.

G. Site Condition Reports: Submit at time of discovery of differing conditions.

1.4 COORDINATION

Coordinate requirements in this article with submittal schedule requirements in Section 013300 "Submittal Procedures."

Coordinate preparation and processing of schedules and reports with performance of construction activities and with scheduling and reporting of separate contractors.

A. Coordinate Contractor's construction schedule with the schedule of values,[ list of subcontracts,] submittal schedule, progress reports, payment requests, and other required schedules and reports.

1. Secure time commitments for performing critical elements of the Work from entities involved.

2. Coordinate each construction activity in the network with other activities and schedule them in proper sequence.

PART 2 -  PRODUCTS

2.1 CONTRACTOR'S CONSTRUCTION SCHEDULE, GENERAL

A. Time Frame: Extend schedule from date established for [commencement of the Work] [the Notice of Award] [the Notice to Proceed] to date of [Substantial Completion] [final completion].

1. Contract completion date shall not be changed by submission of a schedule that shows an early completion date, unless specifically authorized by Change Order.

B. Activities: Treat each story or separate area as a separate numbered activity for each main element of the Work. Comply with the following:

Revise "Activity Duration" Subparagraph below to suit Project. Long activity durations provide less detail and, therefore, less information with which to manage a project. As an alternative to specifying activity duration, indicate minimum and maximum number of activities, which will result in a similar effect.

1. Activity Duration: Define activities so no activity is longer than [20] <Insert number> days, unless specifically allowed by Architect.

2. Procurement Activities: Include procurement process activities for the following long lead items and major items, requiring a cycle of more than 60 days, as separate activities in schedule. Procurement cycle activities include, but are not limited to, submittals, approvals, purchasing, fabrication, and delivery.

a. <Insert list of major items or pieces of equipment>.

3. Submittal Review Time: Include review and resubmittal times indicated in Section 013300 "Submittal Procedures" in schedule. Coordinate submittal review times in Contractor's construction schedule with submittal schedule.

4. Startup and Testing Time: Include no fewer than [15] <Insert number> days for startup and testing.

5. Substantial Completion: Indicate completion in advance of date established for Substantial Completion, and allow time for Architect's[ and Construction Manager's] administrative procedures necessary for certification of Substantial Completion.

6. Punch List and Final Completion: Include not more than [30] <Insert number> days for completion of punch list items and final completion.

C. Constraints: Include constraints and work restrictions indicated in the Contract Documents and as follows in schedule, and show how the sequence of the Work is affected.

Retain first four subparagraphs below if applicable. Coordinate list below with work restrictions listed in Section 011000 "Summary."

1. Phasing: Arrange list of activities on schedule by phase.

2. Work under More Than One Contract: Include a separate activity for each contract.

3. Work by Owner: Include a separate activity for each portion of the Work performed by Owner.

4. Work Restrictions: Show the effect of the following items on the schedule:

a. Coordination with existing construction.

b. Limitations of continued occupancies.

c. Uninterruptible services.

d. Partial occupancy before Substantial Completion.

e. Use of premises restrictions.

f. Provisions for future construction.

g. Seasonal variations.

h. Environmental control.

Retain "Work Stages" Subparagraph below for large projects and complicated small projects. Consider limiting it to critical work or important subcontracts.

5. Work Stages: Indicate important stages of construction for each major portion of the Work.

6. Other Constraints: <Insert constraints not indicated elsewhere>.

D. Milestones: Include milestones indicated in the Contract Documents in schedule, including, but not limited to, the Notice to Proceed, Substantial Completion, and final completion[.][, and the following interim milestones:]

1. <Insert milestones not indicated elsewhere>.

E. Upcoming Work Summary: Prepare summary report indicating activities scheduled to occur or commence prior to submittal of next schedule update. Summarize the following issues:

1. Unresolved issues.

2. Unanswered Requests for Information.

3. Rejected or unreturned submittals.

4. Notations on returned submittals.

5. Pending modifications affecting the Work and Contract Time.

F. Recovery Schedule: When periodic update indicates the Work is [14] <Insert number> or more calendar days behind the current approved schedule, submit a separate recovery schedule indicating means by which Contractor intends to regain compliance with the schedule.

G. Computer Scheduling Software: Prepare schedules using current version of a program that has been developed specifically to manage construction schedules.

Retain paragraph below if Owner requires a specific computer software program.

1. Use [Microsoft Project,] [Primavera,] [Prolog,] [Scheduling component of Project Web site software specified in Section 013100 "Project Management and Coordination,"] <Insert name of specific software,> for [Windows XP] [Windows Vista] <Insert current Windows operating system> [Macintosh OS X] operating system.

2.2 CONTRACTOR'S CONSTRUCTION SCHEDULE (GANTT CHART)

Gantt-chart schedule in this article is adequate for many projects. Delete this article if Project size and complexity justify CPM construction schedule.

A. Gantt-Chart Schedule: Submit a comprehensive, fully developed, horizontal, Gantt-chart-type, Contractor's construction schedule within [30] <Insert number> days of date established for [commencement of the Work] [the Notice to Proceed] [the Notice of Award].

B. Preparation: Indicate each significant construction activity separately. Identify first workday of each week with a continuous vertical line.

1. For construction activities that require three months or longer to complete, indicate an estimated completion percentage in [10] <Insert number> percent increments within time bar.

2.3 CONTRACTOR'S CONSTRUCTION SCHEDULE (CPM SCHEDULE)

CPM schedules are more complex than Gantt-chart schedules. Delete this article if not required. See Evaluations.

A. General: Prepare network diagrams using AON (activity-on-node) format.

Projects using CPM schedules should begin with a startup network diagram of type described in "Startup Network Diagram" Paragraph below.

B. Startup Network Diagram: Submit diagram within [14] <Insert number> days of date established for [commencement of the Work] [the Notice to Proceed] [the Notice of Award]. Outline significant construction activities for the first [90] <Insert number> days of construction. Include skeleton diagram for the remainder of the Work and a cash requirement prediction based on indicated activities.

Revise "CPM Schedule" Paragraph below to suit Project.

C. CPM Schedule: Prepare Contractor's construction schedule using a[ cost- and resource-loaded,] time-scaled CPM network analysis diagram for the Work.

1. Develop network diagram in sufficient time to submit CPM schedule so it can be accepted for use no later than [60] <Insert number> days after date established for [commencement of the Work] [the Notice to Proceed] [the Notice of Award].

a. Failure to include any work item required for performance of this Contract shall not excuse Contractor from completing all work within applicable completion dates, regardless of Architect's approval of the schedule.

2. Establish procedures for monitoring and updating CPM schedule and for reporting progress. Coordinate procedures with progress meeting and payment request dates.

Subparagraph below coordinates between working days of time and calendar days. Under AIA Document A201, the Contract Time is in calendar days.

3. Use "one workday" as the unit of time for individual activities. Indicate nonworking days and holidays incorporated into the schedule in order to coordinate with the Contract Time.

Revise "CPM Schedule Preparation" Paragraph below to suit Project.

D. CPM Schedule Preparation: Prepare a list of all activities required to complete the Work. Using the startup network diagram, prepare a skeleton network to identify probable critical paths.

1. Activities: Indicate the estimated time duration, sequence requirements, and relationship of each activity in relation to other activities. Include estimated time frames for the following activities:

a. Preparation and processing of submittals.

b. Mobilization and demobilization.

c. Purchase of materials.

d. Delivery.

e. Fabrication.

f. Utility interruptions.

g. Installation.

h. Work by Owner that may affect or be affected by Contractor's activities.

i. Testing[ and commissioning].

j. Punch list and final completion.

k. Activities occurring following final completion.

2. Critical Path Activities: Identify critical path activities, including those for interim completion dates. Scheduled start and completion dates shall be consistent with Contract milestone dates.

3. Processing: Process data to produce output data on a computer-drawn, time-scaled network. Revise data, reorganize activity sequences, and reproduce as often as necessary to produce the CPM schedule within the limitations of the Contract Time.

4. Format: Mark the critical path. Locate the critical path near center of network; locate paths with most float near the edges.

a. Subnetworks on separate sheets are permissible for activities clearly off the critical path.

E. Contract Modifications: For each proposed contract modification and concurrent with its submission, prepare a time-impact analysis using a network fragment to demonstrate the effect of the proposed change on the overall project schedule.

F. Initial Issue of Schedule: Prepare initial network diagram from a sorted activity list indicating straight "early start-total float." Identify critical activities. Prepare tabulated reports showing the following:

1. Contractor or subcontractor and the Work or activity.

2. Description of activity.

3. Main events of activity.

4. Immediate preceding and succeeding activities.

5. Early and late start dates.

6. Early and late finish dates.

7. Activity duration in workdays.

8. Total float or slack time.

9. Average size of workforce.

10. Dollar value of activity (coordinated with the schedule of values).

G. Schedule Updating: Concurrent with making revisions to schedule, prepare tabulated reports showing the following:

1. Identification of activities that have changed.

2. Changes in early and late start dates.

3. Changes in early and late finish dates.

4. Changes in activity durations in workdays.

5. Changes in the critical path.

6. Changes in total float or slack time.

7. Changes in the Contract Time.

2.4 REPORTS

A. Daily Construction Reports: Prepare a daily construction report recording the following information concerning events at Project site:

1. List of subcontractors at Project site.

2. List of separate contractors at Project site.

3. Approximate count of personnel at Project site.

4. Equipment at Project site.

5. Material deliveries.

6. High and low temperatures and general weather conditions, including presence of rain or snow.

7. Accidents.

8. Meetings and significant decisions.

9. Unusual events.

10. Stoppages, delays, shortages, and losses.

11. Meter readings and similar recordings.

12. Emergency procedures.

13. Orders and requests of authorities having jurisdiction.

14. Change Orders received and implemented.

Construction Change Directives are used by AIA Document A201. EJCDC Document C-700 uses Work Change Directives.

15. [Construction] [Work] Change Directives received and implemented.

16. Services connected and disconnected.

17. Equipment or system tests and startups.

18. Partial completions and occupancies.

19. Substantial Completions authorized.

Revise "Site Condition Reports" Paragraph below to suit Project and special Owner requirements.

B. Site Condition Reports: Immediately on discovery of a difference between site conditions and the Contract Documents, prepare and submit a detailed report. Submit with a Request for Information. Include a detailed description of the differing conditions, together with recommendations for changing the Contract Documents.

Insert other reports required.

PART 3 -  EXECUTION

3.1 CONTRACTOR'S CONSTRUCTION SCHEDULE

A. Contractor's Construction Schedule Updating: At [monthly] <Insert time> intervals, update schedule to reflect actual construction progress and activities. Issue schedule [one week] <Insert time> before each regularly scheduled progress meeting.

1. Revise schedule immediately after each meeting or other activity where revisions have been recognized or made. Issue updated schedule concurrently with the report of each such meeting.

2. Include a report with updated schedule that indicates every change, including, but not limited to, changes in logic, durations, actual starts and finishes, and activity durations.

3. As the Work progresses, indicate final completion percentage for each activity.

B. Distribution: Distribute copies of approved schedule to Architect[, Construction Manager,] Owner, separate contractors, testing and inspecting agencies, and other parties identified by Contractor with a need-to-know schedule responsibility.

1. Post copies in Project meeting rooms and temporary field offices.

2. When revisions are made, distribute updated schedules to the same parties and post in the same locations. Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in performance of construction activities.

END OF SECTION 013200

	CONSTRUCTION PROGRESS DOCUMENTATION
	013200 - 1



