Copyright 2002 AIA
MASTERSPEC
11/02

Copyright 2002, The American Institute of Architects (AIA)

SECTION 01250 - CONTRACT MODIFICATION PROCEDURES
This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

PART 1 -  GENERAL

1.1 RELATED DOCUMENTS

A. Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

1.2 SUMMARY

A. This Section specifies administrative and procedural requirements for handling and processing Contract modifications.

B. Related Sections include the following:

Changes to the Contract may involve close coordination between this Section and Sections listed below.

1. Division 1 Section "Allowances" for procedural requirements for handling and processing allowances.

2. Division 1 Section "Unit Prices" for administrative requirements for using unit prices.

3. Division 1 Section "Product Requirements" for administrative procedures for handling requests for substitutions made after Contract award.

1.3 MINOR CHANGES IN THE WORK

Revise Article title above and paragraph below if EJCDC Document 1910-8 is used and an engineer is authorized to issue a Field Order instead of supplemental instructions authorizing a Minor Change in the Work.

A. Architect will issue[ through Construction Manager] supplemental instructions authorizing Minor Changes in the Work, not involving adjustment to the Contract Sum or the Contract Time, on [AIA Document G710, "Architect's Supplemental Instructions."] [form included at end of Part 3.]

1.4 PROPOSAL REQUESTS

A. Owner-Initiated Proposal Requests:  [Architect] [Construction Manager] will issue a detailed description of proposed changes in the Work that may require adjustment to the Contract Sum or the Contract Time.  If necessary, the description will include supplemental or revised Drawings and Specifications.

Always retain subparagraph below.  Only a Change Order or a Construction Change Directive authorizes Contractor to proceed with a proposed change.

1. Proposal Requests issued by [Architect] [Construction Manager] are for information only.  Do not consider them instructions either to stop work in progress or to execute the proposed change.

Revise 20-day time period in first subparagraph below to suit Project; suggested 20-day time period may be too long for many projects.

2. Within [time specified in Proposal Request] [20 days] <Insert number of days> after receipt of Proposal Request, submit a quotation estimating cost adjustments to the Contract Sum and the Contract Time necessary to execute the change.

a. Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made.  If requested, furnish survey data to substantiate quantities.

b. Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.

c. Include costs of labor and supervision directly attributable to the change.

d. Include an updated Contractor's Construction Schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship.  Use available total float before requesting an extension of the Contract Time.

B. Contractor-Initiated Proposals:  If latent or unforeseen conditions require modifications to the Contract, Contractor may propose changes by submitting a request for a change to [Architect] [Construction Manager].

1. Include a statement outlining reasons for the change and the effect of the change on the Work.  Provide a complete description of the proposed change.  Indicate the effect of the proposed change on the Contract Sum and the Contract Time.

2. Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made.  If requested, furnish survey data to substantiate quantities.

3. Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.

4. Include costs of labor and supervision directly attributable to the change.

5. Include an updated Contractor's Construction Schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship.  Use available total float before requesting an extension of the Contract Time.

6. Comply with requirements in Division 1 Section "Product Requirements" if the proposed change requires substitution of one product or system for product or system specified.

C. Proposal Request Form:  Use [AIA Document G709 for Proposal Requests] [forms provided by Owner.  Sample copies are included at end of this Section].

1.5 ALLOWANCES

A. Allowance Adjustment:  To adjust allowance amounts, base each Change Order proposal on the difference between purchase amount and the allowance, multiplied by final measurement of work-in-place.  If applicable, include reasonable allowances for cutting losses, tolerances, mixing wastes, normal product imperfections, and similar margins.

1. Include installation costs in purchase amount only where indicated as part of the allowance.

2. If requested, prepare explanation and documentation to substantiate distribution of overhead costs and other margins claimed.

Delete both subparagraphs below if no unit-cost allowances.

3. Submit substantiation of a change in scope of work, if any, claimed in Change Orders related to unit-cost allowances.

Subparagraph below reflects the major problem of unit-cost allowances.  No matter who performs the Work, a final quantity survey is needed.

4. Owner reserves the right to establish the quantity of work-in-place by independent quantity survey, measure, or count.

Paragraph and subparagraphs below are expanded in AIA Document A201.  If the Supplementary Conditions modify the provisions in AIA Document A201, coordinate requirements with the Supplementary Conditions.

Revise number of days indicated below to suit Project; suggested 21-day time period may be too long for many projects.

B. Submit claims for increased costs because of a change in scope or nature of the allowance described in the Contract Documents, whether for the Purchase Order amount or Contractor's handling, labor, installation, overhead, and profit.  Submit claims within [21] <Insert number> days of receipt of the Change Order or Construction Change Directive authorizing work to proceed.  Owner will reject claims submitted later than [21] <Insert number> days after such authorization.

Both subparagraphs below severely restrict Contractor's markup for overhead and profit.  Delete these requirements if the Supplementary Conditions contain these or similar restrictions.  To stipulate maximum amounts for indirect expenses, see AIA Document A511, "Guide for Supplementary Conditions," for suggested modifications to AIA Document A201.

1. Do not include Contractor's or subcontractor's indirect expense in the Change Order cost amount unless it is clearly shown that the nature or extent of work has changed from what could have been foreseen from information in the Contract Documents.

2. No change to Contractor's indirect expense is permitted for selection of higher- or lower-priced materials or systems of the same scope and nature as originally indicated.

1.6 CHANGE ORDER PROCEDURES

A. On Owner's approval of a Proposal Request, [Architect] [Construction Manager] will issue a Change Order for signatures of Owner and Contractor on [AIA Document G701] [form included at end of Part 3].

1.7 CONSTRUCTION CHANGE DIRECTIVE

Revise Article title above and first paragraph and subparagraph below if EJCDC Document 1910-8 is used and an engineer is authorized to issue a Work Change Directive instead of a Construction Change Directive.

Revise first paragraph and subparagraph if Owner requires use of a special form.

A. [Construction] [Work] Change Directive:  [Architect] [Construction Manager] may issue a [Construction] [Work] Change Directive on [AIA Document G714] [EJCDC Document 1910-8-F] [form included at end of Part 3].  [Construction] [Work] Change Directive instructs Contractor to proceed with a change in the Work, for subsequent inclusion in a Change Order.

1. [Construction] [Work] Change Directive contains a complete description of change in the Work.  It also designates method to be followed to determine change in the Contract Sum or the Contract Time.

B. Documentation:  Maintain detailed records on a time and material basis of work required by the [Construction] [Work] Change Directive.

1. After completion of change, submit an itemized account and supporting data necessary to substantiate cost and time adjustments to the Contract.

PART 2 -  PRODUCTS (Not Used)

PART 3 -  EXECUTION (Not Used)

If Owner requires use of special forms, include sample copies here.

END OF SECTION 01250

CONTRACT MODIFICATION PROCEDURES
01250 - 1

