Copyright 1998 AIA
MASTERSPEC
9/98

NIH Version based on AIA MASTERSPEC dated 9/98 and GSA MASTERSPEC dated 9/99

NIH Version dated January 2002

This section uses the term Contracting Officer, Contracting Officer's Technical Representative and/or Project Officer in specific locations within this section based on specific authorities granted each individual under the terms of the contract.  Any changes in these terms at specific locations within these specifications must be coordinated with the Contracting Officer.

<Text> requires insertion of data

[text] requires decision to delete, retain, or edit text in brackets

SECTION 01330 - SUBMITTAL PROCEDURES
PART 1 -  GENERAL

1.1 RELATED DOCUMENTS

A. Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

1.2 SUMMARY

A. This Section includes certain administrative and procedural requirements for shop drawings, coordination drawings, fire protection working plans, schedules, samples and certain other quality assurance submittals.

B. Related Sections:  This specification section is related to any and all specification sections with explicit or implicit reference to submittals.  Specific submittal requirements of these related specification sections are not included in this section.  Related sections include but are not limited to the following specification sections:

Edit the following list to include pertinent Division 1 sections included in the project.

1. Division 1 Section "Summary"

2. Division 1 Section "Project Management and Coordination"

3. Division 1 Section "Construction Progress Documentation"

4. Division 1 Section "Photographic Documentation"

5. Division 1 Section "Quality Requirements"

6. Division 1 Section "References"

7. Division 1 Section "Construction Quality Control"

8. Division 1 Section "Temporary Facilities and Controls"

9. Division 1 Section "Use, Handling, Storage, Transporting, Accumulation and Disposal of NIH Controlled Material"

10. Division 1 Section "Temporary Traffic Controls"

11. Division 1 Section "Safety and Health"

12. Division 1 Section "Product Requirements"

13. Division 1 Section "Execution Requirements"

14. Division 1 Section "Cutting and Patching"

15. Division 1 Section "Selective Demolition"

16. Division 1 Section "Fire Precautions for Hot Work"

17. Division 1 Section "Closeout Procedures"

18. Division 1 Section "Project Record Documents"

19. Division 1 Section "Operation and Maintenance Documentation"

20. Division 1 Section "Demonstration and Training"

1.3 DEFINITIONS

A. Action Submittals:  Written and graphic information that is specified in the contract documents as requiring NIH approval or other NIH action.

B. Informational Submittals:  Written and graphic information that is not specifically indicated as requiring NIH approval or other NIH action but is indicated as a submittal in the specifications.  Informational submittals may be rejected by NIH for not complying with requirements.

C. Shop drawings:  Drawings and schedules specifically prepared for the project, except for coordination drawings.

D. Coordination drawings:  See Division 1 Section "Project Management and Coordination" For definition and contract requirements.

E. Product data:  Manufacturer's standard catalogs, pamphlets and other printed materials, and includes but is not limited to the following:

1. Product specifications

2. Installation instructions

3. Color charts

4. Catalog cuts

5. Rough-in diagrams and templates

6. Wiring diagrams

7. Performance curves

8. Operational range diagrams

9. Mill reports

F. Samples:  Product samples of such scale to allow delivery for review, as well as field samples or mock-ups of full-size physical examples erected on-site or elsewhere, or establish a true-scale standard by which the corresponding work will be judged or a standard for compliance testing.

G. Other quality assurance submittals include materials specifically prepared for the project, except drawings and schedules, and include but are not limited to the following:

1. Design data and calculations

2. Certifications of compliance or conformance

3. Manufacturer's instructions and field reports

1.4 GENERAL SUBMITTAL REQUIREMENTS

A. Coordination:  Coordinate preparation and processing of submittals with performance of construction activities and with the Submittal Schedule specified in Division 1 Section "Construction Progress Documentation."

The following paragraph includes a requirement for the design architect or engineer to designate each submittal required as either an action submittal or an informational submittal on the submittal register.  Action submittals must be distinctly marked with a "G".  Submittals not so designated on the register will be informational submittal by default.  Coordinate with the Project Officer which submittals are action submittals.

B. All submittals will be certified by the Contractor as conforming to the requirements of the contract documents prior to being forwarded to the Contracting Officer.

1. Submittals identified with a "G" adjacent to the requirement on the submittal register are action submittals and require NIH approval prior to the product or item submitted being incorporated into the project.

2. Submittal requirements without the action designation are informational submittals and should be submitted for information prior to the product or item submitted being incorporated into the work.

C. All submittals shall be transmitted to the Contracting Officer within 30 calendar days after receipt of Notice to Proceed, unless the approved Submittal Schedule specifically provides for an earlier or later submission.  Transmit each submittal sufficiently in advance of the scheduled performance of related construction activities to avoid delaying the work, allowing for the review times specified in this section.

Retain the following two paragraphs with sub-paragraphs if one submittal may have impact on another submittal.

D. Coordinate each submittal with other submittals and related activities that require sequential scheduling, to allow for testing, purchase, fabrication and product delivery in a timely manner.

E. Schedule transmittal of different categories of submittals for the same Definable Feature of Work (DFOW) and for different elements of related parts of the work at the same time so as to minimize delay because of the need to review submittals concurrently for coordination.  See Division 1 Section "Construction Quality Control" for definition of DFOW

1. NIH reserves the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.

The following paragraph and sub paragraphs are the primary location for designating submittal review time lines and drives the incorporation of submittal review time in the project schedule per Division 1 Section "Construction Progress Documentation."

Tailor submittal requirements as appropriate.  Delete "preliminary submittal review" subparagraph if not included in Division 1 Section "Construction Progress Documentation."

Tailor review time requirements as appropriate.  Unless directed otherwise by the Project Officer, assume NIH will use the design architect or engineer for submittal review.  Allow additional time for review of items related to work of the lead designer's consultants (MEP, elevators, security systems, etc).  Coordinate submittal review timelines with the Project Officer prior to completing this section.

F. Allow sufficient time for submittal review, corrections following the initial review and resubmittal review before activities scheduled after the submittal approval.

1. Preliminary submittal review:  Allow <Insert number of days> calendar days from receipt by NIH of the submittal for preliminary review

2. Initial submittal review:  Allow <Insert number of days> calendar days from receipt by NIH of the submittals for the initial review.  If consultants are included in the review process add an additional <Insert number of days> for review.

3. Any resubmission required after NIH review shall be made within <Insert number of days> calendar days after return of the submittal, unless specifically authorized otherwise by the Project Officer.

4. Resubmittal review:  Allow <Insert number of days> calendar days from receipt by NIH of the submittals for the initial review.  If consultants are included in the review process add an additional <Insert number of days> for review.

Edit the following subparagraph and add additional subparagraphs as required for the project.

5. Special Review Timelines:

a. Provide not less than 30 calendar days for review of each fire protection submittal and resubmittal.

Edit the following paragraph if construction will be allowed to proceed without approved submittals.  Coordinate with the Project Officer prior to editing.

G. Construction will generally not be allowed to proceed without approved submittals.  The Contracting Officer may, as requested in writing on a case-by-case basis, allow construction to proceed with submittal approval pending.  Failure by the Contractor to provide the required submittals in a timely manner will not result in an extension to the Contractor's Construction Schedule.

H. Failure by the Contractor to provide the required submittals in a timely manner may result in progress payment requests being returned to the Contractor until submittals are up-to-date.

I. Submittal Preparation:  Identify and prepare drawings and samples as specified in the Construction Contract Clauses and other specification sections.  Provide a permanent label on each submittal with the following information:

1. Project name, contract number and work request number.

2. Date of submission

3. Name, address and telephone number of firm or entity that prepared the submittal.

4. Name, address and telephone number of the Contractor.

5. Name, address and telephone number of the subcontractor, supplier or manufacturer.

6. Number and title of appropriate specification section.

7. Drawing number and detail references, as appropriate.

8. Space to record Contractor's review and approval markings approximately 5 by 5 inches (250 by 250 mm).

9. A blank page with a listing of all pages in the submittal shall be attached to the front of the submittal package with at least a 4" by 6" space for the NIH.

J. Submittal Transmittal:  Package each submittal for transmission and handling.  Transmit each submittal from the Contractor to the Contracting Officer by use of a transmittal form.  The following minimum information shall be included on the transmittal form.

1. Project name and number.

2. Date

3. Destination (To:)

4. Source (From:)

5. Names of subcontractor, manufacturer and supplier, as applicable.

6. Category of submittal

7. Description of submittal

8. Number and title of appropriate specification section.

9. Submittal number, including means to separately identify initial submittal and each resubmittal.

10. Certification by Contractor stating that submittal complies with the Contract Documents, or statement of deviations from the requirements of the Contract Documents including minor variations and limitations.  Deviations may be listed on an attached sheet referenced on the transmittal form.

11. Signature of transmitter.

For projects with complicated submittals and/or compressed construction times direct transmission to the lead designer's consultants may be a reasonable option to improve project progress.  Procedure in subparagraph below may cause tracking challenges for the designer and/or Construction Manager, if any.  Procedure may be more appropriate in the Construction Manager's contract.  Include the following paragraph if direct transmittal will be allowed.  Select appropriate designer.  Delete if not allowed.  Coordinate with the Project Officer.

K. Direct Transmittal to Consultant:  When allowed by the Project Officer, submittals may be transmitted directly to design [Architect's][A&E's][Engineer's] consultants, provide duplicate copy of transmittal to [Architect's][A&E's][Engineer's] and Project Officer.  The consultant will return submittal to the [Architect][A&E][Engineer] for return to the Contractor.

Direct transmittal may be allowed or required without identifying specific submittals.  As an option, insert list of submittals below for which direct transmittal to the designer's consultant may or must be used or delete sub paragraph below and identify submittals in the appropriate technical specification section.  Structural, mechanical, plumbing, and electrical components are examples of the work that often benefit from direct transmittal to consultants.

1. <Insert list of specific submittals or specification sections requiring direct transmittal to consultant.>

L. Certifications: Submit notarized certifications from the party certifying compliance of the submittal with specified requirements. Certifications shall be signed by an officer or other individual authorized to sign documents on behalf of the company certifying compliance.  Certifications shall be as described in Division 1 Section "Construction Quality Control."

M. Delegated-Design Submittal:  Comply with requirements in Division 1 Section "Quality Requirements."

N. Contractor's Construction Schedule:  Comply with requirements in Division 1 Section "Construction Progress Documentation."

O. Submittal Schedule:  Comply with requirements in Division 1 Section "Construction Progress Documentation."

PART 2 -  PRODUCTS

2.1 ACTION SUBMITTALS

A. General:  Prepare and submit Action Submittals required by individual Specification Sections.

B. Product Data:  Collect information into a single submittal for each element of construction and type of product or equipment.

1. If information must be specially prepared for submittal because standard printed data are not suitable for use, submit as Shop Drawings, not as Product Data.

2. Mark each copy of each submittal to show which products and options are applicable to the project.

3. Include the following information, as applicable:

Expand list below to suit Project.

a. Manufacturer's written recommendations.

b. Manufacturer's product specifications.

c. Manufacturer's installation instructions.

d. Standard color charts.

e. Manufacturer's catalog cuts.

f. Wiring diagrams showing factory-installed wiring.

g. Printed performance curves.

h. Operational range diagrams.

i. Mill reports.

j. Standard product operating and maintenance manuals.

k. Compliance with recognized trade association standards.

l. Compliance with recognized testing agency standards.

m. Application of testing agency labels and seals.

n. Notation of coordination requirements.

o. Notation of dimensions verified for fit by field measurements.

Retain first subparagraph below as default requirement or insert requirement if number of copies is same for all types of submittals.  Additional copies may be required for projects with a construction manager.  Delete if specific quantity requirements are included with individual submittal requirements elsewhere in this Article.  Coordinate number of submittal copies required with the Project Officer.

Retain second subparagraph below if two-step submittal process is required.

4. Number of Copies:  Submit [three] <Insert number> copies of each submittal, unless otherwise indicated.  NIH will return [two] <Insert number> copies.  Mark up and retain one returned copy as a Project Record Document.

5. Number of Copies:  Submit copies of each submittal, as follows, unless otherwise indicated:

a. Preliminary Submittal:  Submit a single copy of each submittal where selection of options, color, pattern, texture, or similar characteristics is required.  NIH will return submittal with options selected.

b. Initial Submittal:  Submit [three] <Insert number> copies, unless copies are required for operation and maintenance manuals.  Submit [five] <Insert number> copies where copies are required for operation and maintenance manuals.  NIH will retain [two] <Insert number> copies; remainder will be returned.  Mark up and retain one returned copy as a Project Record Document.

C. Shop Drawings:  Prepare and submit originally prepared information, drawn accurately to scale.  Do not reproduce Contract Documents or copy standard printed materials as the basis for Shop Drawings and Coordination Drawings.

1. Preparation:  Include the following information, as applicable:

Revise or expand list below to suit Project.  Comply with Owner's requirements and office policy.

a. Dimensions.

b. Identification of products and materials.

c. Fabrication and installation drawings.

d. Roughing-in and setting diagrams.

e. Wiring diagrams showing field-installed wiring, including power, signal, and control wiring.

f. Shopwork manufacturing instructions.

g. Templates and patterns.

h. Schedules.

i. Design calculations.

j. Compliance with specified standards.

k. Notation of coordination requirements.

l. Notation of dimensions established by any field measurement.

m. Highlighted or encircled deviations from the Contract Documents, if any.

2. Wiring Diagrams:  Differentiate between manufacturer-installed and field-installed wiring.

Revise subparagraph below to establish a standard sheet size and format.

3. Sheet Size:  Except for templates, patterns, and similar full-size drawings, submit Shop Drawings on sheets at least 8-1/2 by 11 inches (215 by 280 mm) but no larger than 30 by 42 inches (750 by 1000 mm).

Retain one of the three subparagraphs below; first and second are one-step procedure; third is two-step procedure (initial and final submittals).  First subparagraph assumes Architect and Contractor will make prints from the reproducible print.

4. Number of Copies:  Submit one correctable, translucent, reproducible print [and one blue- or black-line print] of each submittal. Architect [, through Construction Manager,] will return the reproducible print.

5. Number of Copies:  Submit [three] <Insert number> blue- or black-line prints of each submittal, unless prints are required for operation and maintenance manuals.  Submit [five] <Insert number> prints where prints are required for operation and maintenance manuals.  Architect [and Construction Manager] will retain [two] <Insert number> prints; remainder will be returned. [Mark up and retain one returned print as a Project Record Drawing.]

6. Number of Copies:  Submit copies of each submittal, as follows:

Select one of two subparagraphs below.  First is preferred method of handling Shop Drawings.

a. Initial Submittal:  Submit one correctable, translucent, reproducible print and one blue- or black-line print.  The reproducible print will be returned.

Retain subparagraph below only for small projects.

b. Initial Submittal:  Submit [two] <Insert number> blue- or black-line prints.  One print will be returned.

Retain option of additional prints for NIH distribution if initial submittal is a reproducible print.

c. Final Submittal:  Submit [three] <Insert number> blue- or black-line prints, unless prints are required for operation and maintenance manuals.  Submit [five] <Insert number> prints where prints are required for operation and maintenance manuals.  NIH will retain [two] <Insert number> prints; remainder will be returned.  [Mark up and retain one returned print as a Project Record Drawing.]

D. Coordination Drawings:  Comply with requirements in Division 1 Section "Project Management and Coordination."

E. Fire Protection Working Plan Submittals: Submit fire protection working plans, prepared in full compliance with all requirements stated in NFPA-13.  Sheets shall be no smaller than 30 by 42 inches.

F. Samples:  Prepare physical units of materials or products, including the following:

1. Comply with requirements in Division 1 Section "Quality Requirements" for mockups.

Delete subparagraph below if colors and other characteristics are preselected and specified or scheduled.

2. Samples for Initial Selection:  Submit manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available.

Subparagraph below can be used with or without Samples for initial selection.

3. Samples for Verification:  Submit full-size units or Samples of size indicated, prepared from the same material to be used for the work, cured and finished in manner specified, and physically identical with the product proposed for use, and that show full range of color and texture variations expected.  Samples include, but are not limited to, the following:  partial sections of manufactured or fabricated components; small cuts or containers of materials; complete units of repetitively used materials; swatches showing color, texture, and pattern; color range sets; and components used for independent testing and inspection.

4. Preparation:  Mount, display, or package Samples in manner specified to facilitate review of qualities indicated.  Prepare Samples to match Architect's sample where so indicated.  Attach label on unexposed side that includes the following:

Expand list below to suit Project.

a. Generic description of Sample.

b. Product name or name of manufacturer.

c. Sample source.

Information in subparagraph below may be difficult to obtain.  Request only if required for construction.

5. Additional Information:  On an attached separate sheet, prepared on Contractor's letterhead, provide the following:

a. Size limitations.

b. Compliance with recognized standards.

c. Availability.

d. Delivery time.

6. Submit Samples for review of kind, color, pattern, and texture for a final check of these characteristics with other elements and for a comparison of these characteristics between final submittal and actual component as delivered and installed.

a. If variation in color, pattern, texture, or other characteristic is inherent in the product represented by a Sample, submit at least [three] <Insert number> sets of paired units that show approximate limits of the variations.

Retain subparagraph below where Samples are required to illustrate assembly of different components that comprise a single element, such as a corner section of an operable window.

b. Refer to individual Specification Sections for requirements for Samples that illustrate workmanship, fabrication techniques, details of assembly, connections, operation, and similar construction characteristics.

Revise first two subparagraphs below if Project requires a different procedure.  Consider indicating Samples for initial selection as a separate item in the Submittals Schedule.

7. Number of Samples for Initial Selection:  Submit [one] <Insert number> full set[s] of available choices where color, pattern, texture, or similar characteristics are required to be selected from manufacturer's product line.  The submittal will be returned with options selected.

8. Number of Samples for Verification:  Submit [three] <Insert number> sets of Samples.  NIH will retain [two] <Insert number> Sample sets; remainder will be returned.  [Mark up and retain one returned Sample set as a Project Record Sample.]

a. Submit a single Sample where assembly details, workmanship, fabrication techniques, connections, operation, and other similar characteristics are to be demonstrated.

9. Disposition:  Maintain sets of approved Samples at Project site, available for quality-control comparisons throughout the course of construction activity.  Sample sets may be used to determine final acceptance of construction associated with each set.

Delete first subparagraph below if not required.

a. Samples that may be incorporated into the work are indicated in individual Specification Sections.  Such Samples must be in an undamaged condition at time of use.

b. Samples not incorporated into the work, or otherwise designated as Owner's property, are the property of Contractor.

Indicate specific number of copies required with each type of submittal in two paragraphs and associated subparagraphs below if different from default requirement above.

G. Product Schedule or List:  Prepare a written summary indicating types of products required for the work and their intended location.  Include the following information in tabular form:

1. Type of product.  Include unique identifier for each product.

2. Number and name of room or space.

3. Location within room or space.

2.2 INFORMATIONAL SUBMITTALS

A. General:  Prepare and submit Informational Submittals required by other Specification Sections.  General qualitative requirements are as specified for Action Submittals elsewhere in this section unless otherwise indicated in this Article.

Retain first subparagraph below as default requirement or insert requirement if number of copies is same for all types of submittals.  Additional copies may be required for projects with a construction manager.  Delete if specific quantity requirements are included with individual submittal requirements elsewhere in this Article.

1. Number of Copies:  Submit [two] <Insert number> copies of each submittal, unless otherwise indicated.  NIH will not return copies.

2. Certificates and Certifications:  Provide a notarized statement that includes signature of entity responsible for preparing certification.  Certificates and certifications shall be signed by an officer or other individual authorized to sign documents on behalf of that entity.

3. Test and Inspection Reports:  Comply with requirements in Division 1 Section "Construction Quality Control."

Tailor the following paragraphs.  Delete those that are not required for the project.  Coordinate with requirements identified in the technical specification sections in Divisions 2-16.

B. Contractor's Construction Schedule:  Comply with requirements in Division 1 Section "Construction Progress Documentation."

C. Qualification Data:  Prepare written information that demonstrates capabilities and experience of firm or person as required in the technical specifications and in Division 1 Section " Construction Quality Control."  Include lists of completed projects with project names and addresses, names and addresses of architects and owners, and other information specified.

D. Product Certificates:  Prepare written statements on manufacturer's letterhead certifying that product complies with requirements.

E. Welding Certificates:  Prepare written certification that welding procedures and personnel comply with requirements.  Submit record of Welding Procedure Specification (WPS) and Procedure Qualification Record (PQR) on AWS forms.  Include names of firms and personnel certified.

F. Installer Certificates:  Prepare written statements on manufacturer's letterhead certifying that Installer complies with requirements and, where required, is authorized for this specific Project.

G. Manufacturer Certificates:  Prepare written statements on manufacturer's letterhead certifying that manufacturer complies with requirements.  Include evidence of manufacturing experience where required.

H. Material Certificates:  Prepare written statements on manufacturer's letterhead certifying that material complies with requirements.

I. Material Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting test results of material for compliance with requirements.

J. Preconstruction Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of tests performed before installation of product, for compliance with performance requirements.

K. Compatibility Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of compatibility tests performed before installation of product.  Include written recommendations for primers and substrate preparation needed for adhesion.

L. Field Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of field tests performed either during installation of product or after product is installed in its final location, for compliance with requirements.

M. Product Test Reports:  Prepare written reports indicating current product produced by manufacturer complies with requirements.  Base reports on evaluation of tests performed by manufacturer and witnessed by a qualified testing agency, or on comprehensive tests performed by a qualified testing agency.

Coordinate individual Specification Sections with paragraph below by including specific model code organization in that Section.  If all are same, insert name below.

N. Research/Evaluation Reports:  Prepare written evidence, from a model code organization acceptable to authorities having jurisdiction, that product complies with building code in effect for Project.  Include the following information:

1. Name of evaluation organization.

2. Date of evaluation.

3. Time period when report is in effect.

4. Product and manufacturers' names.

5. Description of product.

6. Test procedures and results.

7. Limitations of use.

Select the appropriate section in this project for O&M data

O. Maintenance Data:  Prepare written and graphic instructions and procedures for operation and normal maintenance of products and equipment.  Comply with requirements in Division 1 Section "[Closeout Procedures] [Operation and Maintenance Data]."

P. Design Data:  Prepare written and graphic information, including, but not limited to, performance and design criteria, list of applicable codes and regulations, and calculations.  Include list of assumptions and other performance and design criteria and a summary of loads.  Include load diagrams if applicable.  Provide name and version of software, if any, used for calculations.  Include page numbers.

Q. Manufacturer's Instructions:  Prepare written or published information that documents manufacturer's recommendations, guidelines, and procedures for installing or operating a product or equipment.  Include name of product and name, address, and telephone number of manufacturer.  Include the following, as applicable:

1. Preparation of substrates.

2. Required substrate tolerances.

3. Sequence of installation or erection.

4. Required installation tolerances.

5. Required adjustments.

6. Recommendations for cleaning and protection.

R. Manufacturer's Field Reports:  Prepare written information documenting factory-authorized service representative's tests and inspections.  Include the following, as applicable:

1. Name, address, and telephone number of factory-authorized service representative making report.

2. Statement on condition of substrates and their acceptability for installation of product.

3. Statement that products at Project site comply with requirements.

4. Summary of installation procedures being followed, whether they comply with requirements and, if not, what corrective action was taken.

5. Results of operational and other tests and a statement of whether observed performance complies with requirements.

6. Statement whether conditions, products, and installation will affect warranty.

7. Other required items indicated in individual Specification Sections.

S. Insurance Certificates and Bonds:  Prepare written information indicating current status of insurance or bonding coverage.  Include name of entity covered by insurance or bond, limits of coverage, amounts of deductibles, if any, and term of the coverage.

T. Construction Photographs [and Videotapes]:  Comply with requirements in Division 1 Section "Photographic Documentation."

Usually delete the following paragraph.  Receipt of Material Safety Data Sheet information by Architect or Engineer may result in unwanted liability for product safety.

2.3 Material Safety Data Sheets:  Submit information directly to NIH.  MSDS sheets submitted directly to [Architect][Engineer] will be returned.

PART 3 -  EXECUTION

3.1 CONTRACTOR'S REVIEW

A. Review each submittal prior to transmission to NIH and check for compliance with the Contract Documents.  Note corrections and field dimensions.  Mark with certification stamp before submitting to NIH

B. Certification Stamp:  Stamp each submittal with a uniform certification stamp.  Include Project name and location, submittal number, Specification Section title and number, name of reviewer, date of Contractor's certification, and statement certifying that submittal has been reviewed, checked, and complies with the Contract Documents.

3.2 NIH ACTION

A. Except for submittals for record or for information or for another purpose where no action and return is required, the Contracting Officer will review submittals and mark returned copies to indicate action taken.

B. Compliance with specified characteristics is the Contractor's responsibility, and is not part of the Contracting Officer's review and indication of action taken.  No matter what review action is taken, final acceptance will depend on the contractor's full compliance with the Contract Documents.

C. Submittals that do not contain the required marking of approval by the Contracting Officer, as indicated in the specifications, shall not be used for construction.

D. Action Stamp:  Each submittal will be stamped with a uniform action stamp. The stamp shall be marked to indicate one of the following actions taken:

1. "Approved" or "Approved as Submitted":  The work covered by the submittal may proceed, provided it complies with the notations or corrections on the submittal and with the requirements of the Contract Documents.

2. "Approved as noted, Resubmission not required":  The contractor is authorized to proceed with work as noted provided the contractor takes no exception to the notations.

3. "Approved as noted, Resubmission Required": The contractor is authorized to proceed with portions of the work as noted.  The contractor must resubmit those items/components so noted with additional information or requirements, for approval, before work may proceed on that portion of the submittal.

4. "Disapproved":  The submittal is incomplete or does not comply with design concept or requirements of the contract documents.  No work shall proceed for this item until resubmittal with appropriate changes is approved.

5. "Not Reviewed":  A submittal marked "not reviewed" will indicate submittal does not have evidence of being reviewed and certified by the Construction Contractor, or is not complete.  A submittal marked "not reviewed" will be returned with an explanation of the reason it is not reviewed.  Resubmit submittals which are returned for lack of review by the contractor or for being incomplete, with appropriate action, coordination, or change.

6. "Receipt Acknowledged" or no action:  Submittals which are for the record or for information only or for another purpose not requiring review action.

END OF SECTION 01330

SUBMITTAL PROCEDURES
01330 - 13

