## Overview
Date: | 2012-09-20
Initial Inspection and Data Collection
Is the structure in a High-Risk Flood Hazard Area2 per ASCE 24 Section 3?
Determine Mitigation Measure
Develop Cost Estimate
Application Development Resources
EHP (Checklist)
Consider if it is a Substantial Improvement?
Approval of Grant
Pre-Award Conditions
Design Work and (Design Checklist3)
Bid Process
Based on costs of bid results , re-confirm Substantial Improvement determination and verify BCR
Pre-Construction and Walk-Through (Checklist)
Construction and Inspections
(Construction Checklist3 ) and Compliance Checks
Certificate of Occupancy
Final Walk-Through (Checklist) and Punch-List Items
Project Closeout (Checklist)
Consider if E.O. 11988 applies
In Zone V or Coastal A Zone – does the erosion control issue1 apply?
Yes -Waiver
No Waiver
Mitigation Project Flowchart
1: If a building is located in a Zone V or Coastal A Zone, and if either a) or b) of the following is true, the building is not eligible: a) the building foundation is attached to an erosion control structure, or b) the building foundation is not attached to an erosion control structure, but an erosion control structure focuses flood forces (wave runup, wave reflection, flow diversion) or erosion impacts on the building or its foundation.
Stop
May consider re-evaluation of Mit. Measures
Choose a measure
Yes or No - Mit. Measure Acceptable
Corrections
Option B
Option A
3: Design Checklist and Construction Checklist refer to tabs named for each mitigation type (e.g., Elevation (New Fnd) Design_Const).
Consider if the structure is Substantially Damaged or will it be Substantially Improved
BCA Input Resources
2: High-Risk Flood Hazard Area: flood hazard area where one or more of the following hazards are known to occur: alluvial fan flooding, flash floods, mudslides, ice jams, high-velocity flows, high-velocity wave action, breaking wave heights greater than or equal to 1.5 ft (Coastal High-Hazard Area or Coastal A Zone), or erosion.
Stop
No
Yes
Cost-Effective
Cost-Effective
Click on Button-Boxes to Navigate Checklists
Checklist Tabs are color coded with the flowchart box colors
Yes
Yes
No
Description of Checklists

## Description of Checklists
Description of Checklists: Guidance ASCE 24 Engineering Standards for HMA Flood Retrofitting and Reconstruction Projects
1. Overview - a flowchart representing the project and grant application "life cycle" with ASCE 24-specific considerations and showing at what point in the process each checklist is meant to be used. Clicking on any of the checklist buttons/boxes will take you to that specific worksheet within the Excel file.
2. Initial Inspection and Data Collection - targeted to the local entity or representative who is beginning the process of project development and is at a building site collecting data for a potential project. This sheet may not be completed in one visit, but it is intended to prompt the user about important project considerations.
3. Cost Estimate Example Sheet - targeted to the local entity (or designer) who will be developing the cost estimate. There are many instances where cost estimates overlook important work items that may impact the Benefit-Cost Analysis; this sheet prompts users to consider these work items.
4. BCA Flood - for the local entity (or state agency providing technical support) putting the BCA together to facilitate data collection for use with the BCA software. This sheet asks the same questions as the BCA flood module. The concept is that a user can answer all of the appropriate questions prior to opening the software. The Damage Frequency Assessment Data Documentation Template is also included should it be needed for developing the BCA.
5. EHP Checklist - for the local entity (or state agency providing technical support) to facilitate data collection for EHP considerations
6. Application Contents Checklist - for the local entity (or state agency providing technical support) to help with overall application development. This checklist asks similar questions to the eGrants system and allows users to gather the data prior to opening eGrants. This checklist should help to users answer the questions properly and with sufficient detail.
The next 3 worksheets are all meant for the design professional to ensure consideration of applicable ASCE 24 provisions for each specific project type. Note that these checklists do not need to be used pre-award. Currently an example certification statement is slated to be included in the guidance for use in grant applications to address feasibility/effectiveness requirements. These group of checklists are meant as "job aids" to help designers interpret how ASCE 24 applies to each relevant project type.
7. Mitigation Reconstruc Design Const - for the design professional to ensure consideration of applicable ASCE 24 provisions for Mitigation Reconstruction projects.
8. Elevation Design Const - for the design professional to ensure consideration of applicable ASCE 24 provisions for Elevation projects .
9. Dry Floodproofing Design Const - for the design professional to ensure consideration of applicable ASCE 24 provisions for dry floodproofing projects.
10. Pre Construction Checklist - targeted to local entity to assist with site/building preparation prior to construction. It is intended to provide the local entity with an idea of how to go through a building prior to construction to document the existing building quality prior to retrofitting. Sheets similar to this have been used to limit call-backs and claims regarding retrofits.
11. Project Closeout - for use by local entity, and potentially state agency serving as grantee to ensure appropriate actions have been taken in conducting project close out. This is consistent with requirements covered in the HMA guidance.
12. Mit Button – A link back to other worksheets. No content for review.
Back to Flowchart

## Initial Inspection and Data Col
Initial Inspection and Data Collection Checklist |  |  | Date:
(Example checklist/inspection report for retrofitting projects) |  |  | 2012-09-20
(This sheet may be typically completed by a local building official, a floodplain manager with some construction experience, or an engineer/architect)
Question/Concern | (inputs) | Notes
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Residential/Nonresidential (select)
Preliminary | (Y/N) | Notes
Right-to Enter Agreement |  | Is there a Right-to-Enter Agreement signed by the owner in the grant application folder?
Tax Card |  | Is there a County or Jurisdiction Property Tax Card within the grant application folder?
Photographs |  | Take a photograph of each side of the building (this may require multiple photos of each side. In order to document the size and shape of the building. Other photographs should document any site conditions that may make access to the building difficult.
Termite Inspection Report |  | (within 1 year of beginning the project)
Asbestos Inspection Report |  | (within 1 year of beginning the project)
Lead Paint Testing |  | (within 1 year of beginning the project)
Location Map |  | The location map should provide an overall location of the building to allow it to be located on a FIRM and a more detailed location map to assist in evaluating site issues during the construction phase.
Latitude ( enter value): |  | (decimal degrees)
Longitude (enter value): |  | (decimal degrees)
Year of Construction (enter value): |  | (for larger buildings this may require multiple dates)
Coordinate Site Visit with the Following:
Owner (Y/N):
Building Inspector (Y/N):
Initial Review |  | Notes
Physical Description of Building Lot: |  | Attach a phyical lot description to the grant application information, which details access issues, general topography, whether the lot is open or treed, and any other buildings in close proximity to the building under consideration for the grant application.
Flood Source (select):
Flood Zone (select): |  | https://msc.fema.gov/webapp/wcs/stores/servlet/FemaWelcomeView?storeId=10001&catalogId=10001&langId=-1
Base Flood Elevation (enter value): | 0
Vertical Datum |  | The vertical datum should be consistent with the flood maps and should be clearly noted
Community Enforced Freeboard (ft) (enter value): | 0 | Freeboard is additional elevation above the base flood elevation typically measured in feet.
Design Flood Elevation (enter value): | 0 | DFE may be BFE plus locally enforced freeboard or program-required freeboard
Finish Floor Elevation (enter value): | 0
Proposed Elevation Height (minimum of one ft above BFE): | 1
Estimated Finished Floor Elevation: | 1
Estimated Feet of Elevation: | 1
Highest Adjacent Grade:
Lowest Adjacent Grade:
Site-Specific Flooding Characteristics (Scour/Depressions/V-Zones):
(must be reviewed by the engineer to evaluate whether the structure is located in a High-Risk Flood Hazard Area)
Is the building located in a floodway? (Y/N)
Is the bulding located in an alluvial fan, flash flood-prone area, mudslide-prone area, erosion-prone area, high-velocity flow area, an area subject to wave action, or area subject to ice jams or debris? (Y/N) |  | See Section 3 of ASCE 24-05
Are any erosion control structures connected to the building or located on the property? (Y/N) |  | See Section 3.5 of ASCE 24-05
Is the structure a Severe Repetitive Loss Property? (Y/N) |  | A Severe Repetitive Loss (SRL) property is a residential property that is covered under an NFIP flood insurance policy and: (a) That has at least four NFIP claim payments (including building and contents) over $5,000 each, and the cumulative amount of such claims payments exceeds $20,000; or (b) For which at least two separate claims payments (building payments only) have been made with the cumulative amount of the building portion of such claims exceeding the market value of the building. For both (a) and (b) above, at least two of the referenced claims must have occurred within any 10-year period, and must be greater than 10 days apart.
Are there any locally enforced height restrictions which could impact the project? (Y/N) |  | These restrictions could state a maximum allowable height for buildings, such as a maximum allowable roof height.
Are there any locally enforced restrictions on foundation types? (Y/N) |  | These restrictions could state a manditory foundation type for buildings in certain areas, such as a requirement that all buildings in a specific location maintain an open fourndation regardless of flooding conditions.
Building Characteristics: | (Select)
Foundation (select): |  | Review each of the foundation types and evalute which best applies to the building. If none of them apply select other. For example, a continuous footing, spread footing, combination foundation might fall into this category, as would combinbations of materials.
Foundation material (select):
Describe any current enclosures below the BFE:
Superstructure Material (select):
(primary material used to frame the building, not the exterior siding)
Is the building subject to Executive Order 11988? (Y/N)
Is there ductwork, an air handler, or water heater in the crawl space or below the heated/living space? (Y/N)
Complete Structure Perimeter Sketch (attach) (Y/N)
Site Survey Plan will be provided if available.
Environmental Factors
Meeting with owner (if available) (Y/N)
Owner Comments:
Discuss possible impacts of elevating existing first floor elevation (FFE) to meet the ASCE 24 requirements, or floodproofing to ASCE 24 elevation requirements
Describe porches/decks and elevation requirements (Attach sketch if necessary)
Plumbing retrofitting requirements (including water well issues)
Does the existing system have backflow prevention valves? (Y/N)
HVAC retrofitting requirements
Fuel tank retrofitting requirements
Are there any know buried fuel tanks on the site?(Y/N) (if yes add notes)
Are the existing fuel tanks currently anchored to resist flood loads? (Y/N)
Electrical utility retrofitting requirements
Sewer retrofitting requirements (discuss existing deficiencies, including septic tank concerns, with local building inspector if available)
Is the septic system sufficiently anchored to prevent flotation or movement during a design flood event? (Y/N)
Landscaping concerns (site access):
Note any accessibility requirements for disabled individuals (note if occupants are wheelchair-bound or using walker)
Evaluate impact of the elevating or floodproofing the structure on public right-of-way and adjacent property (refer questions concerning setbacks to local building code/development authority)
Ancillary structure locations/dimensions:
(sheds, garages, carports, etc.)
Evaluate obstacles to adequate site access for elevation (including soils limitations)
Review Asbestos Inspection Report (Y/N)
Is this unit listed as a historic structure? (Y/N)
(Coordination with the State Historic Preservation Office may be required)
Structural Feasibility
Describe/photograph any visible signs of distress in existing foundation related to adverse soil conditions or improperly distributed load (provide sketches and attach if necessary):
Describe any concerns related to overall cost/practicality of the FEMA-financed retrofitting/foundation improvement:
Review Termite Inspection Report (Y/N)
Base Floor System: Observation and Opinion of Cost of Repair
Observe the structural condition of base floor system (including subfloor). Describe/photograph visible signs of distress. Provide an opinion of the cost of improvements necessary to allow retrofitting and repair of the base floor framing in accordance with the local building code authority’s interpretation of the International Residential Code or the International Building Code and ASCE 24. Attach sketches if necessary. Note that there are no grant funds available to make required non-FEMA-eligible improvements. Other grant funding may be available for non-FEMA-eligible improvements. This limit does not apply to non-FEMA-eligible improvements that are privately funded. If the base floor system is completely or partially inaccessible and/or, based on observations and review of the termite inspection report, the base floor system may have undisclosed damage requiring repairs, the evaluator should indicate the elevation is deferred for that reason (be as specific as possible).
Superstructure: Observation and Opinion of Cost of Repair
Observe the structural condition of the superstructure (including stud or block walls, ceiling joists, and roof framing where accessible). Describe/photograph visible signs of distress. Provide an opinion of the cost of improvements necessary to allow the structure to withstand the stress of retrofit. (NOTE: The responsibility for the structural integrity of the house with respect to the retrofitting process lies with the retrofit contractor who controls the means and methods of retrofitting.) Attach sketches if necessary. Note that there are no grant funds available to make required non-FEMA-eligible improvements. Other grant funding may be available for non-FEMA-eligible improvements. This limit does not apply to non-FEMA-eligible improvements that are privately funded. If areas of the superstructure suspected to be damaged/decayed are completely or partially inaccessible, and in the inspector’s opinion (based on his/her own inspection and review of the termite inspection report) the superstructure may have undisclosed damage requiring repairs, the evaluator should indicate that retrofitting is deferred for that reason. (Be as specific as possible.)
Recommendations (Transfer to Evaluation Summary Page)
Unit recommended for retrofit using the methods compliant with the Hazard Mitigation Assistance Program, the International Residential Code or International Building Code, and ASCE 24. (Y/N)
Notes:
NOTE TO HOMEOWNER AND LOCATION BUILDING CODE AUTHORITY
This report/recommendation is not intended to certify that the house will be free of damages during the retrofit process or associated with the retrofit process. The recommendation to retrofit is based on a limited review of the house and relies on the fact that similar houses in similar conditions have satisfactorily undergone a flood retrofit. The retrofitting contractor is responsible for the means and methods of retrofitting the house and for closely monitoring the results of imposing loads on the house during the retrofit. The retrofit contractor is responsible for taking whatever action is necessary to minimize damage to the house. The contractor and/or local building code authority may judge that a house is unsuitable for retrofit following commencement of construction.
Unit Deferred for Retrofit (Y/N):
Provide a brief summary of the rationale for deferral:
Evaluator Name (Type or Print):
Date of Evaluation (Enter Value):
Reviewed by Project Engineer (Y/N):
Reviewed by Local Building Official (Y/N):
(Provide a summary of building inspector’s comments, if any, including requests for unit-specific engineering design)
Additional Considerations for Retrofitting Projects
Is public notice required prior to beginning the retrofit? (Y/N)
Is a press release required prior to beginning the retrofit? (Y/N)
What hazards other than flood must be mitigated? (Y/N)
Other Comments:
(These comments may include items that cannot be easily answered with yes or no answers.)
Back to Flowchart

## Cost Estimate Example Sheet
Example Elevation Project Cost Estimate |  |  |  | Date:
The example estimate below is intended to provide users unfamiliar with preparing a construction estimate with an approximate level of detail necessary to complete a flood retrofit project estimate. This estimate was developed for the elevation of a residential structure. Line items may differ for each structure, but should include a sufficient level of detail to conduct a benefit-cost analysis and eliminate unexpected costs during the grant implementation process. |  |  |  | 2012-09-20
Grant ID:
Address:
Property Owner:
Year Project Cost Estimate was developed:
Cost Summary
Description | (inputs) | Notes
Engineering & Design Cost: | 0
Construction Cost: | 0
Total Cost: | 0
Grant Eligible Amount: | 0
Non Federal Obligation: | 0
Estimated Annual Maintenance Costs: | 0
Cost Estimate Quantity Breakdown
General House Features
Residential/Nonresidential (select):
Foundation Type (select): | Basement | Review each of the foundation types and evalute which best applies to the building. If none of them apply select other. For example, a continuous footing, spread footing, combination foundation might fall into this category, as would combinbations of materials.
Superstructure Material (select): |  | (primary material used to frame the building, not the exterior siding)
Exterior Siding (select):
Ductwork, Air Handler, Water Heater below DFE (Y/N):
Amount to Elevate: | 0
Foundation
Wall Height (additional height may be required for ductwork): |  | ft | (see Initial Inspection and Data Collection Sheet)
Building Perimeter (all wall lengths necessary for retrofit): |  | lf
Area of Building to Be Retrofitted (footprint): |  | sf
Number of Piers (if applicable): |  | each
Crawlspace Fill Elevation (if applicable): |  | ft
Exterior Landings
Front Porch Area: |  | sf
Front Rail: |  | lf
Back Porch/Deck (to include side areas): |  | sf
Back Rail: |  | lf
Total Porch Area: |  | sf
Total Rail Length: |  | lf
Porch Columns: |  | each
Sets of Stairs: |  | each
Sets of Ramps: |  | each
Brick Veneer & Chimney
Brick Veneer Area (Removal Quantity): |  | sf
Brick Veneer Area (Replacement Quantity): |  | sf
Chimney Height (Exterior Chimneys): |  | ft
Renovation Work
Slab Floor Area: |  | sf | (some structures may require wood floors constructed to replace existing floor slabs for elevation)
Construction Estimate
Sources for cost estimates may include national cost estimating guides, contractor estimates, design professional, or historical data
Mobilization and Lifting of House
Mobilization: |  | lump sum
Tree Removal: |  | lump sum
Lifting of the Building: |  | lump sum
Subtotal: | 0
Foundation
Fill Crawlspace to Existing Ground: |  | per cubic yard
Demolish Existing Footing & Walls: |  | per square foot
Construct Footing: |  | per linear foot
Construct Perimeter Wall: |  | per square foot
Construct Columns: |  | per each
Flood Vents: |  | per each
Bond Beam: |  | per linear foot
Sill Replacement: |  | per linear foot
Subtotal: | 0
Exterior Landings
Porch Decking: |  | per square foot
Porch Columns: |  | per each
Porch Railing: |  | per linear foot
Stairs: |  | per set
Ramps: |  | per each
Subtotal: | 0
Brick Veneer & Chimney
Brick Removal: |  | per square foot
Brick Replacement: |  | per square foot
Chimney Removal: |  | per each
Chimney Replacement: |  | per each
Chimney Footing: |  | per cubic yard
Subtotal: | 0
Floor Repairs
Repair Floor Area: |  | per square foot
Plumbing/Electrical/Mechanical
Ductwork Removal & Replacement: |  | lump sum
A/C Unit Elevation: |  | lump sum
Water/Sewer Line Extension: |  | lump sum
Gas Line Extension: |  | lump sum
Electrical Service Extension: |  | lump sum
Subtotal: | 0
Renovation Work
Framed Floor: |  | per square foot
Door Removal/Replacement: |  | per each
Replumb Bathroom/Laundry Room: |  | lump sum
Interior Stairs Rework: |  | per set
Garage Door Removal/Reinstallation: |  | lump sum
Reframe Exterior Walls: |  | per square foot
Frame/Construct Mechanical Platform: |  | lump sum
Rework Covered Walkway: |  | lump sum
Demolish Carport: |  | lump sum
Downspout Extension: |  | lump sum
Subtotal: | 0
Post Construction Repairs/Punch List
Patch/Repair Plaster: |  | per square foot
Punch List/ Demobilization: |  | lump sum
Subtotal: | 0
Other Retrofit Costs
(units)
(units)
Subtotal: | 0
Retrofit Subtotal: | 0
Additional Project Costs
Markup: |  | typically a percent of total costs
Escalation: |  | typically a percent of total costs
Permitting: |  | typically a percent of total costs
Contractor Profit: |  | typically a percent of total costs
Subtotal: | 0
Retrofit Total: | 0
Notes:
Notes regarding items not covered in the cost estimate:
Back to Flowchart
Note on C29: feet
Note on C30: linear feet
Note on C31: square feet
Note on C33: feet
Note on C36: square feet
Note on C37: linear feet
Note on C38: square feet
Note on C39: linear feet
Note on C40: square feet
Note on C41: linear feet
Note on C47: square feet
Note on C48: square feet
Note on C49: feet
Note on C52: square feet

## BCA Input Resources
Benefit Cost Analysis Input Resources |  | Date:
2012-09-20
Resources
http://www.fema.gov/government/grant/bca.shtm | Benefit-Cost Analysis
http://www.bchelpline.com/BCAToolkit/resources_flood.html | Flood Module Resources
http://www.bchelpline.com/BCAToolkit/resources_dfa.html | Damage Frequency Assessment Module Resources
http://www.bchelpline.com/index.html | BCA Helpline Web Site
http://www.bchelpline.com/BCAToolkit/index.html | BCA Resource Kit
http://www.bchelpline.com/BCAToolkit/resource_files/BCA_Reference_Guide.pdf | BCA Reference Guide (June 2009)
http://www.bchelpline.com/BCAToolkit/resource_files/BCA_Reference_Guide_Supplement.pdf | BCA Reference Guide Supplement (June 2011)
http://www.fema.gov/media-library/assets/documents/33634?id=7851 | Hazard Mitigation Assistance (HMA) Unified Guidance
Benefit Cost Analysis ASCE 24 Guidance
Flood Zone: | AE
Mitigation Measure: | Mitigation Reconstruction
Recommendation for Elevation: | Use ASCE 24 Table 2-1
Back to Flowchart

## EHP Checklist
Environmental Planning and Historic Preservation (EHP) Program Checklist |  |  |  | Date:
2012-09-20
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Mitigation Retrofit Project Type:
| Checklist (Y/N) | Notes:
Has the EHP Screening Form been completed? |  |  | http://www.fema.gov/library/viewRecord.do?fromSearch=fromsearch&id=4802
Have details been provided in the Scope of Work to identify all possible structure modifications and upgrades, the full limit(s) of ground disturbance, and all construction staging areas?
For new construction, does the Scope of Work include critical information such as site acreage, new building square footage, number of stories, utilities, access roads, parking, sidewalks, stormwater facilities, etc.?
Have the footprint, limits of ground disturbance, and areas of previously disturbed and undisturbed ground been noted on a sketch site map (including construction staging areas)?
Have alternatives to the proposed action been considered and described in the project subapplication?
Have photographs of the proposed project area been included in the subapplication (include the project site and surrounding area)?
Has a location map of the project been included in the subapplication (include latitude/longitude)?
Will existing utilities be used in the project (if not include information in the Scope of Work regarding the installation of new utilities - including trenching)?
Will existing access roads be used in the project (if not include information on the Scope of Work regarding the location and nature of the new access roads)?
Will any equipment be installed?
A description of vegetation, including amount (area), type, and extent to be removed or affected.
Cultural resources information that is useful for the EHP review:
Color photographs of all buildings and structures on the site, including any building, structure, object, or man-made site or landscape feature that is 50 years or more in age. At least one photograph provided of a building should be the front or primary façade showing the entire elevation.
Color photographs of the area surrounding the project site such that the general character and nature is discernible (e.g., row of houses facing the project site, current vegetative cover, etc.).
Documentation of the year(s) of construction for the original facility and any additions or modifications to the existing building/structure/facility (building permits, tax assessments, historic maps, documentary photographs, architectural drawings, owner recollection, etc.) if readily available.
Copies of any available plans, site plans, etc., for the existing building/structure/facility, as well as documentation of any changes made since the original construction.
Plans showing the limits of proposed excavations or other ground disturbing activities (compression, grading, excavation, drilling, etc.) associated with the project.
Location maps, including topographic, NRCS Soils, and road maps showing the subject property and a quarter-mile radius around it.
Any known historic properties within a quarter-mile radius of the project site, including those listed in the National Register of Historic Places, designated National Historic Landmarks, listed in the State register, or recognized locally as historic.
Exerpts from known cultural resources surveys/studies describing the architectural/archaeological/historical significance of the properties that exist within a quarter-mile radius of the project site.
Documentation of the use of past uses of the property, including known ground-disturbing activities (e.g., mining, grading, etc.).
Endangered and threatened species information that is useful for the EHP review:
Documents (e.g., Biological Assessment, initial study, Database Report, environmental impact assessment) evaluating potential effects of the project activities on biological resources. As well as any impacts to adjacent or downstream wetlands/WOUS need to be addressed also
State species lists identifying endangered, threatened, or otherwise protected species potentially affected by the proposed project.
Documentation of coordination with other agencies (e.g., USFWS, State Fish and Game Agencies, State Natural Heritage Program), including studies, reports and recommendations.
Wetland information that is useful for the EHP review:
| Checklist | Notes:
Detailed maps (e.g., United States Army Corps of Engineers, United States Fish and Wildlife Service National Wetlands Inventory Maps) defining wetland boundaries in the project area.
Studies and reports (e.g., wetland survey maps and reports, flood elevations and velocities) documenting the project scope as it relates to the occupancy and modification of wetlands, including direct and indirect effects.
Documentation of compliance and consistency with Federal, State, Tribal, county and local floodplain management programs and plans.
Documentation of any public notices or public meetings.
Documentation of coordination with other agencies (e.g., United States Army Corps of Engineers, Natural Resources Conservation Service, National Flood Insurance Program, State and local floodplain managers) including studies, reports, and recommendations.
Water quality information that is useful in the EHP Review:
Identification of all surface waters in the project area regardless of drainage area, size, or perceived hazard level. Information about surface waters should include dimensions, proximity of the project activity to the water, and the expected and possible impacts of the project on surface waters, if any.
Detailed descriptions and related studies and reports of proposed disturbances or discharges into bodies of water or wetlands. Disturbances include clearing, grading, dredging, cutting, or filling. Discharges include storm water, wastewater, or pollutants.
Documents (e.g., Initial Study, Environmental Impact Statement) evaluating potential effects of the project activities on water resources.
Documentation of best management practices to be used for erosion and sediment control.
Documentation of coordination with other agencies (e.g. United States Army Corps of Engineers, Environmental Protection Agency, State Department of Natural Resources, or Department of Environmental Protection), including studies and reports and recommendations.
Air quality information that is useful for the EHP review:
Does the subapplicant engage in pre-disaster planning?
Has the subapplicant obtained the required permits?
Has the subapplicatn evaluated the effects of actions on air quality?
Has the subapplicant followed State and local laws and policies regarding?:
debris burning
equipment exhaust
construction dust
Coastal Zone Management information that is useful for the EHP review:
Detailed maps, studies, and reports documenting the project scope and surrounding areas in relation to coastal zones (e.g., beaches, islands, transitional and intertidal zones, salt marshes, estuaries). Such documentation should include any land extending inward to the extent necessary to control shorelines.
Documentation of compliance and consistency with State coastal management programs and plans.
Documentation of coordination with State and Federal agencies (e.g., National Oceanic and Atmospheric Administation, Office of Ocean and Coastal Resource Management, United States Fish and Wildlife Service, State Coastal Zone Management Agency), including studies, reports, and recommendations
Fish and Wildlife Coordination Act information that is useful for the EHP review:
Detailed plans and studies for the control or modification of a natural stream or body of water.
Detailed maps, studies, and reports documenting the project scope and surrounding areas, including construction of dams, berms, impoundments, stream relocation, and water-diversion structures.
Detailed descriptions and related studies and reports of proposed discharges of pollutants, including industrial, mining, municipal wastes, or dredging and fill material into a body of water or wetlands.
Recommendations of the United States Fish and Wildlife Service and affected State agency(ies) for protecting game and non-game fish and wildlife and their habitat.
Documentation of coordination with other agencies (e.g., USFWS, NMFS, State fish and game departments), including studies, reports, and recommendations.
Resource Conservation and Recovery Act information that is useful for the EHP reviews includes:
Develop a debris management plan during normal operations and activate the plan following a disaster.
Identify and permit debris staging and disposal sites, also during normal operations.
Use appropriate volume-reduction methods to minimize the solid waste that must be disposed of.
Has the site been checked for the presence of hazardous materials and hazardous waste?
Has the site been checked for the presence of lead paint or materials containing asbestos?
If there are hazardous materials, hazardous waste, materials coated with lead paint, or materials containing asbestos have they been properly disposed of or is there a plan in place to properly dispose of the materials?
Environmental justice-related information that is useful in the EHP review:
Documentation from other agencies (e.g., U.S. Census Bureau, State, Regional, County, and local planning and development agencies), including studies, reports, and recommendations.
Studies and reports (e.g., traffic, noise, dust, odor, and hazardous and toxic materials) documenting the project scope and surrounding areas in relation to low-income and minority populations, including direct and indirect effects.
Census data and income information of affected populations (e.g., location of public housing, minority and low-income neighborhoods).
Review the following resources for additional guidance.
http://www.fema.gov/media-library/assets/documents/33634?id=7851 | Hazard Mitigation Assistance (HMA) Unified Guidance
http://www.fema.gov/environmental-planning-and-historic-preservation-program/environmental-historic-preservation-1 | EHP Guidance for FEMA Grant Applicants
Back to Flowchart

## Application Development Res
E-Grants Application Development Resources |  | Date:
2012-09-20
Resources
http://www.fema.gov/mitigation-egrants-system-0 | FEMA Mitigation eGrants System Web Site
http://www.fema.gov/library/viewRecord.do?id=2815 | Mitigation eGrants Blank Project Pre-application
http://www.fema.gov/library/viewRecord.do?id=4801 | Mitigation eGrants Project Sub-application Form
http://www.fema.gov/library/viewRecord.do?id=4800 | Mitigation eGrants Management Costs Sub-application Form
http://www.fema.gov/media-library/assets/documents/33634?id=7851 | Hazard Mitigation Assistance (HMA) Unified Guidance
Back to Flowchart

## Mitigation Reconst Design Const
| Mitigation Reconstruction |  |  | Date:
2012-09-20
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Building Code Used for Construction:
ASCE 24 Design Verification Section
| The use of this checklist does not ensure code compliance for the structure or the structure foundation and is only intended to provide the user with a list of items necessary for compliance with ASCE 24. | Applicable Sections* (Applicable sections may vary depending on the flood zone and other conditions) | Design Verification | Construction Verification
1.) | Is the structure classified as a flood prone structure as defined in ASCE 24? | Section 1.4.1
2.) | If the building is relocated on the site, does the building meet all the applicable siting requirements of ASCE 24? | Sections 2.2, 4.1.1, and 4.3
3.) | Does the structure meet the requirements of ASCE 24 for interaction with flood protective works? | Section 1.4.2
4.) | Does the structure meet the requirements of ASCE 24 for interaction with erosion control structures? | Sections 1.5.2 and 4.7
5.) | Do the soil conditions the structure is constructed on meet the requirements of ASCE 24? | Sections 1.5.3.1 and 4.5.2
6.) | Is the structure classification consistent with ASCE 24? | Section 1.4.3
7.) | Were the load combinations used to design the structure consistent with the requirements of ASCE 24 and ASCE 7? | Sections 1.6 and 4.2
8.) | Does the structure and ancillary structures meet the elevation requirements of ASCE 24? | Sections 1.5.2, 2.3, and 4.4
9.) | If included in the structure design do the foundation walls meet the requirements of ASCE 24? | Sections 2.5.2, 2.6, and 4.5
10.) | If included in the structure design do the piers, posts, columns, and piles meet the requirements of ASCE 24? | Sections 4.5.5, 4.5.6, and 4.5.7
11.) | If included in the structure design do the pile caps meet the requirements of ASCE 24? | Sections 4.5.6.6, 4.5.6.7, and 4.5.6.8
12.) | If piers, posts, columns, or piles are included in the structure design do the spacing on the piers, posts, columns, or piles meet the requirements of ASCE 24? | Section 4.5.6.9
13.) | If piles are included in the structure does the design address the use of mixed founcation elements that meet the requirements of ASCE 24? | Section 4.5.6.10
14.) | If included in the structure design do the grade beams meet the requirements of ASCE 24? | Section 4.5.9
15.) | If included in the structure design do the foundation attachements and bracing meet the requirements of ASCE 24? | Section 4.5.10
16.) | If included in the structure design do the slabs-on-grade meet the requirements of ASCE 24? | Sections 2.5 and 4.5.8
17.) | If included in the structure design does the fill meet the requirements of ASCE 24? | Sections 2.4 and 4.5.4
18.) | If included in the structure design do the shear walls meet the requirements of ASCE 24? | Section 4.5.11
19.) | If included in the structure design do the anchorage and connection points meet the requirements of ASCE 24? | Sections 1.5.3.3, 1.5.3.4, 1.5.5, 4.5.1, 4.5.6.6, 4.5.6.7, and 4.5.6.8
20.) | If included in the structure design do the enclosures (including breakaway walls) meet the requirements of ASCE 24? | Sections 2.6 and 4.6
21.) | If included in the structure design do the openings (engineered and nonengineered) meet the requirements of ASCE 24? | Sections 2.6.1 and 2.6.2
22.) | If included in the structure design do the decks, concrete pads, or patios meet the requirements of ASCE 24? | Sections 4.8 and 9.2
23.) | Do the materials (including: metal components, concrete elements, masonry elements, wood & timber elements, and finishes) meet the requirements of ASCE 24? | Section 5
24.) | Do the materials meet the requirements for corrosive environments defined in ASCE 24? | Section 5.2.2.1
25.) | Do the materials meet the requirements for noncorrosive environments defined in ASCE 24? | Section 5.2.2.2
26.) | Do the utilities (electrical, plumbing, sanitary systems, mechanical, heating, ventilation, air conditioning, tanks, and elevators) meet the requirements of ASCE 24? | Section 7
27.) | Does the building access for the structure meet the requirements of ASCE 24? | Section 8
28.) | If included in the structure design does the garage (attached and detached) or carport meet the requirements of ASCE 24? | Section 9.3
29.) | If included in the structure does the chimney(s) or fireplace(s) meet the requirements of ASCE 24? | Section 9.4
30.) | If included in the structure design does the pool meet the requirements of ASCE 24? | Section 9.5
31.) | If any portion of the structure meets the requirements of miscellaneous items (as governed by Section 9) does it meet the requirements of ASCE 24? | Section 9.1
* The section numbers provided in this section provide general references to the provisions, but other unnamed sections may apply or not all sections listed may apply.
Notes:
Back to Flowchart
Mitigation Options

## Elevation Design Const
Elevation |  |  |  | Date:
2012-09-20
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Building Code Used for Construction:
Note: | Some portions of this checklist may not apply with elevation projects NOT requiring a completely new foundation.
ASCE 24 Design Verification Section
| The use of this checklist does not ensure code compliance for the structure or the structure foundation and is only intended to provide the user with a list of items necessary for compliance with ASCE 24. | Applicable Sections* (Applicable sections may vary depending on the flood zone and other conditions) | Design Verification | Construction Verification
1.) | Is the structure classified as a flood prone structure as defined in ASCE 24? | Section 1.4.1
2.) | Does the structure meet the requirements of ASCE 24 for interaction with flood protective works? | Section 1.4.2
3.) | Does the foundation for the elevation project meet the requirements of ASCE 24 for interaction with erosion control structures? | Sections 1.5.2 and 4.7
4.) | Do the observed soil conditions the structure is constructed on meet the requirements of ASCE 24? | Sections 1.5.3.1 and 4.5.2
5.) | Is the structure classification consistent with ASCE 24? | Section 1.4.3
6.) | Were the load combinations used to design the foundation consistent with the requirements of ASCE 24 and ASCE 7? | Sections 1.6 and 4.2
7.) | Does the structure and ancillary structures (associated with the elevation project) meet the elevation requirements of ASCE 24? | Sections 1.5.2, 2.3, and 4.4
8.) | If included in the foundation design for the elevation project, do the foundation walls meet the requirements of ASCE 24? | Sections 2.5.2, 2.6, and 4.5
9.) | If included in the foundation design for the elevation project, do the piers, posts, columns, and piles meet the requirements of ASCE 24? | Sections 4.5.5, 4.5.6, and 4.5.7
10.) | If piers, posts, columns, or piles are included in the foundation design for the elevation project, do the spacing on the piers, posts, columns, or piles meet the requirements of ASCE 24? | Section 4.5.6.9
11.) | If piles are included in the foundation design for the elevation project, do the pile caps meet the requirements of ASCE 24? | Sections 4.5.6.6, 4.5.6.7, and 4.5.6.8
12.) | If piles are included in the foundation does the design address the use of mixed founcation elements that meet the requirements of ASCE 24? | Section 4.5.6.10
13.) | If included in the foundation design for the elevation project, do the grade beams meet the requirements of ASCE 24? | Section 4.5.9
14.) | If included in the foundation design for the elevation project, do the foundation attachements and bracing meet the requirements of ASCE 24? | Section 4.5.10
15.) | If included in the foundation design for the elevation project, do the slabs-on-grade meet the requirements of ASCE 24? | Sections 2.5 and 4.5.8
16.) | If included in the foundation design for the elevation project, does the fill meet the requirements of ASCE 24? | Sections 2.4 and 4.5.4
17.) | If included in the foundation design for the elevation project, do the shear walls meet the requirements of ASCE 24? | Section 4.5.11
18.) | If included in the foundation design for the elevaiton project, do the anchorage and connection points meet the requirements of ASCE 24? | Sections 1.5.3.3, 1.5.3.4, 1.5.5, 4.5.1, 4.5.6.6, 4.5.6.7, and 4.5.6.8
19.) | If included in the foundation design for the elevation project, do the enclosures (including breakaway walls) meet the requirements of ASCE 24? | Sections 2.6 and 4.6
20.) | If included in the foundation design for the elevation proejct, do the openings (engineered and nonengineered) meet the requirements of ASCE 24? | Sections 2.6.1 and 2.6.2
21.) | If included in the foundation design for the elevation project or impacting the foundation, do the decks, concrete pads, or patios meet the requirements of ASCE 24? | Sections 4.8 and 9.2
22.) | Do the materials used in the foundation for the elevation project (including: metal components, concrete elements, masonry elements, wood & timber elements, and finishes) meet the requirements of ASCE 24? | Section 5
23.) | Do the materials used in the foundation for the elevation project meet the requirements for corrosive environments defined in ASCE 24? | Section 5.2.2.1
24.) | Do the materials used in the foundation for the elevation meet the requirements for noncorrosive environments defined in ASCE 24? | Section 5.2.2.2
25.) | Do the utilities (electrical, plumbing, sanitary systems, mechanical, heating, ventilation, air conditioning, tanks, and elevators) impacted by the elevation project meet the requirements of ASCE 24? | Section 7
26.) | Does the building access impacted by the elevation project meet the requirements of ASCE 24? | Section 8
27.) | If a garage (attached and detached) or carport cause impacts to the foundation for the elevation project, does the garage or carport meet the requirements of ASCE 24? | Section 9.3
28.) | If a chimney(s) or fireplace(s) are impacted by the foundation for the elevation project does the chimney or fireplace meet the requirements of ASCE 24? | Section 9.4
29.) | If a pool causes impacts to the foundation for the elevation project, does the pool meet the requirements of ASCE 24? | Section 9.5
30.) | If any portion of the structure meets the requirements of miscellaneous items (as governed by Section 9) and impacts the foundation for the elevation project, does it meet the requirements of ASCE 24? | Section 9.1
* The section numbers provided in this section provide general references to the provisions, but other unnamed sections may apply or not all sections listed may apply.
Notes:
Back to Flowchart
Mitigation Options

## Dry Floodproofing Design Const
Dry Floodproofing |  |  |  | Date:
2012-09-20
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Building Code Used for Construction:
ASCE 24 Design Verification Section
| The use of this checklist does not ensure code compliance for the structure or the structure foundation and is only intended to provide the user with a list of items necessary for compliance with ASCE 24. | Applicable Sections* (Applicable sections may vary depending on the flood zone and other conditions) | Design Verification | Construction Verification
1.) | Is the structure classified as a flood prone structure as defined in ASCE 24? | Section 1.4.1
2.) | Does the structure meet the requirements of ASCE 24 for interaction with flood protective works? | Section 1.4.2
3.) | Does the proposed dry floodproofed area meet the requirements of ASCE 24 for interaction with erosion control structures? | Sections 4.7 and 6.2.2
4.) | Do the observed soil conditions the structure is constructed on meet the requirements of ASCE 24? | Sections 1.5.3.1 and 1.5.4
5.) | Does the dry floodproofing design address all the sour and erosion protection requirements of ASCE 24? | Sections 1.5.3.2 and 1.5.3.3
6.) | Is the structure classification consistent with ASCE 24? | Section 1.4.3
7.) | Does the dry floodproofed area (walls, floors, and flood shields) meet all the load and load combination requirements of ASCE 24 and ASCE 7? | Section 1.6
8.) | Does the dry floodproofed area meet the elevation requirements of ASCE 24? | Section 1.5.2
9.) | If included in the dry floodproofing design do the foundation walls meet the requirements of ASCE 24? | Section 4.5
10.) | If included in the dry floodproofing design do the piers, posts, columns, and piles meet the requirements of ASCE 24? | Sections 4.5.5, 4.5.6, and 4.5.7
11.) | If included in the dry floodproofing design do the pile caps meet the requirements of ASCE 24? | Sections 4.5.6.5 and 4.5.6.8
12.) | If piles, posts, columns, or piles are included in the dry floodproofing design do the spacing on the piers, posts, columns, or piles meet the requirements of ASCE 24? | Section 4.5.6.9
13.) | If piles are included in the dry floodproofed area does the design address the use of mixed founcation elements that meet the requirements of ASCE 24? | Section 4.5.6.10
14.) | If included in the dry floodproof design do the grade beams meet the requirements of ASCE 24? | Section 4.5.9
15.) | If included in the dry floodproof design do the foundation attachements and bracing meet the requirements of ASCE 24? | Section 4.5.10
16.) | If included in the dry floodproofing design do the slabs-on-grade meet the requirements of ASCE 24? | Section 4.5.8
17.) | If included in the dry floodproofing design does the fill meet the requirements of ASCE 24? | Section 4.5.4
18.) | If included in the dry floodproofing design do the shear walls meet the requirements of ASCE 24? | Section 4.5.11
19.) | If included in the dry floodproofing design do the anchorage and connection points meet the requirements of ASCE 24? | Sections 4.5.6.6, 4.5.6.7, and 4.5.6.8
20.) | If included in the dry floodproofing design do the enclosures (including breakaway walls) meet the requirements of ASCE 24? | Sections 2.1 and 4.6
21.) | If included in the dry floodproofing design do the openings (engineered and nonengineered) meet the requirements of ASCE 24? | Sections 2.6.1 and 2.6.2
22.) | If included in the design for the dry floodproofing project or impacting the dry floodproofed area, do the decks, concrete pads, or patios meet the requirements of ASCE 24? | Sections 4.8 and 9.2
23.) | Do the materials used in the dry floodproofed area (including: metal components, concrete elements, masonry elements, wood & timber elements, and finishes) meet the requirements of ASCE 24? | Section 5
24.) | Do the materials used in the dry floodproofed area meet the requirements for corrosive environments defined in ASCE 24? | Section 5.2.2.1
25.) | Do the materials used in the dry floodproofing meet the requirements for noncorrosive environments defined in ASCE 24? | Section 5.2.2.2
26.) | Does the design of the dry floodproofed area address all of the requirements of ASCE 24 regarding the nature and characteristics of the flooding hazard, flood warning times, access, structure occupancy, and functional dependence? | Section 6.1
27.) | Do the dry floodproofed areas and associated utilities meet the substantial impermeability requirements of ASCE 24? | Section 6.2
28.) | Does the design of the dry floodproofed area incorporate the use of sump pumps to remove accumulated water and does the system comply with the requirements of ASCE 24? | Section 6.2
29.) | If flood shields are used do they meet the loading requirements of ASCE 24? | Section 6.2.2
30.) | Does the design of the dry floodproofed area and implementation of the dry floodproofing measures address the flood warning time and planning requirements as stated in ASCE 24? | Section 6.2.3
31.) | If human intervention is required for the implementing the dry floodproofing measures are the human intervention requirements of ASCE 24 met? | Section 6.2.3
32.) | If flood shields are used have all the submital requirements in ASCE 24 been met? | Section 6.2.3
33.) | If flood shields are used do they meet the loading requirements of ASCE 24? | Section 6.2.2
34.) | Do the utilities (electrical, plumbing, sanitary systems, mechanical, heating, ventilation, air conditioning, tanks, and elevators) impacted by the dry floodproofing project meet the requirements of ASCE 24? | Section 7
35.) | Does the building access and egress impacted by the dry floodproofing project meet the requirements of ASCE 24 (including meeting the egress requirements from the dry floodproofed area)? | Sections 6.2.2, 6.2.3, and 8.0
36.) | If a garage (attached and detached) or carport cause impacts to the dry floodproofed area, does the garage or carport meet the requirements of ASCE 24? | Section 9.3
37.) | If a chimney(s) or fireplace(s) are impacted by or cause impacts to the dry floodproofed area does the chimney or fireplace meet the requirements of ASCE 24? | Section 9.4
38.) | If a pool causes impacts to the dry floodproofed area, does the pool meet the requirements of ASCE 24? | Section 9.5
39.) | If any portion of the structure meets the requirements of miscellaneous items (as governed by Section 9) and impacts the dry floodproofed area, does it meet the requirements of ASCE 24? | Section 9.1
* The section numbers provided in this section provide general references to the provisions, but other unnamed sections may apply or not all sections listed may apply.
Notes:
Back to Flowchart
Mitigation Options

## Pre Const Checklist
Pre/Post-Construction Property Evaluation Checklist |  |  |  |  | Date:
Example |  |  |  |  | 2012-09-20
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Mitigation Retrofit Project Type:
EXTERIOR
Sidewalks - note condition
DOORS
Storm Door 1 |  | working properly | not working properly
Storm Door 2 |  | working properly | not working properly
Screen Door 1 |  | working properly | not working properly
Screen Door 2 |  | working properly | not working properly
Front Door 1 |  | working properly | not working properly
Front Door 2 |  | working properly | not working properly
Side Door 1 |  | working properly | not working properly
Side Door 2 |  | working properly | not working properly
Side Door 3 |  | working properly | not working properly
Side Door 4 |  | working properly | not working properly
Rear Door 1 |  | working properly | not working properly
Rear Door 2 |  | working properly | not working properly
WINDOWS & SCREENS - note any glass cracks, missing glass, missing screens, holes, etc.
Front
Side 1
Rear
Side 2
EXTERIOR WALLS - note any cracks, holes, etc.
Front
Side 1
Rear
Side 2
Light Fixtures
Roof - note condition
Satellite Dish - note condition
TV Antenna (VHF/UHF)
Septic Tank - note condition
Attached Garage
Door 1
Door 2
Garage Interior - notes
Notes:
*The Owner should remove all landscaping around house. The Contractor and the City of _______ assume NO liability for landscaping that has not been removed by owner.
INTERIOR
PORCH 1
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 0 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Screens
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
PORCH 2
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 0 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Screens
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
UTILITY ROOM/MISC.
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Washing Machine |  | working properly | not working properly | request removal
Dryer |  | working properly | not working properly | request removal
Hot Water Heater |  | working properly | not working properly | request removal
Freezer |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
LIVING ROOM 1
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
LIVING ROOM 2
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
DINING ROOM
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
KITCHEN
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Countertops
Cabinets
Cabinet Doors |  | working properly | not working properly
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Sink |  | working properly | not working properly
Refrigerator |  | working properly | not working properly
Icemaker |  | working properly | not working properly
Freezer |  | working properly | not working properly | request removal
Stove |  | working properly | not working properly
Stove Hood (Light/exhaust fan) |  | working properly | not working properly
Dishwasher |  | working properly | not working properly
Garbage Disposal |  | working properly | not working properly
Microwave - built in |  | working properly | not working properly
Microwave - counter top |  | working properly | not working properly | request removal
Notes:
BEDROOM 1
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
BEDROOM 2
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
BEDROOM 3
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes: ________________________________________________________________________________________________
BEDROOM 4
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
HALL
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 0 1 2 3 4 5 6 7 8 9 10 11 12
Light Fixture(s) |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
BATH 1
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Toilet |  | working properly | not working properly
Sink |  | working properly | not working properly
Shower/Tub |  | working properly | not working properly
Notes:
BATH 2
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Toilet |  | working properly | not working properly
Sink |  | working properly | not working properly
Shower/Tub |  | working properly | not working properly
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
ROOM: _____________________________________
Door 1 |  | working properly | not working properly
Door 2 |  | working properly | not working properly
Closet Door(s) |  | working properly | not working properly
Walls
Floor
Ceiling
Trim/Molding
Receptacles | (circle total) 1 2 3 4 5 6 7 8 9 10 11 12
Ceiling Fan |  | working properly | not working properly
Light Fixture(s) |  | working properly | not working properly | request removal
Window A/C Unit |  | working properly | not working properly | request removal
Window 1 |  | working properly | not working properly
Window 2 |  | working properly | not working properly
Window 3 |  | working properly | not working properly
Window 4 |  | working properly | not working properly
Window 5 |  | working properly | not working properly
Heat Unit |  | working properly | not working properly | request removal
Notes:
Additional Notes:
*All window A/C units should be removed from windows.
*All items hanging on all walls must be taken down and secured.
*All valuables, including TVs, computers, and electronics, must be removed from the house.
*All glass and breakable items must be removed or secured.
*Items on tables, shelves, etc. must be secured.
*The Contractor and the City of ______assume NO liability for all items not removed by owner.
We, the parties, certify that the above information is correct to the best of our knowledge and that the videographic evidence may be used to supplement the report above. The owner is hereby reminded of the release for the City of ________ which states that minor cracking and separation is to be expected as a result of retrofitting work. These cracks may occur in walls, floors, or ceilings. Retrofitting work may also extend existing cracks in walls, floors, ceilings, and windows.
Prior to Retrofitting:
|  | Contractor |  | Date
|  | Owner’s Representative |  | Date
|  | Program Administrator |  | Date
|  | Owner |  | Date
|  | Owner |  | Date
___________________________________________________________________________________________________
Following Completion of Retrofitting:
|  | Owner |  | Date
|  | Owner |  | Date
|  | Program Administrator |  | Date
Back to Flowchart
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a
n/a

## Project Closeout
Project Closeout List |  | Date:
2012-09-20
Provided only as an example - other information may be required
Case File #/PIN:
Street Address:
City:
State:
County:
Zip Code:
Owner:
Grant Program:
Mitigation Retrofit Project Type:
Building Code Used for Construction:
Resources
http://www.fema.gov/media-library/assets/documents/33634?id=7851 | Hazard Mitigation Assistance (HMA) Unified Guidance
http://www.fema.gov/government/grant/pa/faq.shtm | FEMA Grants Frequently Asked Questions
| Checklist (Y/N) | Notes
Is the subgrant completed in compliance with the approved Scope of Work? (The Grantee [State/Tribe] must conduct a site visit or collect photographs for a project subgrant to ensure the approved Scope of Work was completed.)
Was the subgrant completed in compliance with all environmental mitigation conditions attached to it?
Have actual expenditures have been documented and are they consistent with the SF-424A or SF-424C?
Has all program income been deducted from total project costs as specified in 44 CFR Section 13.25(g)(1)?
Whenever cost underruns are identified, the Grantee should submit de-obligation requests to FEMA.
Was all project work performed in accordance with all required permits and applicable building codes as modified or protected by the approved project?
Attach Project Schedule and include the following:
-Reason(s) for delay;
-Current status of the activity/activities;
-Approved POP termination date and new projected completion date;
-Remaining available funds, both Federal and non-Federal;
-Budget outlining how remaining Federal and non-Federal funds will be expended;
-Include milestones and timeframe for achieving each milestone and the position/person responsible for the task; and
-Certification that the activity/activities were completed within the extended Period of Performance without any modification to the original Scope of Work approved by FEMA. (if applicable)
For projects involving an insurable facility, has the required hazard insurance (e.g., NFIP) has been secured?
Geospatial coordinates, in the form of latitude and longitude with an accuracy of +/- 20 meters (64 feet), have been provided for the project. For minor localized flood reduction, hazardous fuels reduction, and soil stabilization projects, an accurate recording of the official acreage, using open file formats geospatial files (i.e., shapefiles), has been submitted (For geocoding resources, see the Hazard Mitigation Assistance Unified Guidance Part X C.3).
Were photographs taken of all four sides of the building (Attach photographs of all four sides of the building)
Submit a copy of the Certificate of Occupancy for the retrofitted building or Mitigation Reconstruction
Submit a copy of the Elevation Certificate for the retrofitted building or Mitigation Reconstruction
Submit documentation of inspections such as demolition; foundation; plumbing, mechanical, gas and electrical systems; floodplain; frame and masonry; sheathing; fire-resistance rating; and final inspections.
Submit documentation that all appropriate environmental (see EHP documentation), land use/zoning, and building permits have been obtained.
Submit a copy of the Recorded Deed Amendment for maintaining flood insurance if required for project type (e.g., Mitigation Reconstruction, Structure Elevation)
Submit a certification by an engineer, design professional, or floodplain manager stating that the elevation of the building is in compliance with the NFIP and the technical bulletins.
Verify the following with State Officials:
The Grantee (State/Tribe) ensures all subgrants have been closed out as identified in Part VI D.1;
The Grantee (State/Tribe) reconciles/adjusts subgrant costs, ensures that non-Federal share costs are documented, and that all costs submitted are eligible according to the FEMA-approved Scope of Work;
The Grantee (State/Tribe) receives and processes cost adjustments or returns unobligated funds to FEMA via SMARTLINK or PARS. Final payment is made to the Grantee (State/Tribe);
Cost Share Documentation (including):
-Record of Donor
-Dates of Donation
-Rates for staffing, equipment or usage, supplies, etc.
-Amounts of donation or value of donation
-Deposit slips for cash donations
The Grantee (State/Tribe) submits a closeout letter to FEMA with supporting documentation, including:
-Statement that SOW has been completed as approved and all EHP requirements have been satisfied (include documentation of Scope of Work Modifications);
-SF-425 (for PARS, the final SF-425 is also submitted via PARS);
-SF-270, Request for Advance or Reimbursement, if applicable, or request for deobligation of unused funds, if applicable;
-FEMA Form 20-18, Report on Government Property, if applicable; and
The Grantee notifies FEMA that the grant is ready for final closeout.
Hazard Mitigation Grant Program (HMGP)
Items to be Retained by applicant
All records and documentation associated with this project should be retained for five (5) years.
This information should include, but is not limited to the following:
- Copies of the request for reimbursement forms (HMGP-4) and the fiscal activity summary sheet.
- Original application and any change in scope of work approvals.
- Description of completed project or Engineer’s certificate of completion.
- Budget breakdown of expended funds, including local matches.
- Invoices, receipts, vouchers, or other verification of expenses.
- Duplication of Benefits worksheets and information (for acquisition projects).
- Copies of restricted deeds (for acquisition projects).
- Copies of single audit or other required audits.
- All correspondence from project approval to completion.
- Copies of land or rights of way agreements.
- Copies of contracts awarded for project work.
- Any additional items identified as necessary for audit purposes.
Back to Flowchart

## Lists (hidden)
| Question1 |  | FloodZone | CoastFldZone | ResNR | StructureType |  | GrantProg |  | BCAModule | FloodMitProj | ElevCert | NRTypeStr | DDFType | DamageOpt | NRDDF | LosFac | LosService | RDDF
| Yes |  | n/a | n/a | n/a | Building |  | FMA |  | Flood | Acquisition | n/a | n/a | n/a | n/a | USACE - Wilmington: Department Store, structure | Fire Station | Other | USACE Generic
| No |  | X (shaded) or B | A Zone | Residential | Other |  | HMGP |  | Hurricane Wind | Elevation | Diagram 1A | Engineered | Default | Default | USACE - Wilmington: Supermarket, structure | Hospital | Operating Income | USACE Generic Residential DDF, 1-Story, No Basement
| n/a |  | X (unshaded) or C | Coastal A Zone | Nonresidential | Utility |  | PA |  | Damage-Frequency Assesssment | Dry Flood Proofing/Flood Barrier | Diagram 1B | Pre-Engineered | Library | User-entered | USACE - New Orleans: Department Store, structure, salt water, long duration | Police Station | Education | USACE Generic Residential DDF, 1-Story, With Basement
|  |  | A | V Zone |  |  |  | PDM |  | Tornado Safe Room | Drainage Improvement | Diagram 2 |  | Custom |  | USACE - New Orleans: Department Store, structure, salt water, short duration | Other | Library | USACE Generic Residential DDF, 2-Story, No Basement
|  |  | AE |  |  |  |  | RFC |  | Earthquake | Other | Diagram 3 |  |  |  | USACE - New Orleans: Department Store, structure, fresh water, long duration |  | Government | USACE Generic Residential DDF, 2-Story, With Basement
| MitType |  | A1-30 |  |  |  |  | SRL |  | Wildfire |  | Diagram 4 |  |  |  | USACE - New Orleans: Department Store, structure, fresh water, short duration |  |  | USACE Generic Residential DDF, Split Level, No Basement
|  |  | AH | [8 empty] | Diagram 5 |  |  |  | USACE - New Orleans: Department Store, structure, composite water & duration |  |  | USACE Generic Residential DDF, Split Level, With Basement
| Mitigation Reconstruction |  | AO |  | Design | [6 empty] | Diagram 6 |  |  |  | USACE - New Orleans: Large Grocery, structure, salt water, long duration |  |  | FEMA FIA DDF, 1-Story, No Basement
| Elevation (New Foundation) |  | AR | [8 empty] | Diagram 7 |  |  |  | USACE - New Orleans: Large Grocery, structure, salt water, short duration |  |  | FEMA FIA DDF, 1-Story, With Basement
| Elevation (Existing Foundation) |  | A99 |  | SD/LRFD | [6 empty] | Diagram 8 |  |  |  | USACE - New Orleans: Large Grocery, structure, fresh water, long duration |  |  | FEMA FIA DDF, 2-Story, No Basement
| Utility Elevation |  | D |  | ASD | [6 empty] | Diagram 9 |  |  |  | USACE - New Orleans: Large Grocery, structure, fresh water, short duration |  |  | FEMA FIA DDF, 2-Story, With Basement
| Dry Floodproofing |  | V | [8 empty] | Other |  |  |  | USACE - New Orleans: Large Grocery, structure, composite water & duration |  |  | FEMA FIA DDF, Split Level, No Basement
| Acquisition |  | VE,V1-30 | [12 empty] | USACE - Galveston: Food Warehouse, structure |  |  | FEMA FIA DDF, Split Level, With Basement
| Other | [14 empty] | USACE - Galveston: Warehouse, structure |  |  | FEMA FIA DDF, Mobile Home
[16 empty] | USACE - New Orleans: Warehouse, structure, salt water, long duration |  |  | FEMA FIA DDF, Coastal V With Obstruction
[16 empty] | USACE - New Orleans: Warehouse, structure, salt water, short duration |  |  | FEMA FIA DDF, Coastal V Without Obstruction
[16 empty] | USACE - New Orleans: Warehouse, structure, fresh water, long duration |  |  | USACE - Chicago: one story, no basement, Structure
FloodSource |  | ResType | FoundType | BCAFndType | FoundMat | SuperMat | Veneer | LoadComb | StrCat | PrimaryUse | [5 empty] | USACE - New Orleans: Warehouse, structure, fresh water, short duration |  |  | USACE - Chicago: one story, w/ basement, Structure
[16 empty] | USACE - New Orleans: Warehouse, structure, composite water & duration |  |  | USACE - Chicago: split level, no basement, Structure
Riverine |  | n/a | Slab | None Of The Below | Wood | Wood | Brick | SD/LFRD | I | Retail-Furniture | [5 empty] | USACE - St. Paul: Warehouse, structure, fresh water |  |  | USACE - Chicago: split level, w/ basement, Structure
Coastal |  | one-story | Crawl Space | Slab | Steel | Masonry | Wood Siding | ASD | II | Retail-Electronics | [5 empty] | USACE - Wilmington: Warehouse, structure |  |  | USACE - Chicago: two story, no basement, Structure
|  | two or more stories | Pier | Pier | Concrete | Concrete | Stucco |  | III | Retail-Clothing | [5 empty] | USACE - Galveston: Airport, structure |  |  | USACE - Chicago: two story, w/ basement, Structure
|  | split level | Pile | Pile | Masonry | SIPs | Vinyl |  | IV | Hotel | [5 empty] | USACE - Galveston: Sewage Treatment, structure |  |  | USACE - Galveston: one & 1/2 story, no basement, Structure
|  | mobile home | Basement |  |  | Manufactured Home | Cement Board |  |  | Fast Food | [5 empty] | USACE - Galveston: Utility Company, structure |  |  | USACE - Galveston: one story, no basement, Structure
|  | other buildings | Other |  |  |  | EIFS |  |  | Non-Fast Food | [5 empty] | USACE - New Orleans: Utility Company, structure, salt water, long duration |  |  | USACE - Galveston: two story, no basement, Structure
FZ | [6 empty] | Curtain Wall |  |  | Hospital | [5 empty] | USACE - New Orleans: Utility Company, structure, salt water, short duration |  |  | USACE - New Orleans: one story, Pier foundation, structure, fresh water, short duration
[10 empty] | Medical Office | [5 empty] | USACE - New Orleans: Utility Company, structure, fresh water, long duration |  |  | USACE - New Orleans: one story, Pier foundation, structure, fresh water, long duration
n/a |  | FM | [7 empty] | Protective Services | [5 empty] | USACE - New Orleans: Utility Company, structure, fresh water, short duration |  |  | USACE - New Orleans: one story, Slab foundation, structure, fresh water, short duration
A | [9 empty] | Correctional Facility | [5 empty] | USACE - New Orleans: Utility Company, structure, composite water & duration |  |  | USACE - New Orleans: one story, Slab foundation, structure, fresh water, long duration
AE |  | Mitigation Reconstruction | [7 empty] | Recreation | [5 empty] | USACE - St. Paul: Professional, structure, fresh water |  |  | USACE - New Orleans: one story, Pier foundation, structure, salt water, short duration
A1-30 |  | Elevation | [7 empty] | Religious Facilities | [5 empty] | USACE - Wilmington: Office Building, structure |  |  | USACE - New Orleans: one story, Pier foundation, structure, salt water, long duration
AH |  | Dry Flood Proofing/Flood Barrier | [7 empty] | Schools | [5 empty] | USACE - Galveston: Hospital, Structure |  |  | USACE - New Orleans: one story, Slab foundation, structure, salt water, short duration
AO |  | Utility Elevation | [7 empty] | Service Station | [5 empty] | USACE - Galveston: Doctor's Office, Structure |  |  | USACE - New Orleans: one story, Slab foundation, structure, salt water, long duration
AR |  | Other | [7 empty] | Office One-Story | [5 empty] | USACE - New Orleans: Medical Office, structure, salt water, long duration |  |  | USACE - New Orleans: one story, Structure, fresh water, short duration
A99 | [9 empty] | Convenience Store | [5 empty] | USACE - New Orleans: Medical Office, structure, salt water, short duration |  |  | USACE - New Orleans: one story, Structure, fresh water, long duration
D | [9 empty] | Grocery | [5 empty] | USACE - New Orleans: Medical Office, structure, fresh water, long duration |  |  | USACE - New Orleans: one story, Structure, salt water, short duration
X (shaded) or B | [9 empty] | Apartment | [5 empty] | USACE - New Orleans: Medical Office, structure, fresh water, short duration |  |  | USACE - New Orleans: one story, Structure, salt water, long duration
X (unshaded) or C | [9 empty] | Industrial Light | [5 empty] | USACE - New Orleans: Medical Office, structure, composite water & duration |  |  | USACE - New Orleans: one story, Pier foundation, structure, fresh water, short duration
Coastal A Zone | [9 empty] | Warehouse, Refrigerated | [5 empty] | USACE - Galveston: City Hall, structure |  |  | USACE - New Orleans: one story, Slab foundation, structure, fresh water, short duration
V | [9 empty] | Warehouse, Non-Refrigerated | [5 empty] | USACE - Galveston: Post Office, structure |  |  | USACE - New Orleans: one story, Pier foundation, structure, salt water, long duration
VE,V1-30 | [9 empty] | Other | [5 empty] | USACE - New Orleans: Government facility, structure, salt water, long duration |  |  | USACE - New Orleans: one story, Slab foundation, structure, salt water, long duration
[16 empty] | USACE - New Orleans: Government facility, structure, salt water, short duration |  |  | USACE - New Orleans: two story, Pier foundation, structure, fresh water, short duration
[16 empty] | USACE - New Orleans: Government facility, structure, fresh water, long duration |  |  | USACE - New Orleans: two story, Pier foundation, structure, fresh water, long duration
[16 empty] | USACE - New Orleans: Government facility, structure, fresh water, short duration |  |  | USACE - New Orleans: two story, Slab foundation, structure, fresh water, short duration
|  | Mitigation Reconstruction | Elevation | Dry Flood Proofing/Flood Barrier | Utility Elevation | Other | [9 empty] | USACE - New Orleans: Government facility, structure, composite water & duration |  |  | USACE - New Orleans: two story, Slab foundation, structure, fresh water, long duration
[16 empty] | USACE - Wilmington: Post Office, structure |  |  | USACE - New Orleans: two story, Pier foundation, structure, salt water, short duration
n/a |  | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | [9 empty] | USACE - Galveston: Fire Station, structure |  |  | USACE - New Orleans: two story, Pier foundation, structure, salt water, long duration
A |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - Galveston: Police Station, structure |  |  | USACE - New Orleans: two story, Slab foundation, structure, salt water, short duration
AE |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - Galveston: Commercial School, structure |  |  | USACE - New Orleans: two story, Slab foundation, structure, salt water, long duration
A1-30 |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - Galveston: Library, structure |  |  | USACE - New Orleans: two story, Structure, fresh water, short duration
AH |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - Wilmington: School, Structure |  |  | USACE - New Orleans: two story, Structure, fresh water, long duration
AO |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: Elementary school, structure, salt water, long duration |  |  | USACE - New Orleans: two story, Structure, salt water, short duration
AR |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: Elementary school, structure, salt water, short duration |  |  | USACE - New Orleans: two story, Structure, salt water, long duration
A99 |  | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 2-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: Elementary school, structure, fresh water, long duration |  |  | USACE - New Orleans: two story, Pier foundation, structure, fresh water, short duration
D |  | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | [9 empty] | USACE - New Orleans: Elementary school, structure, fresh water, short duration |  |  | USACE - New Orleans: two story, Slab foundation, structure, fresh water, short duration
X (shaded) or B |  | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | [9 empty] | USACE - New Orleans: Elementary school, structure, composite water & duration |  |  | USACE - New Orleans: two story, Pier foundation, structure, salt water, long duration
X (unshaded) or C |  | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | Recommend at least 1 ft above flooding | [9 empty] | USACE - New Orleans: College, structure, salt water, long duration |  |  | USACE - New Orleans: two story, Slab foundation, structure, salt water, long duration
Coastal A Zone |  | Use ASCE 24 Table 4-1 | Use ASCE 24 Table 4-1 | Use ASCE 24 Table 6-1 | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: College, structure, salt water, short duration |  |  | USACE - St. Paul: one story, Structure
V |  | Use ASCE 24 Table 4-1 | Use ASCE 24 Table 4-1 | Dry Floodproofing not recommended | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: College, structure, fresh water, long duration |  |  | USACE - St. Paul: two story, Structure
VE,V1-30 |  | Use ASCE 24 Table 4-1 | Use ASCE 24 Table 4-1 | Dry Floodproofing not recommended | Use ASCE 24 Table 7-1 | Consult ASCE 24 | [9 empty] | USACE - New Orleans: College, structure, fresh water, short duration |  |  | USACE - Wilmington: one & 1/2 story, Pile foundation, structure
[16 empty] | USACE - New Orleans: College, structure, composite water & duration |  |  | USACE - Wilmington: one & 1/2 story, Structure
USACE - Wilmington: one & 1/2 story w/ 1/2 living area below, Structure
Datum | [18 empty] | USACE - Wilmington: one story, Pile foundation, structure
USACE - Wilmington: one story, Structure
1929 NGVD | [18 empty] | USACE - Wilmington: one story w/ 1/2 living area below, Structure
1988 NAVD | [18 empty] | USACE - Wilmington: one story w/ basement, Structure
USACE - Wilmington: split level, Structure
USACE - Wilmington: two story, Pile foundation, structure
USACE - Wilmington: two story, Structure
USACE - Wilmington: two story w/ 1/2 living area below, Structure
USACE - Chicago: Mobile Home, structure
USACE - Galveston: Mobile Home, structure
USACE - New Orleans: Mobile Home, structure, fresh water, short duration
USACE - New Orleans: Mobile Home, structure, fresh water, long duration
USACE - New Orleans: Mobile Home, structure, salt water, short duration
USACE - New Orleans: Mobile Home, structure, salt water, long duration
USACE - New Orleans: Mobile Home, structure, fresh water, short duration
USACE - New Orleans: Mobile Home, structure, fresh water, long duration
USACE - New Orleans: Mobile Home, structure, salt water, short duration
USACE - New Orleans: Mobile Home, structure, salt water, long duration
USACE - New Orleans: Mobile Home, structure, fresh water, short duration
USACE - New Orleans: Mobile Home, structure, salt water, long duration
USACE - Wilmington: Mobile Home, structure
USACE - Chicago: Apartment Unit Grade, Structure
USACE - Chicago: Apartment Unit Sub-Grade, Structure
USACE - Galveston: Apartment, living area on one floor, Structure
USACE - Galveston: Condominium, living area on multiple floors, Structure
USACE - Wilmington: Apartments, Structure
USACE - Galveston: Hotel, structure
USACE - Galveston: Motel Unit, structure
USACE - Wilmington: Hotel, structure
USACE - Wilmington: Motel, structure
USACE - Galveston: Nursing Home, structure
USACE - Galveston: Nursing Home, structure
USACE - Wilmington: Rest Home, structure

## Mit Button
Mitigation Reconstruction Checklist
Elevation Checklist
Dry Floodproofing Checklist
Back to Flowchart