Copyright 2002 and 2005 AIA
MASTERSPEC Full Length
11/02 (R 05/06)

Copyright 2002 and 2005 by The American Institute of Architects (AIA)

Exclusively published and distributed by Architectural Computer Services, Inc. (ARCOM) for the AIA

SECTION 013300 - SUBMITTAL PROCEDURES
This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

PART 1 -  GENERAL

1.1 RELATED DOCUMENTS

A. Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.

1.2 SUMMARY

A. This Section includes administrative and procedural requirements for submitting Shop Drawings, Product Data, Samples, and other submittals.

B. Related Sections include the following:

Subparagraphs below include submittals usually specified in other Sections.  Revise to suit Project.

1. Division 01 Section "Payment Procedures" for submitting Applications for Payment and the Schedule of Values.

2. Division 01 Section "Project Management and Coordination" for submitting and distributing meeting and conference minutes and for submitting Coordination Drawings.

3. Division 01 Section "Construction Progress Documentation" for submitting schedules and reports, including Contractor's Construction Schedule and the Submittals Schedule.

4. Division 01 Section "Photographic Documentation" for submitting [construction photographs] [and] [construction videotapes].

5. Division 01 Section "Quality Requirements" for submitting test and inspection reports[and for mockup requirements].

6. Division 01 Section "Closeout Procedures" for submitting warranties.

7. Division 01 Section "Project Record Documents" for submitting Record Drawings, Record Specifications, and Record Product Data.

8. Division 01 Section "Operation and Maintenance Data" for submitting operation and maintenance manuals.

9. Division 01 Section "Demonstration and Training" for submitting videotapes of demonstration of equipment and training of Owner's personnel.

10. Divisions 02 through 49 Sections for specific requirements for submittals in those Sections.

1.3 DEFINITIONS

A. Action Submittals:  Written and graphic information that requires Architect's[ and Construction Manager's]  responsive action.

B. Informational Submittals:  Written information that does not require Architect's[ and Construction Manager's]  responsive action.  Submittals may be rejected for not complying with requirements.

1.4 SUBMITTAL PROCEDURES

See Evaluations for cautions on use of CAD Drawings, in first paragraph below, for submittals.

A. General:  Electronic copies of CAD Drawings of the Contract Drawings will[ not] be provided by Architect for Contractor's use in preparing submittals.

B. Coordination:  Coordinate preparation and processing of submittals with performance of construction activities.

1. Coordinate each submittal with fabrication, purchasing, testing, delivery, other submittals, and related activities that require sequential activity.

Retain subparagraph and associated subparagraph below if one submittal has an impact on another submittal.  Submittals that require concurrent review should be so indicated in those Sections.

2. Coordinate transmittal of different types of submittals for related parts of the Work so processing will not be delayed because of need to review submittals concurrently for coordination.

a. [Architect reserves] [Architect and Construction Manager reserve] the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.

C. Submittals Schedule:  Comply with requirements in Division 01 Section "Construction Progress Documentation" for list of submittals and time requirements for scheduled performance of related construction activities.

D. Processing Time:  Allow enough time for submittal review, including time for resubmittals, as follows.  Time for review shall commence on [Architect's] [Construction Manager's] receipt of submittal.  No extension of the Contract Time will be authorized because of failure to transmit submittals enough in advance of the Work to permit processing, including resubmittals.

1. Initial Review:  Allow [15] <Insert number> days for initial review of each submittal.  Allow additional time if coordination with subsequent submittals is required.  [Architect] [Construction Manager] will advise Contractor when a submittal being processed must be delayed for coordination.

2. Intermediate Review:  If intermediate submittal is necessary, process it in same manner as initial submittal.

3. Resubmittal Review:  Allow [15] <Insert number> days for review of each resubmittal.

Delete subparagraph below if not required.

4. Sequential Review:  Where sequential review of submittals by Architect's consultants, Owner, or other parties is indicated, allow [21] <Insert number> days for initial review of each submittal.

Insert list of submittals below requiring sequential review, or delete and identify submittals in Sections where they are specified.  Structural, mechanical, plumbing, and electrical components are examples of the Work that often require sequential review.

a. <Insert list of Specification Sections requiring sequential review.>

Allowing procedure in subparagraph below may cause tracking problems for Architect and Construction Manager, if any.  Delete if not allowed.  See Evaluations.

5. Concurrent Consultant Review:  Where the Contract Documents indicate that submittals may be transmitted simultaneously to Architect and to Architect's consultants, allow [15] <Insert number> days for review of each submittal.  Submittal will be returned to [Architect] [Construction Manager, through Architect,] before being returned to Contractor.

Insert list of submittals below allowing concurrent review or delete and identify submittals in Sections where they are specified.  Structural, mechanical, plumbing, and electrical components are examples of the Work that often require simultaneous transmittal to Architect and consultants.

a. <Insert list of Specification Sections allowing concurrent review.>

E. Identification:  Place a permanent label or title block on each submittal for identification.

1. Indicate name of firm or entity that prepared each submittal on label or title block.

2. Provide a space approximately [6 by 8 inches (150 by 200 mm)] <Insert size> on label or beside title block to record Contractor's review and approval markings and action taken by Architect[ and Construction Manager].

3. Include the following information on label for processing and recording action taken:

Revise list below to suit Project.

a. Project name.

b. Date.

c. Name and address of Architect[ and Construction Manager].

d. Name and address of Contractor.

e. Name and address of subcontractor.

f. Name and address of supplier.

g. Name of manufacturer.

Revise first subparagraph and associated subparagraph below to suit Project and office practice.  See Evaluations.

h. Submittal number or other unique identifier, including revision identifier.

1) Submittal number shall use Specification Section number followed by a decimal point and then a sequential number (e.g., 061000.01).  Resubmittals shall include an alphabetic suffix after another decimal point (e.g., 061000.01.A).

i. Number and title of appropriate Specification Section.

j. Drawing number and detail references, as appropriate.

k. Location(s) where product is to be installed, as appropriate.

l. Other necessary identification.

F. Deviations:  [Highlight] [Encircle] [Highlight, encircle,] or otherwise specifically identify deviations from the Contract Documents on submittals.

Coordinate first paragraph and subparagraphs below with office policy.  Marking numerous copies of submittals can be time consuming.

G. Additional Copies:  Unless additional copies are required for final submittal, and unless Architect[ or Construction Manager]  observes noncompliance with provisions in the Contract Documents, initial submittal may serve as final submittal.

1. Submit one copy of submittal to concurrent reviewer in addition to specified number of copies to Architect[ and Construction Manager].

2. Additional copies submitted for maintenance manuals will[ not] be marked with action taken and will be returned.

H. Transmittal:  Package each submittal individually and appropriately for transmittal and handling.  Transmit each submittal using a transmittal form.  Architect[ and Construction Manager]  will [return submittals, without review,] [discard submittals] received from sources other than Contractor.

If retaining last option in subparagraph below, insert a sample of the form to be used at end of Section.

1. Transmittal Form:  Use [AIA Document G810] [CSI Form 12.1A] [facsimile of sample form at end of Section].

Delete subparagraph above or below.  Retain below if transmittal forms typically used by contractors are acceptable; otherwise, retain above.  Above is more common.

2. Transmittal Form:  Provide locations on form for the following information:

Revise list below to suit Project.

a. Project name.

b. Date.

c. Destination (To:).

d. Source (From:).

e. Names of subcontractor, manufacturer, and supplier.

f. Category and type of submittal.

g. Submittal purpose and description.

h. Specification Section number and title.

i. Drawing number and detail references, as appropriate.

j. Transmittal number[, numbered consecutively].

k. Submittal and transmittal distribution record.

l. Remarks.

m. Signature of transmitter.

Retain subparagraph below with either transmittal form above.

3. On an attached separate sheet, prepared on Contractor's letterhead, record relevant information, requests for data, revisions other than those requested by Architect[ and Construction Manager]  on previous submittals, and deviations from requirements in the Contract Documents, including minor variations and limitations.  Include same label information as related submittal.

I. Resubmittals:  Make resubmittals in same form and number of copies as initial submittal.

1. Note date and content of previous submittal.

2. Note date and content of revision in label or title block and clearly indicate extent of revision.

3. Resubmit submittals until they are marked "<Insert approval notation from Architect's (and Construction Manager's) action stamp>."

J. Distribution:  Furnish copies of final submittals to manufacturers, subcontractors, suppliers, fabricators, installers, authorities having jurisdiction, and others as necessary for performance of construction activities.  Show distribution on transmittal forms.

K. Use for Construction:  Use only final submittals with mark indicating "<Insert approval notation from Architect's (and Construction Manager's) action stamp>" taken by Architect[ and Construction Manager].

1.5 CONTRACTOR'S USE OF ARCHITECT'S CAD FILES

A. General:  At Contractor's written request, copies of Architect's CAD files will be provided to Contractor for Contractor's use in connection with Project, subject to the following conditions:

Examples of items that may be included in subparagraph below include limitation to files that already exist, limitations on incorporating modifications, limitations on availability of Architect's consultant files, limitation of CAD system formats, limitation on CAD entity attributes and layering, restrictions on Contractor's use, cost of providing files, mode of transmittal, and delivery time.

1. <Insert conditions on which CAD files will made available.>

PART 2 -  PRODUCTS

2.1 ACTION SUBMITTALS

A. General:  Prepare and submit Action Submittals required by individual Specification Sections.

Delete subparagraph below if not required.  If retained, determine whether paper copies are still required, such as for Project Record Documents.

1. Submit electronic submittals directly to extranet specifically established for Project.

Additional copies may be required for each type of submittal below for projects with a construction manager.

B. Product Data:  Collect information into a single submittal for each element of construction and type of product or equipment.

1. If information must be specially prepared for submittal because standard printed data are not suitable for use, submit as Shop Drawings, not as Product Data.

2. Mark each copy of each submittal to show which products and options are applicable.

3. Include the following information, as applicable:

Revise list below to suit Project.

a. Manufacturer's written recommendations.

b. Manufacturer's product specifications.

c. Manufacturer's installation instructions.

d. Standard color charts.

e. Manufacturer's catalog cuts.

f. Wiring diagrams showing factory-installed wiring.

g. Printed performance curves.

h. Operational range diagrams.

i. Mill reports.

j. Standard product operation and maintenance manuals.

k. Compliance with specified referenced standards.

l. Testing by recognized testing agency.

m. Application of testing agency labels and seals.

n. Notation of coordination requirements.

4. Submit Product Data before or concurrent with Samples.

5. Number of Copies:  Submit [three] <Insert number> copies of Product Data, unless otherwise indicated.  Architect[, through Construction Manager,] will return [two] <Insert number> copies.  Mark up and retain one returned copy as a Project Record Document.

C. Shop Drawings:  Prepare Project-specific information, drawn accurately to scale.  Do not base Shop Drawings on reproductions of the Contract Documents or standard printed data[, unless submittal of Architect's CAD Drawings are otherwise permitted].

1. Preparation:  Fully illustrate requirements in the Contract Documents.  Include the following information, as applicable:

Revise list below to suit Project.  Comply with Owner's requirements and office policy.

a. Dimensions.

b. Identification of products.

c. Fabrication and installation drawings.

d. Roughing-in and setting diagrams.

e. Wiring diagrams showing field-installed wiring, including power, signal, and control wiring.

f. Shopwork manufacturing instructions.

g. Templates and patterns.

h. Schedules.

i. Design calculations.

j. Compliance with specified standards.

k. Notation of coordination requirements.

l. Notation of dimensions established by field measurement.

m. Relationship to adjoining construction clearly indicated.

n. Seal and signature of professional engineer if specified.

o. Wiring Diagrams:  Differentiate between manufacturer-installed and field-installed wiring.

Revise subparagraph below to establish a standard sheet size and format.

2. Sheet Size:  Except for templates, patterns, and similar full-size drawings, submit Shop Drawings on sheets at least 8-1/2 by 11 inches (215 by 280 mm) but no larger than 30 by 40 inches (750 by 1000 mm).

Retain one of two subparagraphs below.  First subparagraph assumes Architect and Contractor will make copies from opaque print.

3. Number of Copies:  Submit two opaque (bond) copies of each submittal. Architect[, through Construction Manager,]  will return one copy.

4. Number of Copies:  Submit [three] <Insert number> opaque copies of each submittal, unless copies are required for operation and maintenance manuals.  Submit [five] <Insert number> copies where copies are required for operation and maintenance manuals.  Architect[ and Construction Manager]  will retain [two] <Insert number> copies; remainder will be returned.[  Mark up and retain one returned copy as a Project Record Drawing.]

D. Samples:  Submit Samples for review of kind, color, pattern, and texture for a check of these characteristics with other elements and for a comparison of these characteristics between submittal and actual component as delivered and installed.

1. Transmit Samples that contain multiple, related components such as accessories together in one submittal package.

2. Identification:  Attach label on unexposed side of Samples that includes the following:

Revise list below to suit Project.

a. Generic description of Sample.

b. Product name and name of manufacturer.

c. Sample source.

d. Number and title of appropriate Specification Section.

3. Disposition:  Maintain sets of approved Samples at Project site, available for quality-control comparisons throughout the course of construction activity.  Sample sets may be used to determine final acceptance of construction associated with each set.

Delete first subparagraph below if not required.

a. Samples that may be incorporated into the Work are indicated in individual Specification Sections.  Such Samples must be in an undamaged condition at time of use.

b. Samples not incorporated into the Work, or otherwise designated as Owner's property, are the property of Contractor.

Revise first two subparagraphs and associated subparagraphs below if Project requires a different procedure.  Consider indicating Samples for initial selection as a separate item in the Submittals Schedule.

Delete subparagraph and associated subparagraph below if colors and other characteristics are preselected and specified or scheduled.

4. Samples for Initial Selection:  Submit manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available.

a. Number of Samples:  Submit [one] <Insert number> full set(s) of available choices where color, pattern, texture, or similar characteristics are required to be selected from manufacturer's product line.  Architect[, through Construction Manager,]  will return submittal with options selected.

Subparagraph below can be used with or without Samples for initial selection.

5. Samples for Verification:  Submit full-size units or Samples of size indicated, prepared from same material to be used for the Work, cured and finished in manner specified, and physically identical with material or product proposed for use, and that show full range of color and texture variations expected.  Samples include, but are not limited to, the following:  partial sections of manufactured or fabricated components; small cuts or containers of materials; complete units of repetitively used materials; swatches showing color, texture, and pattern; color range sets; and components used for independent testing and inspection.

a. Number of Samples:  Submit [three] <Insert number> sets of Samples.  Architect[ and Construction Manager]  will retain [two] <Insert number> Sample sets; remainder will be returned.[  Mark up and retain one returned Sample set as a Project Record Sample.]

1) Submit a single Sample where assembly details, workmanship, fabrication techniques, connections, operation, and other similar characteristics are to be demonstrated.

2) If variation in color, pattern, texture, or other characteristic is inherent in material or product represented by a Sample, submit at least [three] <Insert number> sets of paired units that show approximate limits of variations.

Product schedule or list in paragraph below is different than product list requested at beginning of Project, which is specified in Division 01 Section "Product Requirements."

E. Product Schedule or List:  As required in individual Specification Sections, prepare a written summary indicating types of products required for the Work and their intended location.  Include the following information in tabular form:

1. Type of product.  Include unique identifier for each product.

2. Number and name of room or space.

3. Location within room or space.

4. Number of Copies:  Submit [three] <Insert number> copies of product schedule or list, unless otherwise indicated.  Architect[, through Construction Manager,]  will return [two] <Insert number> copies.

a. Mark up and retain one returned copy as a Project Record Document.

Retain first paragraph below for projects with a construction manager.

F. Contractor's Construction Schedule:  Comply with requirements specified in Division 01 Section "Construction Progress Documentation" for Construction Manager's action.

G. Submittals Schedule:  Comply with requirements specified in Division 01 Section "Construction Progress Documentation."

H. Application for Payment:  Comply with requirements specified in Division 01 Section "Payment Procedures."

I. Schedule of Values:  Comply with requirements specified in Division 01 Section "Payment Procedures."

If needed, combine subcontract list in paragraph below with product list above.  Subcontract list is required by AIA Document A201 to be submitted as soon as practical after award of the Contract.

J. Subcontract List:  Prepare a written summary identifying individuals or firms proposed for each portion of the Work, including those who are to furnish products or equipment fabricated to a special design.[  Use CSI Form 1.5A.] Include the following information in tabular form:

1. Name, address, and telephone number of entity performing subcontract or supplying products.

2. Number and title of related Specification Section(s) covered by subcontract.

3. Drawing number and detail references, as appropriate, covered by subcontract.

4. Number of Copies:  Submit [three] <Insert number> copies of subcontractor list, unless otherwise indicated.  Architect[, through Construction Manager,]  will return [two] <Insert number> copies.

a. Mark up and retain one returned copy as a Project Record Document.

K. LEED Submittals:  Comply with requirements specified in Division 01 Section "Sustainable Design Requirements."

1. Number of Copies:  Submit [three] <Insert number> copies of LEED submittals, unless otherwise indicated.

2.2 INFORMATIONAL SUBMITTALS

A. General:  Prepare and submit Informational Submittals required by other Specification Sections.

Retain first subparagraph below as default requirement or requirement if number of copies is same for all types of submittals.  Additional copies may be required for projects with a construction manager.  Delete if specific quantity requirements are included with individual submittal requirements elsewhere in this Article.

1. Number of Copies:  Submit [two] <Insert number> copies of each submittal, unless otherwise indicated.  Architect[ and Construction Manager]  will not return copies.

2. Certificates and Certifications:  Provide a notarized statement that includes signature of entity responsible for preparing certification.  Certificates and certifications shall be signed by an officer or other individual authorized to sign documents on behalf of that entity.

3. Test and Inspection Reports:  Comply with requirements specified in Division 01 Section "Quality Requirements."

B. Coordination Drawings:  Comply with requirements specified in Division 01 Section "Project Management and Coordination."

Delete first paragraph below for projects with a construction manager.

C. Contractor's Construction Schedule:  Comply with requirements specified in Division 01 Section "Construction Progress Documentation."

D. Qualification Data:  Prepare written information that demonstrates capabilities and experience of firm or person.  Include lists of completed projects with project names and addresses, names and addresses of architects and owners, and other information specified.

E. Welding Certificates:  Prepare written certification that welding procedures and personnel comply with requirements in the Contract Documents.  Submit record of Welding Procedure Specification (WPS) and Procedure Qualification Record (PQR) on AWS forms.  Include names of firms and personnel certified.

F. Installer Certificates:  Prepare written statements on manufacturer's letterhead certifying that Installer complies with requirements in the Contract Documents and, where required, is authorized by manufacturer for this specific Project.

G. Manufacturer Certificates:  Prepare written statements on manufacturer's letterhead certifying that manufacturer complies with requirements in the Contract Documents.  Include evidence of manufacturing experience where required.

H. Product Certificates:  Prepare written statements on manufacturer's letterhead certifying that product complies with requirements in the Contract Documents.

I. Material Certificates:  Prepare written statements on manufacturer's letterhead certifying that material complies with requirements in the Contract Documents.

J. Material Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting test results of material for compliance with requirements in the Contract Documents.

K. Product Test Reports:  Prepare written reports indicating current product produced by manufacturer complies with requirements in the Contract Documents.  Base reports on evaluation of tests performed by manufacturer and witnessed by a qualified testing agency, or on comprehensive tests performed by a qualified testing agency.

Coordinate individual Specification Sections with first paragraph and subparagraphs below by including specific model code organization in that Section.  If all are same, insert name below.

L. Research/Evaluation Reports:  Prepare written evidence, from a model code organization acceptable to authorities having jurisdiction, that product complies with building code in effect for Project.  Include the following information:

1. Name of evaluation organization.

2. Date of evaluation.

3. Time period when report is in effect.

4. Product and manufacturers' names.

5. Description of product.

6. Test procedures and results.

7. Limitations of use.

M. Schedule of Tests and Inspections:  Comply with requirements specified in Division 01 Section "Quality Requirements."

N. Preconstruction Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of tests performed before installation of product, for compliance with performance requirements in the Contract Documents.

O. Compatibility Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of compatibility tests performed before installation of product.  Include written recommendations for primers and substrate preparation needed for adhesion.

P. Field Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of field tests performed either during installation of product or after product is installed in its final location, for compliance with requirements in the Contract Documents.

Q. Maintenance Data:  Prepare written and graphic instructions and procedures for operation and normal maintenance of products and equipment.  Comply with requirements specified in Division 01 Section "Operation and Maintenance Data."

R. Design Data:  Prepare written and graphic information, including, but not limited to, performance and design criteria, list of applicable codes and regulations, and calculations.  Include list of assumptions and other performance and design criteria and a summary of loads.  Include load diagrams if applicable.  Provide name and version of software, if any, used for calculations.  Include page numbers.

S. Manufacturer's Instructions:  Prepare written or published information that documents manufacturer's recommendations, guidelines, and procedures for installing or operating a product or equipment.  Include name of product and name, address, and telephone number of manufacturer.  Include the following, as applicable:

1. Preparation of substrates.

2. Required substrate tolerances.

3. Sequence of installation or erection.

4. Required installation tolerances.

5. Required adjustments.

6. Recommendations for cleaning and protection.

T. Manufacturer's Field Reports:  Prepare written information documenting factory-authorized service representative's tests and inspections.  Include the following, as applicable:

1. Name, address, and telephone number of factory-authorized service representative making report.

2. Statement on condition of substrates and their acceptability for installation of product.

3. Statement that products at Project site comply with requirements.

4. Summary of installation procedures being followed, whether they comply with requirements and, if not, what corrective action was taken.

5. Results of operational and other tests and a statement of whether observed performance complies with requirements.

6. Statement whether conditions, products, and installation will affect warranty.

7. Other required items indicated in individual Specification Sections.

U. Insurance Certificates and Bonds:  Prepare written information indicating current status of insurance or bonding coverage.  Include name of entity covered by insurance or bond, limits of coverage, amounts of deductibles, if any, and term of the coverage.

V. Construction [Photographs] [and] [Videotapes]:  Comply with requirements specified in Division 01 Section "Photographic Documentation."

Receipt of Material Safety Data Sheet (MSDS) information by Architect may result in unwanted liability for product safety.  Many architects return submittals that contain MSDSs with transmittals that indicate that MSDSs are not required by the Contract Documents and that they were not reviewed.  See Evaluations.

W. Material Safety Data Sheets (MSDSs):  Submit information directly to Owner; do not submit to Architect.

1. Architect will not review submittals that include MSDSs and will return the entire submittal for resubmittal.

2.3 DELEGATED DESIGN

This Article directly relates to AIA Document A201 requirement for Contractor to provide professional services where indicated by the Contract Documents.  AIA Document A201 refers to design professional, but no definition is included.  Delete this Article if authorities having jurisdiction do not allow Contractor to perform these services.  See Evaluations.

A. Performance and Design Criteria:  Where professional design services or certifications by a design professional are specifically required of Contractor by the Contract Documents, provide products and systems complying with specific performance and design criteria indicated.

1. If criteria indicated are not sufficient to perform services or certification required, submit a written request for additional information to Architect.

B. Delegated-Design Submittal:  In addition to Shop Drawings, Product Data, and other required submittals, submit [three] <Insert number> copies of a statement, signed and sealed by the responsible design professional, for each product and system specifically assigned to Contractor to be designed or certified by a design professional.

1. Indicate that products and systems comply with performance and design criteria in the Contract Documents.  Include list of codes, loads, and other factors used in performing these services.

PART 3 -  EXECUTION

3.1 CONTRACTOR'S REVIEW

A. Review each submittal and check for coordination with other Work of the Contract and for compliance with the Contract Documents.  Note corrections and field dimensions.  Mark with approval stamp before submitting to Architect[ and Construction Manager].

B. Approval Stamp:  Stamp each submittal with a uniform, approval stamp.  Include Project name and location, submittal number, Specification Section title and number, name of reviewer, date of Contractor's approval, and statement certifying that submittal has been reviewed, checked, and approved for compliance with the Contract Documents.

3.2 ARCHITECT'S[ AND CONSTRUCTION MANAGER'S] / ACTION

A. General:  Architect[ and Construction Manager]  will not review submittals that do not bear Contractor's approval stamp and will return them without action.

Most architects (and construction managers) use a stamp to indicate action taken on submittals.  Retain first paragraph and subparagraph below if such a stamp is used, or substitute another system to comply with office policy or Owner's requirements.  AIA Document A201 states that "the Architect will review and approve or take other appropriate action upon the Contractor's submittals." The CMa version of AIA Document A201 states that Construction Manager will review and approve submittals before transmitting those recommended for approval to Architect.

B. Action Submittals:  Architect[ and Construction Manager]  will review each submittal, make marks to indicate corrections or modifications required, and return it.  Architect[ and Construction Manager]  will stamp each submittal with an action stamp and will mark stamp appropriately to indicate action taken, as follows:

On advice of counsel, select appropriate terms for action stamp and insert term and explanation of each action taken in subparagraph below.  See Evaluations.

1. <Insert description of each action indicated on Architect's (and Construction Manager's) stamp.>

C. Informational Submittals:  Architect[ and Construction Manager]  will review each submittal and will not return it, or will return it if it does not comply with requirements.  Architect[ and Construction Manager]  will forward each submittal to appropriate party.

D. Partial submittals are not acceptable, will be considered nonresponsive, and will be returned without review.

E. Submittals not required by the Contract Documents may not be reviewed and may be discarded.

END OF SECTION 013300

SUBMITTAL PROCEDURES
013300 - 1

