MEETING MINUTES

Timbers Office Park Project LA # 96191/97038/97046
Date:  2/22/01 Location: Timbers Office Park Time: 11:00 PM_
Attendees:
NAME                                      ORGANIZATION
                              PHONE
Chuck Dammon

Dammon Engineering

649-5832/641-5950

Ben White


Orleans Parish School BD

942-3517/942-3516

Jason Grogtson

RFCC




956-2005/456-2010

Tigger Larson                        Thyssen Dover Elevator

1. Description of work completed:

A. Elevator  #1 is being worked on in bldg 3510, Elevator #2 will start repair tomorrow.

Elevators in bldg 3500 are complete per spec’s, we are waiting for quotes from the contractor to bring it up to phase II compliance.

Simplex hooked the elevators up to the alarm.

B. The new sidewalk is installed next to the boiler room and preparations for the installation of sod to start next week.

C. The bathroom renovations are 98% complete in bldg. 3500. New wallpaper was added to the handicap stalls in both the mens and womens bathrooms. Today the support for the stall will be installed to complete the installation.
E.              D. The conduit for the new power line for the sign in front of bldg. 3500 is      installed and the backfill complete, the wire will be pulled next week.

F. Installation of the new wallpaper is complete on the third floor bldg. 3500, carpet & base will be installed next week.  Bldg. 3500 2nd floor lobby finished wallpaper installation, carpet and base to start next week.

2. Action items developed from meeting:

A. Alan Hollingsworth with Thyssen Dover Elevator will give RFCC a list of  the additional items and prices for the phase II upgrade on the elevator.

B.  The wrong doors were received for Bldg. 3510 that are to be installed next   to  payroll, they must show a “B” label.

 _________________________Date______

Chuck Dammon/Project Manager

