## Sheet1
|  |  | P.O. Progression: | P.O. Balance | Total Value of P.O.
Line Item 1 | Original Purchase Order: 96782, 6/10/2013 |  | 23000 | 23000 | 23000
23000
6405 | Invoice from Dammon, 9/17/2013 |  |  | 23000
|  | Labor Fees | -6867.5 | 16132.5
|  | Survey Fee | -8800 | 7332.5
|  | Soils analysis fees | -5060 | 2272.5
2272.5
Line Item 2 | Amendment #1, 10/8/2013 |  | 79277.52 | 81550.02 | 102277.52
|  | Phase 1 and Phase 2a- 3,348 s.f. Southside Building Addition, 3 Ramps w/doors in main warehouse & renovation of existing office space. 7% of estimated construction cost $1,132,136.00 |  | 81550.02
81550.02
81550.02
81550.02
6422 | Invoice from Dammon, 10/30/2013 |  | -30411.26 | 51138.76
|  | Amendment #1 through 50% Design |  | 51138.76
51138.76
6431 | Invoice from Dammon, 11/26/2013 |  | -51138.76 | 0
|  | Amendment #1 through 100% Design |  | 0
0
Line Item 3 | Proposed Amendment #3, 1/30/2014 |  | 39396 | 39396 | 141673.52
|  | Phase 2B - Mezzanine Office Addition inside existing warehouse with the renovation of existing power, sprinkler, domestic water, compressed air & natural gas, 7% of estimated construction cost $562,800.00 |  | 39396
39396
39396
39396
39396
6463 | Invoice from Dammon 2/27/2014 |  | -35396 | 4000
| Reduction for CX Fire Marshal & Site Visits |  | -4000 | 0
Line Item 4 | Proposed Amendment #2, 1/30/2014 |  | 23030.05 | 23030.05 | 164703.57
|  | Phase 1 - Southside Building Addition - adjustment for actual construction cost, Amendment #1, $1,494,001.00 based on the addition of two ramps w/doors, new 350' demising wall, removal of portable offices, new cased opening, enlarging existing cased opening & two new exit doors with stairs. All of these were not included in our proposal Amendment #1 |  | 23030.05
23030.05
23030.05
23030.05
23030.05
23030.05
23030.05
6454R1 | Invoice from Dammon 2/4/2014 |  | -23030.05 | 0
0
Line Item 5 | Proposed Amendment #4, 2/27/2014 |  | 70000 | 70000 | 234703.57
|  | Phase 3 - 2 Story Office Building Addition NorthEast corner of building |  | 70000
70000
70000
70000
Line Item 6 | Proposed Amendment #5, 9/19/2014 |  | 7800 | 77800 | 242503.57
Phase 3 - 2 Story Office Building Structural Calculations to support single story