## Sheet1
Progress | Progress Completion | Rate | Amount to Collect
13085.54
Program/Schematic Design Phase | 100% | 10% | 1308.554
Design Development Phase | 100% | 15% | 1962.831
Construction Document Phase | 100% | 30% | 3925.662
Bidding and Contract Phase | 100% | 5% | 654.277
Construction Phase | 0% | 35% | 0
Construction Close Out Phase | 0% | 4% | 0
One Year Warranty Inspection | 0% | 1% | 0
| Totals | 100% | 7851.324
Less Previously invoiced |  |  | 0
Total Amount Due |  |  | 7851.324