March 20, 2001

Mr. Bruce Levy

Facility Planning Dept

Orleans Parish School Board

4300 Almonaster Ave.

New Orleans, LA  70126

RE;
NOCHC

Project # 96127
Meter for New Chiller

Dear Bruce;

   Dammon Engineering, Inc has spoken to Bob Bindewald of Industrial & Mechanical Contractors, Inc. about the lack power for the new chiller installed at the school.  Mr. Bindewald has stated that the Permit Department (City of New Orleans) has approved the installation of the meter box from the electrical contractor (Ormand Electric). And further more the Permit department has turned over the approval to Entergy several days ago, no one can give me an exact date of when that happened. I talked to Bob Bindewald of I.M.C. this morning (03-20-02) and he has stated that the electrical contractor (Ormand Electric) has called and was able to talk to Claude Phipps of Entergy and they are to install a meter at NOCHC Friday.

I personally called Claude Phipps (Entergy) with the phone numbers you have given me and one number just rings and the other number his voice mail answers. Both yesterday and today I have left messages for him to call me to verify the situation. This morning at 9:45 am Claude Phipps of Entergy has returned my call and stated that he has scheduled it to be installed Friday (03-22-02), But is trying to have it installed before that.

IM in receipt of your email and will schedule a weekly meeting starting next week, I will let you know what day that will be. Also IM writing a letter to I.M.C. to get the parking lot completed.

Sincerely,

Chuck Dammon/Project Manager

