## Sheet1
Progress | Progress Completion | Rate | Amount to Collect
18875.13
Program/Schematic Design Phase | 100% | 10% | 1887.513
Design Development Phase | 100% | 15% | 2831.2695
Construction Document Phase | 100% | 30% | 5662.539
Bidding and Contract Phase | 100% | 5% | 943.7565
Construction Phase | 0% | 35% | 0
Construction Close Out Phase | 0% | 4% | 0
One Year Warranty Inspection | 0% | 1% | 0
| Totals | 100% | 11325.078
Less Previously invoiced |  |  | 0
Total Amount Due |  |  | 11325.078