## Sheet1
Activities / Tasks / Items | Priority | Assigned To | Status | NOTES
Intro letters to acute care hospitals **ASC only** |  | Holly | Not Started
Admitting privileges for the local hospital(s) - All physicians |  | Holly | Not Started | need input from the physician's and also their approval to the hospitals
Internal accreditation credentialing for Medical Director/Proceduralists |  | Holly | Not Started
Provider Proctoring program |  | Holly | Not Started
Gov Body privileging letters to providers |  | Holly | Not Started
Accreditation Floorplan approval |  | Holly | Not Started | Cost is responsibility of organization. $285
Accreditation Application |  | Holly | Not Started | Cost is responsibility of organization Approx $6000
Dept Public Health registration if applicable |  | Holly | Not Started | Cost is responsibility of organization Approx $300
Small Generator Waste Permit |  | Holly | Not Started | Cost is responsibility of organization Approx $300
Business Permit |  | Organization | Not Started | Cost is responsibility of organization Varies by location
Register with State for new Hires |  | Organization | Not Started | no cost
CLIA Waived application. Clia Moderate not included in the base contract. |  | Holly | Not Started | Cost is responsibility of organization. $113 State and approx $300 CMS. Annual requirement
CLIA moderate requires one physician to be Lab Director and take the applicable course online through the University of Iowa. |  | Organization | Not Started
Radiology safety plan, dossimetry reports |  | Holly | Not Started
Radiology badge contract |  | Holly | Not Started | Cost is responsibility of organization. Approx. $800/yr
Business Associate Agreements |  | Holly | Not Started
Register C arm with state within 30 days of installation |  | Holly | Not Started | Cost is responsibility of organization
Obtain FDA 2579 when C arms installed |  | Holly | Not Started
Air Quality Control permit if applicable |  | Holly | Not Started | Cost is responsibility of organization. Approx $300
State Licence if applicable |  | Holly |  | Cost is responsibility of organization. Varies by State
Radiology Shielding Plan |  | Holly | Not Started | Therapy Physics - $800
Order Nurse supplies |  | Holly | Not Started | Expect $6000-$10,000.
Arrange for Vendor Contracts |  | Holly | Not Started
Hospital Transfer Agreement |  | Holly | Not Started
1st Quality Council Meeting/ Governing body meeting/Infection control (mandatory) |  | Holly | Not Started
Bio equipment inspection before survey |  | Holly | Not Started | Cost is responsbility of organization. Cost $400 approx.
Physicist after installation of c-arms |  | Holly | Not Started | Cost approx. $900
Building occupancy & fire marshall |  | Organization | Not Started | Cost varies per location
Fire Extinguisher Inspection before survey |  | Holly | Not Started | Cost is reponsibility of organization. Approx $300
CO2 Fire Extinguisher for procedure rooms |  | Organization | Not Started | About $100. Cost is resp of organization
Pharmacist contract |  | Holly | Not Started | Requirements vary by State. Cost to be arranged between pharmacist and facility.
SDS (Hazard Communications) Program |  | Holly | Not Started
Narcotic procurement process |  | Holly | Not Started | Organization must obtain 222 forms and have a DEA with new facility address
Employee Illness & Injury Program |  | Holly | Not Started | Workers compensation insurance needed
Facility Safety manual |  | Holly | Not Started
Environment of Care Program |  | Holly | Not Started
LIFE SAFETY |  | Holly | Not Started
Cleaning schedule & policies |  | Holly | Not Started
Policies and Procedures, Bylaws, Mission Statement |  | Holly | Not Started | Discharge instructions and preop instructions will be customized to your requirements.
Electronic procedure forms (or hardcopy paper) |  | Holly | Not Started | A few options available. I use IntakeQ for electronic forms. Very economical and can be used as an EMR.
Emergency Preparedness Plan |  | Holly | Not Started
Discharge instructions |  | Holly | Not Started | carbonless forms from professional printers
Patients Rights Posters |  | Holly | Not Started
Privacy practice brochures |  | Holly | Not Started
Narcotic and procedure log books |  | Holly | Not Started
Patient Registration Forms |  | Holly | Not Started
Crash Cart logs and algorithms |  | Holly | Not Started
Reporting Adverse Events program |  | Holly | Not Started
Crisis Flip charts (Emergency prep program) |  | Holly | Not Started
Allergic Reaction flip charts |  | Holly | Not Started
Sexual harassment policy & training |  | Holly | Not Started
NPSG |  | Holly | Not Started
High Alert Medications List, Confused Drug Names, Tall man letters |  | Holly | Not Started
Quality projects x2 (mandatory) |  | Holly | Not Started
Quality indicators |  | Holly | Not Started
State Risk Mgmt Program |  | Holly | Not Started
All Hazards Risk Assessment |  | Holly | Not Started
Infection Risk Assessment |  | Holly | Not Started
HR files |  | Holly | Not Started
HR / Staff notice board |  | Holly | Not Started
Staff Competencies |  | Holly | Not Started
Picture name badges |  | Organization | Not Started | www.nametagwizard.com I will assist to order correct badges. Cost $10 per staff member. Organization responsible for cost.
Background checks |  | Organization | Not Started | www.clearchecks.com Basic background $30. Organiation responsible for cost.
Staff TB tests and other mandatory forms |  | Holly | Not Started | organization responsible for cost of TB tests and any other health requirements mandated by the State eg. N95 fit tests
staff meeting - Drills, Cleaning, updates, hand hygiene, Emergency Prep, end of day PR cleaning, HIPAA, |  | Holly | Not Started
Initial OSHA training modules for staff |  | Holly | Not Started
Cleaning contract |  | Holly | Not Started | organization responsible for costs. Cost varies.
Linen contract - includes scrubs for staff in procedure room |  | Holly | Not Started | organization responsible for costs. Base price for low volume is $35/week.
Waste pickup contract |  | Holly | Not Started | organization responsible for costs Approx $155/month for 1 pickup /month.
Oxygen contract |  | Holly | Not Started | organization responsible for costs. If compressed O2 bottles, expect $1200 at startup then $100+ per month.
Occupational Health Contract |  | Holly | Not Started | Needed for employee Illness and Injury program.
Biohazard spill kits & signage |  | Holly | Not Started
OSHA approved first aid kit & signage |  | Holly | Not Started
Emergency Evacuation Program |  | Holly | Not Started
Safety and Security Program |  | Holly | Not Started
Mandatory State postings (signage) |  | Holly | Not Started
Instructions for Use bin (IFU) |  | Holly | Not Started
Noah weather wind up radio/solar / 2-way radios |  | Holly | Not Started
Temp Recorder for medication fridge |  | Organization | Not Started | Must be a recording thermometer. Roughly $300 on amazon
2 portable (pocket size) Spo2 monitors & 2 manual BP cuffs for crash carts |  | Organization | Not Started
Time out white boards for procedure rooms |  | Holly | Not Started | Cost is $200. Holly has in stock
3M mop non-aerosol and disposable pads |  | Holly | Not Started | Cost is $200. This is the only mop that meets infection control requirements.
Assist with physical set up of faciity |  | Holly | Not Started | Organization will need to arrange for the equipment to be unloaded from trucks and brought into facility then setup of stands, etc.
If a preliminary survey is required, consultant can arrange to be onsite to assist with surveyor. |  | Holly | Not Started | Additional fee required if this visit is outside of the basic contract.