## G702
Application and Certificate for Payment
TO OWNER: |  |  |  |  | PROJECT: | [7 empty] | APPLICATION NO: | 4 | Distribution to:
St Tammany Parish School Board |  |  |  |  | BOYET JR HIGH SCHOOL | [7 empty] | PERIOD TO: | 2024-08-23 | OWNER:
[5 empty] | HVAC REPLACEMENT | [7 empty] | CONTRACT FOR: | BOYET JR HIGH SCHOOL | ENGINEER | x
FROM CONTRACTOR: |  |  |  |  | VIA | [7 empty] | CONTRACT DATE: | 2024-03-27 | CONTRACTOR:
A&A Mechanical, LLC |  |  |  |  | ENGINEER: |  |  | DAMMON ENGINEERING |  |  |  |  | PROJECT NOS: | PO428 | FIELD:
[8 empty] | INC. | [6 empty] | OTHER:
CONTRACTOR'S APPLICATION FOR PAYMENT | [10 empty] | The undersigned Contractor certifies that to the best of the Contractor's knowledge, information and belief the Work covered by this Application for Payment has been completed in accordance with the Contract Documents, that all amounts have been paid by the Contractor for Work for which previous Certificates for Payment were issued and payments received from the Owner, and that current payment shown herein is now due.
Application is made for payment, as shown below, in connection with the Contract.
Continuation Sheet, AIA Document G703, is attached.
1. | ORIGINAL CONTRACT SUM …………………………………………………………… | [6 empty] | $ | 356000
2. | NET CHANGE BY CHANGE ORDERS…………………………………………………. | [6 empty] | $ | 4283.77 |  | CONTRACTOR: A&A Mechanical, LLC.
3. | CONTRACT SUM TO DATE (Line 1 ± 2)……………………………………………. | [6 empty] | $ | 360283.77 |  | By:
4. | TOTAL COMPLETED & STORED TO DATE (Column G on G703)…………………………………………… | [6 empty] | $ | 356133.77 |  | State of: Louisiana
5. | RETAINAGE: | [9 empty] | County of: Orleans
| a. | 10% | of Completed Work | [7 empty] | Subscribed and sworn to before
|  | (Column D + E on G703) |  |  | $ | 35613.377 |  |  |  |  | me this day of 2024
| b. | 10% | of Stored Material | [7 empty] | Notary Public:
|  | (Included in line 5a.) |  |  | $ | 0 |  |  |  |  | My Commission expires: At Death
| Total Retainage (Lines 5a + 5b or Total in Column I of G703……………………… | [6 empty] | $ | 35613.377
6. | TOTAL EARNED LESS RETAINAGE ……………………………………………………… | [6 empty] | $ | 320520.393 |  | ARCHITECT'S CERTIFICATE FOR PAYMENT
|  | (Line 4 Less Line 5 Total) | [8 empty] | In accordance with the Contract Documents, based on on-site observations and the data comprising this application, the Architect certifies to the Owner that to the best of the Architect's knowledge, information and belief the Work has progressed as indicated, the quality of the Work is in accordance with the Contract Documents, and the Contractor is entitled to payment of the AMOUNT CERTIFIED.
7. | LESS PREVIOUS CERTIFICATES FOR PAYMENT ……………………………………………………… | [6 empty] | $ | 143003.1
(Line 6 from prior Certificate)
8a | LESS TAX SAVINGS FOR OWNER |  |  | ………………………………….. |  |  |  | $ |  | 0
8b. | LESS INVOICES PAID BY OWNER |  |  | …………………………………. |  |  |  | $ |  | 0
8. | CURRENT PAYMENT DUE……………………………………………………………….. | [6 empty] | $ | 177517.293
9. | BALANCE TO FINISH, INCLUDING RETAINAGE | [9 empty] | AMOUNT CERTIFIED…..……………………………………………………………. $
|  | (Line 3 less Line 6) |  |  | $ | 39763.377 |  |  |  |  | (Attach explanation if amount certified differs from the amount applied. Initial all figures on this Application and on the Continuation Sheet that are changed to conform with amount certified.)
CHANGE ORDER SUMMARY |  |  |  |  | ADDITIONS |  |  | DEDUCTIONS
Total changes approved in previous months by Owner |  |  |  |  | $ | 4283.77 |  | $ |  | 0 | By: | ________________________________________________ Date: _________________
Total approved this Month |  |  |  |  | $ | 0 |  | $ |  | 0 | This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the Contractor named herein. Issuance, payment and acceptance of payment are without prejudice to any rights of the Owner or Contractor under this Contract.
|  |  |  | TOTALS | $ | 4283.77 |  | $ |  | 0
NET CHANGES by Change Order |  |  |  |  | $ |  | 4283.77
™
Document G702 − 1992
AIA

## Sheet1
4150 | 0
320520.393 | 0
143003.1

## S-O-V
| DOCUMENT, APPLICATION AND CERTIFICATION FOR PAYMENT | [5 empty] | DATE : | 2024-08-13
| Job Name |  |  | Application #4 |  | JOB# 6215 | THRU | 2024-08-23
| Boyet Jr. High HVAC replace | Scheduled | Previous | This | Stored Mat |  | ARCHITECTS PROJECT#
ITEM | DESCRIPTION | Value | Application | Application | This App | TOTAL | % COMP | BAL TO FIN | RETAINAGE
1 | General Conditions | 10626.55 | 7437.62 | 3188.93 | 0 | 10626.55 | 100% | 0 | 318.893
2 | Bond | 6134.31 | 6134.31 | 0 | 0 | 6134.31 | 100% | 0 | 0
3 | Permits | 8685.54 | 8685.54 | 0 | 0 | 8685.54 | 100% | 0 | 0
4 | Mobilization | 7120 | 5360 | 1760 | 0 | 7120 | 100% | 0 | 176
5 | Demolition | 4542.98 | 1200 | 3342.98 | 0 | 4542.98 | 100% | 0 | 334.298
6 | Security Ladders | 7980.24 | 7980.24 | 0 | 0 | 7980.24 | 100% | 0 | 0
7 | Roofing | 14362.5 | 7181 | 7181.5 | 0 | 14362.5 | 100% | 0 | 718.15
8 | Structurtal Platforms | 57418.5 | 19140 | 38278.5 | 0 | 57418.5 | 100% | 0 | 3827.85
9 | Sheet metal work | 53544 | 15000 | 38544 | 0 | 53544 | 100% | 0 | 3854.4
10 | Electrical work | 32200 | 5000 | 27200 | 0 | 32200 | 100% | 0 | 2720
11 | Rooftop Units | 34057.36 | 34057.36 | 0 | 0 | 34057.36 | 100% | 0 | 0
12 | Split Systems | 34074.36 | 15000 | 19074.36 | 0 | 34074.36 | 100% | 0 | 1907.436
13 | Spiral Duct work | 12527.53 | 0 | 12527.53 | 0 | 12527.53 | 100% | 0 | 1252.753
14 | Grills | 3056.37 | 3056.37 | 0 | 0 | 3056.37 | 100% | 0 | 0
15 | Louvers/w motorized dmpr | 1762.57 | 0 | 1762.57 | 0 | 1762.57 | 100% | 0 | 176.257
16 | Insulation | 32085 | 10000 | 22085 | 0 | 32085 | 100% | 0 | 2208.5
17 | Rigging and Hoisting | 6670 | 0 | 6670 | 0 | 6670 | 100% | 0 | 667
18 | Supervisiion | 22765.98 | 13659.57 | 4956.41 | 0 | 18615.98 | 82% | 4150 | 495.641
19 | A/C Condensate Drains | 3942.46 | 0 | 3942.46 | 0 | 3942.46 | 100% | 0 | 394.246
20 | Test & Balance | 2443.75 | 0 | 2443.75 | 0 | 2443.75 | 100% | 0 | 244.375
21 | CO#1 Painting | 1771 | 0 | 1771 | 0 | 1771 | 100% | 0 | 177.1
22 | CO#1 Fencing | 2512.77 | 0 | 2512.77 | 0 | 2512.77 | 100% | 0 | 251.277
| TOTALS | 360283.77 | 158892.01 | 197241.76 | 0 | 356133.77 | 98.85% | 4150 | 19724.176
[6 empty] | Amount due this application |  |  | 177517.584

## G703 (hidden)
Continuation Sheet
AIA Document G702 - 1992, Application and Certification for Payment, or G736 - 2009, | [5 empty] | APPLICATION NO: |  | 4
Project Application and Project Certificate for Payment, Construction Manager as Adviser Edition, | [5 empty] | APPLICATION DATE: |  | 2020-07-21
containing Contractor's signed certification is attached. | [5 empty] | PERIOD TO: |  | 2020-07-31
In tabulations below, amounts are in US dollars. | [5 empty] | ARCHITECT'S PROJECT NO: |  | 1900501
Use Column I on Contracts where variable retainage for line items may apply.
A | B | C | D | E | F | G |  | H | I
ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  | MATERIALS PRESENTLY STORED (NOT IN D OR E) | TOTAL COMPLETED AND STORED TO DATE (D+E+F) | % (G ÷ C) | BALANCE TO FINISH (C - G) | RETAINAGE (IF VARIABLE RATE)
|  |  | FROM PREVIOUS APPLICATION (D + E) | THIS PERIOD
100 | Mobilization | 5000 | 0 | 2500 |  | 2500 | 50% | 2500 | 250
200 | Close Out Documents | 500 | 0 | 0 |  | 0 | 0% | 500 | 0
300 | Grease Trap (Material) | 14000 | 0 | 0 |  | 0 | 0% | 14000 | 0
400 | Grease Trap Installation (Labor) | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
500 | Natural Gas (Material) | 40000 | 0 | 25000 |  | 25000 | 62.5% | 15000 | 2500
600 | Natural Gas (Labor) | 16000 | 0 | 10400 |  | 10400 | 65% | 5600 | 1040
700 | Fire / Domestic Water Tie-in (Material) | 31000 | 0 | 0 |  | 0 | 0% | 31000 | 0
800 | Fire / Domestic Water Tie-in (Labor) | 12000 | 0 | 0 |  | 0 | 0% | 12000 | 0
900 | U/G Sanitary Sewer (Material) | 4500 | 0 | 0 |  | 0 | 0% | 4500 | 0
1000 | U/G Sanitary Sewer (Labor) | 5500 | 0 | 0 |  | 0 | 0% | 5500 | 0
1100 | A/G Sanitary Sewer & Vent (Material) | 4000 | 0 | 0 |  | 0 | 0% | 4000 | 0
1200 | A/G Sanitary Sewer & Vent (Labor) | 7000 | 0 | 0 |  | 0 | 0% | 7000 | 0
1300 | Greasy Waste (Material) | 3000 | 0 | 0 |  | 0 | 0% | 3000 | 0
1400 | Greasy Waste (Labor) | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
1600 | Roof Drainage (Material) | 16500 | 0 | 0 |  | 0 | 0% | 16500 | 0
1700 | Roof Drainage (Labor) | 17000 | 0 | 0 |  | 0 | 0% | 17000 | 0
1800 | Domestic Water (Material) | 3000
1900 | Domestic Water (Labor) | 4000 | 0 | 0 |  | 0 | 0% | 4000 | 0
2000 | Heat Trace | 3000
2100 | Roof Top Units (Material) | 67500 | 0 | 0 |  | 0 | 0% | 67500 | 0
2200 | Roof Top Units ( Misc Labor) | 1000 | 0 | 0 |  | 0 | 0% | 1000 | 0
2300 | Roof Top Units (Rig & Hoist) | 28000 | 0 | 0 |  | 0 | 0% | 28000 | 0
2400 | Exhaust Fans (Material) | 1500 | 0 | 0 |  | 0 | 0% | 1500 | 0
2500 | Exhaust Fans (Labor) | 300 | 0 | 0 |  | 0 | 0% | 300 | 0
2600 | Sheetmetal | 11700 | 0 | 0 |  | 0 | 0% | 11700 | 0
2700 | Insulation | 15000
| GRAND TOTAL | 318900 | 0 | 37900 | 0 | 37900 | 11.88% | 260000 | 3790
™
Document G703 − 1992
AIA