## Sheet1
Number |  |  | Distribution |  |  |  |  | Title | Vendor or Subcontractor | Received |  | Returned |  |  | Response |  |  |  | Allow 15 business days for review of each submittal
Specification Number | Submittal Item No. | Resubmittal No. | A | S | M | E | P |  |  | Date Received | Copies or Electronic (E) | Date Sent | Copies Returned | Date Due Back | Reviewed | Reviewed as Noted | Revise & Resubmit | Rejected
Comments
033000 | 001 | 0 | [5 empty] | Cast in Place Concrete |  | 2024-01-26 |  | 2024-02-02 |  | 2024-02-05 | x
085000 | 001 | 0 | [5 empty] | Windows |  | 2024-01-26 |  |  |  | 2024-02-05
102113 | 001 | 0 | [5 empty] | Toilet Compartments |  | 2024-01-26 |  |  |  | 2024-02-05
102800 | 001 | 0 | [5 empty] | Toilet, Bath & Laundry Acc |  | 2024-01-26 |  |  |  | 2024-02-05
103000 | 001 | 0 | [5 empty] | Engineered Composites Fabrications |  | 2024-01-26 |  |  |  | 2024-02-05
104416 | 001 | 0 | [5 empty] | Fire Extinguishers |  | 2024-01-26 |  |  |  | 2024-02-05
220000 | 001 | 0 | [5 empty] | Plumbing |  | 2024-01-26 |  |  |  | 2024-02-05
260000 | 001 | 0 | [5 empty] | Electrical - Distribution Equipment |  | 2024-01-26 |  | 2024-01-30 |  | 2024-02-05 |  | x
260000 | 002 | 0 | [5 empty] | Electrical - Light Fixtures |  | 2024-01-26 |  | 2024-01-31 |  | 2024-02-05 | x
321313 | 001 | 0 | [5 empty] | Concrete Pavement |  | 2024-01-26 |  | 2024-02-02 |  | 2024-02-05 | x
133419 | 001 | 0 | [5 empty] | Metal Building |  | 2024-02-07 |  | 2024-02-08 |  | 2024-02-17 | x
133419 | 002 | 0 | [5 empty] | Building Insulation |  | 2024-02-07 |  | 2024-02-08 |  | 2024-02-17 | x
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
1900-01-09
Formulas:
Date Due Back = [Received]+10